## FTTH
Customer Details | Cluster | Work Order ID | Contractor | Date logged | Date of payment/Start Date | HP Cost ( Services + MTN Materials) | HC cost ( Services+ MTN Materials) | Service Costs Ugx (HP Services + HC Services) | Total Costs Ugx | Installation Delay ( Days) | Installation Status | Planned End Date | Activation status | Actual End Date | Total MTTi | MTTi After Payment | Issues ( Remarks) | Snags | Homes Passed
null null. 256772649913. OLD KAMPALA.0.37371232.660769. FTTH_10_M | Bweyogerere | MTNFTTH75128522 | Enetworks | 2023-04-02 | 2023-04-02 | 0 | 698345.6 | 480275 | 698345.6 | 0 | Done | 2023-04-04 | On air | 2023-04-04 | 2 | 2 |  |  | 10
null null. 256772121452. Kulambiro Ring Road.0.37367532.606814. FTTH_10_M | Kisaasi | MTNFTTH67168145 | Enetworks | 2023-04-02 | 2023-04-02 | 0 | 698345.6 | 480275 | 698345.6 | 0 | Done | 2023-04-04 | On Air | 2023-04-04 | 2 | 2 |  |  | 10
null null. 256771432154. Mbalwa.0.36518232.653176. FTTH_10_M | Bweyogerere | MTNFTTH84862451 | Enetworks | 2023-04-02 | 2023-04-02 | 0 | 832424.6 | 614354 | 832424.6 | 0 | Done | 2023-04-04 | On Air | 2023-04-03 | 1 | 1 |  |  | 4
null null . 256772122095. Kyanja Ring Road. 0.388722 32.596013. FTTH_10_M | Kisaasi | MTNFTTH66035684 | Enetworks | 2023-03-15 | 2023-04-01 | 0 | 660366 | 442295 | 660365.6 | 0 | Done | 2023-04-03 | On air | 2023-04-04 | 20 | 3 |  |  | 0
MICHAEL TWINOKWESIGA. 256787311412. OLD KAMPALA.0.37718732.604425. FTTH_10_M | Kisaasi | MTNFTTH77585252 | Enetworks | 2023-04-02 | 2023-04-02 | 0 | 829763.6 | 609494 | 829763.6 | 0 | Done | 2023-04-04 | On air | 2023-04-04 | 2 | 2 |  |  | 0
WINNIE KARUNGI. 256762333844. Akright Estate bwebajja. 0.157488,32.544707. FTTH_10_M | Bwebajja | MTNFTTH24010127 | Chrif | 2023-04-05 | 2023-04-05 | 229065 | 576956 | 576956 | 806022 | 0 | Done | 2023-04-07 | On Air | 2023-04-05 | 0 | 0 |  |  | 2
ABDU SSEKALALA. 256779154759. 0.387362,32.598603. FTTH_40_M | Kisaasi | MTNFTTH46346240 | Enetworks | 2023-04-04 | 2023-04-04 | 0 | 859436.6 | 623774 | 859436.6 | 0 | Done | 2023-04-06 | On Air | 2023-04-05 | 1 | 1 |  |  | 2
null null. 256772642435. Makerere Kikoni.0.34271432.561313. FTTH_10_M | Makerere | MTNFTTH54260688 | Chrif | 2023-04-01 | 2023-04-01 | 0 | 0 | 1786875 | 2429794.5 | 0 | Done | 2023-04-03 | On Air | 2023-04-06 | 5 | 5 |  |  | 6
null null. 256777717920. Ebony Villas.0.175932.517883. FTTH_10_M | Bwebajja | MTNFTTH80432574 | Chrif | 2023-04-02 | 2023-04-02 | 2193550 | 590131 | 1939000 | 2783681 | 0 | Done | 2023-04-04 | On Air | 2023-04-06 | 4 | 4 |  |  | 2
null null. 256763430154. OLD KAMPALA.0.31103232.644218. FTTH_10_M | Luzira | MTNFTTH74130714 | Enetworks | 2023-04-02 | 2023-04-02 | 0 | 808568.6 | 599294 | 808568.6 | 0 | Done | 2023-04-04 | On Air | 2023-04-06 | 4 | 4 |  |  | 4
null null. 256772449928. Eseri Complex Ntinda.0.35801932.614396. FTTH_10_M | Ntinda Kiwatule | MTNFTTH03633004 | Enetworks | 2023-04-03 | 2023-04-03 | 0 | 846719.6 | 617654 | 856719.6 | 0 | Done | 2023-04-05 | On Air | 2023-04-07 | 4 | 4 |  |  | 4
null null. 256788343186. OLD KAMPALA.0.24570232.614958. FTTH_10_M | Ggaba | MTNFTTH27316162 | Rontech | 2023-04-03 | 2023-04-03 | 208750 | 782695 | 743670 | 991445 | 0 | Done | 2023-04-05 | On Air | 2023-04-06 | 3 | 3 |  |  | 0
null null. 256784041012. OLD KAMPALA.0.31159632.557911. FTTH_20_M | Rubaga | MTNFTTH17051604 | Rontech | 2023-04-03 | 2023-04-03 | 2509237 | 709346.5 | 2954778.5 | 3218583.5 | 0 | Done | 2023-04-05 | On Air | 2023-04-06 | 3 | 3 |  |  | 1
null null. 256774178190. Bunga.0.2727832.622696. FTTH_20_M | Ggaba | MTNFTTH31787602 | Rontech | 2023-04-03 | 2023-04-03 | 2509237 | 709346.5 | 2954778.5 | 3218583.5 | 0 | Done | 2023-04-05 | On Air | 2023-04-06 | 3 | 3 |  |  | 7
null null. 256762929398. Namugera Drive.0.38934232.602031. FTTH_10_M | Kisaasi | MTNFTTH68157676 | Enetworks | 2023-04-03 | 2023-04-03 | 0 | 754321.6 | 424835 | 754321.6 | 0 | Done | 2023-04-05 | On Air | 2023-04-05 | 2 | 2 |  |  | 0
null null. 256776747882. KITGUM.0.358913,32.637857. FTTH_20_M_O | Ntinda Kiwatule | MTNFTTH82778188 | Enetworks | 2023-04-02 | 2023-04-02 | 1074438 | 517230.6 | 1107300 | 1591668.6 | 0 | Done | 2023-04-04 | On Air | 2023-04-06 | 4 | 4 |  |  | 6
null null. 256777588113. Ndere Cultural Centre.0.363351,32.605806. FTTH_10_M | Ntinda Kiwatule | MTNFTTH65051234 | Enetworks | 2023-04-03 | 2023-04-03 | 0 | 956267.6 | 742595 | 956267.6 | 0 | Done | 2023-04-05 | On Air | 2023-04-06 | 3 | 3 |  |  | 4
null null. 256787175726. Florida Apartments.0.402616,32.652336. FTTH_10_M | Kira | MTNFTTH15875071 | Enetworks | 2023-04-04 | 2023-04-04 | 2067746 | 535841.25 | 2075454.75 | 2603587.5 | 0 | Done | 2023-04-06 | On Air | 2023-04-07 | 3 | 3 |  |  | 3
Rose Sente. 256772408718. OLD KAMPALA.0.405838,32.655798. FTTH_20_M | Kira | MTNFTTH07002006 | Enetworks | 2023-04-04 | 2023-04-04 | 2067746 | 535841.25 | 2075454.75 | 2603587.5 | 0 | Done | 2023-04-06 | On Air | 2023-04-07 | 3 | 3 |  |  | 3
null null. 256772200932. Florida Apartments.0.402616,32.652336. FTTH_20_M | Kira | MTNFTTH76533058 | Enetworks | 2023-04-04 | 2023-04-04 | 2067746 | 535841.25 | 2075454.75 | 2603587.5 | 0 | Done | 2023-04-06 | On Air | 2023-04-07 | 3 | 3 |  |  | 3
null null. 256770899096. Namugongo.0.388827,32.654827. FTTH_10_M | Sonde | MTNFTTH26282262 | Enetworks | 2023-04-04 | 2023-04-04 | 0 | 638984.6 | 418715 | 638984.6 | 0 | Done | 2023-04-06 | On Air | 2023-04-06 | 2 | 2 |  |  | 12
GODFREY OMUNO. 256772000892. Mpererwe.0.381891,32.576158. FTTH_10_M | Gayaza | MTNFTTH61672760 | Enetworks | 2023-04-05 | 2023-04-05 | 4178566.8 | 538727 | 220562.5 | 1101712.5 | 0 | Done | 2023-04-07 | On Air | 2023-04-07 | 2 | 2 |  |  | 12
JOHNSON NATUHWERA. 256779104995. Kira Town.0.397225,32.638695. FTTH_20_M | Kira | MTNFTTH24075826 | Enetworks | 2023-04-05 | 2023-04-05 | 2067746 | 535841.25 | 2075454.75 | 2603587.5 | 0 | Done | 2023-04-07 | On Air | 2023-04-07 | 2 | 2 |  |  | 3
GRACE DAVIS WAMPA. 256780259023. OLD KAMPALA.0.387718,32.640524. FTTH_20_M | Kira | MTNFTTH62102365 | Enetworks | 2023-04-05 | 2023-04-05 | 0 | 432214.5 | 115632 | 432214.5 | 0 | Done | 2023-04-07 | On Air | 2023-04-06 | 1 | 1 |  |  | 15
CATHERINe NINSIIMA. 256779494473. OLD KAMPALA.0.365502,32.626671. FTTH_10_M | Ntinda Kiwatule | MTNFTTH64508374 | Enetworks | 2023-04-05 | 2023-04-05 | 704992 | 517230.6 | 737854 | 1222222.6 | 0 | Done | 2023-04-07 | On Air | 2023-04-06 | 1 | 1 |  |  | 6
null null. 256775425140. OLD KAMPALA.0.287824,32.625449. FTTH_20_M | Ggaba | MTNFTTH62142734 | Rontech | 2023-04-03 | 2023-04-03 | 789529 | 977530 | 1478237 | 1767059 | 0 | Done | 2023-04-05 | On Air | 2023-04-08 | 5 | 5 |  |  | 7
ABDULLAHI OSMAN MOHAMOUD. 256786258600. Security 2000 Ltd..0.30602632.604837. FTTH_10_M | Namuwongo | MTNFTTH08647227 | Rontech | 2023-04-01 | 2023-04-01 | 1249783 | 783328 | 1718635 | 2033111 | 0 | Done | 2023-04-03 | On Air | 2023-04-08 | 7 | 7 | ROW issue |  | 2
null null. 256776222939. Lweza Kampala - Entebbe Rd.0.22586532.553603. FTTH_20_M | Najjanankumbi | MTNFTTH12733575 | Rontech | 2023-04-01 | 2023-04-01 | 789529 | 724609 | 1278091 | 1514138 | 0 | Done | 2023-04-03 | On Air | 2023-04-11 | 10 | 10 | ROW issue |  | 2
null null. 256777221773. KITGUM.0.32074832.563257. FTTH_10_M | Rubaga | MTNFTTH14331700 | Chrif | 2023-04-02 | 2023-04-02 | 417176 | 1553948 | 1632108 | 1971124 | 0 | Done | 2023-04-04 | On Air | 2023-04-10 | 8 | 8 | Located at Najjanakumbi - Chrif handling |  | 5
Mohamed Ibrahim. 256789789717. Nakulabye Pride microfinance.0.318932.5981. FTTH_10_M | Makerere | MTNFTTH06380155 | Chrif | 2023-04-02 | 2023-04-02 | 218070.6 | 474650 | 474650 | 692721 | 0 | Done | 2023-04-04 | On Air | 2023-04-07 | 5 | 5 |  |  | 5
null null. 256779635803. MTN Mutundwe Data Center.0.28669232.534207. FTTH_10_M | Rubaga | MTNFTTH45854712 | Rontech | 2023-04-02 | 2023-04-02 | 841642 | 673774 | 1293295 | 1515415 | 0 | Done | 2023-04-04 | On Air | 2023-04-10 | 8 | 8 | Delayed Access to Mutundwe |  | 6
null null. 256784294795. Mbalwa Police Post.0.36312232.654505. FTTH_20_M | Bweyogerere | MTNFTTH87751775 | Enetworks | 2023-04-03 | 2023-04-03 | 2473038.3333 | 578591 | 2419532.6667 | 2971829.3333 | 0 | Done | 2023-04-05 | On Air | 2023-04-08 | 5 | 5 |  |  | 6
null null. 256770539653. Buwate.0.40505932.619267. FTTH_20_M | Buwate | MTNFTTH84510788 | Enetworks | 2023-04-03 | 2023-04-03 | 1817240.8 | 517230.6 | 1677130 | 2334471.4 | 0 | Done | 2023-04-05 | On Air | 2023-04-09 | 6 | 6 | SYSTEM ISSUE |  | 24
null null. 256770524975. Salama road lekana stage.0.265004,32.595753. FTTH_10_M | Ggaba | MTNFTTH47632885 | Rontech | 2023-04-03 | 2023-04-03 | 789529 | 680408 | 1222162 | 1469937 | 0 | Done | 2023-04-05 | On Air | 2023-04-08 | 5 | 5 |  |  | 1
null null. 256761055015. Rubis Kansanga Service Station.0.291152,32.605721. FTTH_20_M | Ggaba | MTNFTTH56672364 | Rontech | 2023-04-04 | 2023-04-04 | 883969 | 825801 | 1433595 | 1709770 | 0 | Done | 2023-04-06 | On Air | 2023-04-08 | 4 | 4 |  |  | 1
JOSEPH SSEMBATYA. 256772123178. OLD KAMPALA.0.37507,32.603729. FTTH_10_M | Kisaasi | MTNFTTH26717548 | Enetworks | 2023-04-05 | 2023-04-05 | 0 | 973180.6 | 746314 | 973180.6 | 0 | Done | 2023-04-07 | On Air | 2023-04-08 | 3 | 3 |  |  | 12
ANNA IYOGIL. 256784415831. SB Homes Bukasa-Muyenga.0.285281,32.627278. FTTH_10_M | Muyenga | MTNFTTH01165606 | Rontech | 2023-04-05 | 2023-04-05 | 789529 | 936601 | 1460767 | 1726130 | 0 | Done | 2023-04-07 | On Air | 2023-04-08 | 3 | 3 |  |  | 7
JOEL WACHA. 256788141349. Kyanja Ring Road.0.388722,32.596013. FTTH_10_M | Kisaasi | MTNFTTH27620772 | Enetworks | 2023-04-05 | 2023-04-05 | 0 | 752187.1 | 537415 | 752187.1 | 0 | Done | 2023-04-07 | On Air | 2023-04-08 | 3 | 3 |  |  | 7
TIMOTHY KASAGA. 256772123312. Pentagon Apartments.0.318144,32.641735. FTTH_10_M | Luzira | MTNFTTH24836631 | Enetworks | 2023-04-05 | 2023-04-05 | 2811230 | 580321 | 2530548 | 3181050.6 | 0 | Done | 2023-04-07 | On Air | 2023-04-08 | 3 | 3 |  |  | 23
OTIM APIO. 256785304654. ABJA ESTATES LTD.0.364338,32.59569. FTTH_20_M | Kisaasi | MTNFTTH24478040 | Enetworks | 2023-04-05 | 2023-04-05 | 791979 | 531031 | 1102740 | 1323009.6 | 0 | Done | 2023-04-07 | On Air | 2023-04-07 | 2 | 2 |  |  | 4
REBECCA SENOGA. 256772468282. Nican Resort Hotel.0.229229,32.54397. FTTH_10_M | Najjanankumbi | MTNFTTH10628486 | Rontech | 2023-04-05 | 2023-04-05 | 1114534 | 863347 | 1742392 | 1977882 | 0 | Done | 2023-04-07 | On Air | 2023-04-10 | 5 | 5 |  |  | 4
MAXWELL AKORA. 256788075447. OLD KAMPALA.0.079846,32.471008. FTTH_20_M | Entebbe | MTNFTTH26717847 | Chrif | 2023-04-06 | 2023-04-06 | 0 | 550692 | 337020 | 550692 | 0 | Done | 2023-04-08 | On Air | 2023-04-08 | 2 | 2 |  |  | 3
JUSTINE NAMUGULA. 256778117924. OLD KAMPALA.0.248513,32.612025. FTTH_10_M | Ggaba | MTNFTTH51121261 | Rontech | 2023-04-06 | 2023-04-06 | 789529 | 899283 | 1423445 | 1688812 | 0 | Done | 2023-04-08 | On Air | 2023-04-08 | 2 | 2 |  |  | 8
Chris Kimera. 256773119430. 5a Kisota 001, Kampala, Uganda.0.365736,32.598909. FTTH_10_M | Kisaasi | MTNFTTH14375131 | Enetworks | 2023-04-06 | 2023-04-06 | 0 | 890719.6 | 661654 | 890719.6 | 0 | Done | 2023-04-08 | On Air | 2023-04-09 | 3 | 3 |  |  | 0
FLORENCE NAMUGANZA. 256777699969. Kisaasi.0.361441,32.596655. FTTH_10_M | Kisaasi | MTNFTTH88510638 | Enetworks | 2023-04-06 | 2023-04-06 | 1050945 | 487031 | 1125679 | 1537975.6 | 0 | Done | 2023-04-08 | On Air | 2023-04-09 | 3 | 3 |  |  | 3
null null. 256761404684. OLD KAMPALA.0.380072,32.598195. FTTH_10_M | Kisaasi | MTNFTTH84241477 | Enetworks | 2023-04-06 | 2023-04-06 | 0 | 948241.6 | 723574 | 948241.6 | 0 | Done | 2023-04-08 | On Air | 2023-04-08 | 2 | 2 |  |  | 4
SANDRA PATRICIA ANENA. 256788658353. OLD KAMPALA.0.311953,32.653081. FTTH_20_M | Luzira | MTNFTTH42810101 | Enetworks | 2023-04-07 | 2023-04-07 | 0 | 627091.6 | 679574 | 904241.6 | 0 | Done | 2023-04-09 | On Air | 2023-04-08 | 1 | 1 |  |  | 0
Akech Ngong. 256778511772. OLD KAMPALA.0.371549,32.70349. FTTH_20_M | Seeta | MTNFTTH57265713 | Enetworks | 2023-04-07 | 2023-04-07 | 2044455.6 | 531031 | 2033460 | 2575486.2 | 0 | Done | 2023-04-09 | On Air | 2023-04-08 | 1 | 1 |  |  | 2
Ngonzi Henry. 256775894282. Kisaasi:Kyanja Ring Road. 0.38717,32.603768. FTTH_10_M | Kisaasi | MTNFTTH34755333 | Enetworks | 2022-02-18 | 2023-04-09 | 1513658.2 | 487031 | 1545149 | 2000688.8 | 0 | Done | 2023-04-11 | On Air | 2023-04-10 | 416 | 1 |  |  | 14
Saron. 256762017530. 20a Pope Paul Rd, Kampala, Uganda Kabusu Kabusu round about. 0.297098,32.556856.FTTH_20_M | Ndeeba | MTNFTTH58152357 | Rontech | 2023-03-23 | 2023-04-04 | 2108663 | 687189 | 2554499 | 2795853 | 0 | Done | 2023-04-06 | On Air | 2023-04-10 | 18 | 6 |  |  | 7
null null. 256775207420. Kitende.0.232.533333. FTTH_10_M | Kajjansi | MTNFTTH50101553 | Chrif | 2023-04-02 | 2023-04-02 | 4356562.4 | 1529920.2 | 3174635.5714 | 4204630.4286 | 0 | Done | 2023-04-04 | On Air | 2023-04-11 | 9 | 9 | Consolidation WIP |  | 5
DIANA ONDOGA. 256776878918. Mutongo. 0.32225532.642623. FTTH_10_M | Luzira | MTNFTTH11153132 | Enetworks | 2023-04-03 | 2023-04-03 | 3730418.2 | 517231 | 3431749 | 4247648.8 | 0 | Done | 2023-04-05 | On Air | 2023-04-10 | 7 | 7 | ROW issue |  | 14
null null. 256772959645. OLD KAMPALA.0.27651,32.601072. FTTH_10_M | Ggaba | MTNFTTH86488338 | Rontech | 2023-04-04 | 2023-04-04 | 2059640.5 | 611446.5 | 2243733 | 2671087 | 0 | Done | 2023-04-06 | On Air | 2023-04-11 | 7 | 7 | Contact unavailable |  | 9
NANCY MUSISI. 256771860834. Kisaasi:Kulambiro. 0.391366,32.6122. FTTH_10_M | Kisaasi | MTNFTTH60157180 | Enetworks | 2022-02-22 | 2023-04-09 | 589930.5 | 429231 | 646794 | 1019161.1 | 0 | Done | 2023-04-11 | On Air | 2023-04-11 | 413 | 2 |  |  | 2
null null. 256772479796. 5a Rock Cl.0.36839332.607828. FTTH_20_M | Kisaasi | MTNFTTH82102786 | Enetworks | 2023-04-03 | 2023-04-03 | 0 | 1200524.1 | 968160 | 1200524 | 0 | Done | 2023-04-05 | On Air | 2023-04-11 | 8 | 8 | ROW issue |  | 4
null null. 256776911119. Katale Seguku.0.233668,32.545845. FTTH_10_M | Najjanankumbi | MTNFTTH32873385 | Rontech | 2023-04-04 | 2023-04-04 | 2250511.7778 | 396258.8889 | 2572838.8889 | 2646770.6667 | 0 | Done | 2023-04-06 | On Air | 2023-04-11 | 7 | 7 | The client had ROW issuess (Among the consolidated clients) |  | 3
SHEILA TEKITENDWA. 256771339872. Kabowa Church of Uganda Primary School.0.283439,32.556667. FTTH_10_M | Muyenga | MTNFTTH02751647 | Rontech | 2023-04-05 | 2023-04-05 | 2287763 | 805349 | 2857623 | 3093113 | 0 | Done | 2023-04-07 | On Air | 2023-04-13 | 8 | 8 |  |  | 11
CHARLES DOMINIC ONGOM. 256771257724. Luzira Prison.0.300157,32.640285. FTTH_10_M | Luzira | MTNFTTH07813256 | Enetworks | 2023-04-05 | 2023-04-05 | 871953 | 531031 | 1171719 | 1402983.6 | 0 | Done | 2023-04-07 | On Air | 2023-04-14 | 9 | 9 | ROW issue |  | 21
KAY ADOCH. 256762228828. OLD KAMPALA.0.255707,32.630867. FTTH_10_M | Ggaba | MTNFTTH54770372 | Rontech | 2023-04-05 | 2023-04-05 | 2541661 | 900531 | 3190386 | 3442192 | 0 | Done | 2023-04-07 | On Air | 2023-04-13 | 8 | 8 | ROW with neighbours |  | 3
HOPE BABIRYE. 256774566590. Tirupati Mazima Mall.0.299592,32.596384. FTTH_10_M | Muyenga | MTNFTTH12442856 | Rontech | 2023-04-05 | 2023-04-05 | 894398 | 740792 | 1364393 | 1635190 | 0 | Done | 2023-04-07 | On Air | 2023-04-14 | 9 | 9 | Delayedby HLS |  | 20
MUSTAFA BAHTIYAR. 256762738375. JINJA.0.439819,33.218456. FTTH_10_M | Jinja | MTNFTTH72668312 | Enetworks | 2023-04-06 | 2023-04-06 | 2560973.6667 | 457714 | 2456023 | 3018688 | 5 | Done | 2023-04-08 | On Air | 2023-04-14 | 8 | 3 | HighBOQ, looking for a consolidation |  | 12
GODFREY OMUNO. 256773661319. Kitende.0.2,32.533333. FTTH_10_M | Kajjansi | MTNFTTH80284234 | Chrif | 2023-04-06 | 2023-04-06 | 4247700 | 560014.5 | 2053721.5 | 2403857.5 | 0 | Done | 2023-04-08 | On Air | 2023-04-11 | 5 | 5 |  |  | 6
SIMON OJENGO. 256778112717. Nile International Hospital.0.439952,33.218515. FTTH_10_M | Jinja | MTNFTTH16706660 | Enetworks | 2023-04-06 | 2023-04-06 | 5609732 | 457714 | 562665 | 3018688 | 5 | Done | 2023-04-08 | On Air | 2023-04-14 | 8 | 3 | High BOQ, looking for a consolidation |  | 13
SIMON MUGOYA. 256762895821. Kironde Road.0.297216,32.614705. FTTH_10_M | Muyenga | MTNFTTH76172207 | Rontech | 2023-04-06 | 2023-04-06 | 1695313 | 776420 | 2265005 | 2471733 | 0 | Done | 2023-04-08 | On Air | 2023-04-13 | 7 | 7 | The custodian's approval was required. |  | 4
MUSA MAKYA KYAMPA. 256761076635. Step By Step P/S.0.383743,32.594464. FTTH_10_M | Kisaasi | MTNFTTH77221707 | Enetworks | 2023-04-06 | 2023-04-06 | 672696 | 531031 | 976860 | 1203726.6 | 4 | Done | 2023-04-08 | On Air | 2023-04-14 | 8 | 4 | On hold. Waiting for caretaker's support |  | 5
DAVID OMUGETHUM. 256770414746. Seguku.0.237516,32.541173. FTTH_10_M | Najjanankumbi | MTNFTTH08072435 | Rontech | 2023-04-07 | 2023-04-07 | 2294899.5 | 547974.5 | 2438255.5 | 2842874 | 0 | Done | 2023-04-09 | On Air | 2023-04-13 | 6 | 6 | Delayed due to Customer unavailability |  | 4
ENOCK ATWEBEMBEIRE. 256780162396. OLD KAMPALA.0.341003,32.656778. FTTH_10_M | Bweyogerere | MTNFTTH35828424 | Enetworks | 2023-04-07 | 2023-04-07 | 2015954 | 465031 | 1780400 | 2480984.6 | 0 | Done | 2023-04-09 | On Air | 2023-04-11 | 4 | 4 |  |  | 8
SAMUEL NSUBUGA. 256783558333. Bulabira Road.0.379962,32.622687. FTTH_20_M | Ntinda kiwatule | MTNFTTH44678533 | Enetworks | 2023-04-07 | 2023-04-07 | 2161134.8 | 443031 | 1802680 | 2604165.4 | 0 | Done | 2023-04-09 | On Air | 2023-04-12 | 5 | 5 |  |  | 12
AHMED MOHAMED ELMUNIR AHMED SAFIELDIN M A AWA. 256787372249. 8a York Terrace.0.329103,32.59756. FTTH_40_M | Kololo | MTNFTTH28423274 | Chrif | 2023-04-08 | 2023-04-08 | 0 | 574949 | 352480 | 574949 | 8 | Done | 2023-04-10 | On Air | 2023-04-14 | 6 | -2 |  |  | 5
LILIAN MPINGA. 256772499307. OLD KAMPALA.0.399987,32.682404. FTTH_20_M | Sonde | MTNFTTH74812616 | Enetworks | 2023-04-09 | 2023-04-09 | 962957 | 465031 | 1117559 | 1427987.6 | 0 | Done | 2023-04-11 | On Air | 2023-04-12 | 3 | 3 |  |  | 2
AUGUSTINE OCHIENG. 256789529867. Spire Road.0.425299,33.211912. FTTH_10_M | Jinja | MTNFTTH87506271 | Enetworks | 2023-04-10 | 2023-04-10 | 0 | 1069181.6 | 853310 | 1069181.6 | 0 | Done | 2023-04-12 | On Air | 2023-04-12 | 2 | 2 |  |  | 17
PAUL KABAGAMBE. 256772887165. Naalya Estate.0.367685,32.638646. FTTH_10_M | Ntinda kiwatule | MTNFTTH45217781 | Enetworks | 2023-04-10 | 2023-04-10 | 1513658.2 | 465031 | 1523149 | 1978688.8 | 0 | Done | 2023-04-12 | On Air | 2023-04-14 | 4 | 4 |  |  | 15
IMMACULATE KAGAMBO MUTESI. 256777918230. Mutungo Ring Road.0.315531,32.646261. FTTH_10_M | Luzira | MTNFTTH41303318 | Enetworks | 2023-04-11 | 2023-04-11 | 0 | 705762.6 | 481095 | 705762.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-12 | 1 | 1 |  |  | 7
ALFRED RUTAASYA IBINGIRA. 256772460274. OLD KAMPALA.0.316405,32.645869. FTTH_20_M | Luzira | MTNFTTH28838773 | Enetworks | 2023-04-11 | 2023-04-11 | 1437290 | 465031 | 1525189 | 1902320.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-14 | 3 | 3 |  |  | 12
null null. 256775181988. null. 0.364005,32.607078. FTTH_10_M | Ntinda Kiwatule | MTNFTTH34638558 | Enetworks | 2023-04-07 | 2023-04-07 | 0 |  | 3583500 | 4222080 | 0 | Done | 2023-04-09 | On Air | 2023-04-12 | 5 | 5 |  |  | 0
MICHAEL KAWUMA. 256773174054. Lungujja Community Health Caring Organisation (LUCOHECO).0.309698,32.541288. FTTH_10_M | Rubaga | MTNFTTH28130322 | Chrif | 2023-04-05 | 2023-04-05 | 2134006 | 584111 | 1916676 | 2718117 | 0 | Done | 2023-04-07 | On Air | 2023-04-14 | 9 | 9 |  |  | 5
ISAAC KAMYA. 256760750681. JINJA.0.439893,33.218478. FTTH_10_M | Jinja | MTNFTTH50170502 | Enetworks | 2023-04-11 | 2023-04-11 | 2560973.6667 | 457714 | 2456023 | 3018688 | 0 | Done | 2023-04-13 | On Air | 2023-04-14 | 3 | 3 |  |  | 13
ANGEL AYEBARE. 256782083131. Kireka.0.337484,32.646896. FTTH_10_M | Bweyogerere | MTNFTTH87704548 | Enetworks | 2023-04-11 | 2023-04-11 | 0 | 800868.6 | 591594 | 800868.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-14 | 3 | 3 |  |  | 0
PETER KATUNDA. 256782206303. Najjera Hospital.0.375081,32.625199. FTTH_10_M | Ntinda kiwatule | MTNFTTH14000760 | Enetworks | 2023-04-11 | 2023-04-11 | 0 | 883824.6 | 665754 | 883824.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-13 | 2 | 2 |  |  | 6
FRED YIGA. 256394715475. OLD KAMPALA.0.3839,32.593892. FTTH_10_M | Kisaasi | MTNFTTH02460376 | Enetworks | 2023-04-12 | 2023-04-12 | 0 | 946334.8 | 490795 | 946334.8 | 0 | Done | 2023-04-14 | On Air | 2023-04-14 | 2 | 2 |  |  | 18
GERALD TOOKEMA. 256781608893. OLD KAMPALA.0.304173,32.546299. FTTH_20_M | Rubaga | MTNFTTH58145536 | Chrif | 2023-04-12 | 2023-04-12 | 643350 | 568366 | 872700 | 1211716 | 0 | Done | 2023-04-14 | On Air | 2023-04-14 | 2 | 2 |  |  | 16
KIRABO SSEGUJJA. 256760820466. OLD KAMPALA.0.387105,32.603841. FTTH_20_M | Kisaasi | MTNFTTH55638222 | Enetworks | 2023-04-12 | 2023-04-12 | 416505 | 509531 | 539375 | 926036 | 0 | Done | 2023-04-14 | On Air | 2023-04-13 | 1 | 1 |  |  | 4
null null 256784219921 Bukoto Bukoto 0.350525 ,32.595242 FTTH_20_M | Ntinda bukoto | MTNFTTH81763404 | Enetworks | 2023-02-28 | 2023-04-11 | 1279970.4 | 465031 | 1318290 | 1745001 | 0 | Done | 2023-04-13 | On Air | 2023-04-12 | 43 | 1 |  |  | 6
null null. 256774095142. Prime General Supply Ntinda. 0.341292,32.621121. FTTH_20_M | Ntinda Bukoto | MTNFTTH74012524 | Enetworks | 2023-03-15 | 2023-04-03 | 2640083 | 564731 | 2504229 | 3204813.6 | 0 | Done | 2023-04-05 | On Air | 2023-04-14 | 30 | 2 |  |  | 6
JONATHAN NKOOLA. 256773410868. Kyanja.0.395861,32.593671. FTTH_40_M | Kisaasi | MTNFTTH27645285 | Enetworks | 2023-04-12 | 2023-04-12 | 612585.6 | 334950 | 560875 | 947535.6 | 0 | Done | 2023-04-14 | On Air | 2023-04-14 | 2 | 2 |  |  | 7
Kelvin Mubanga Musana. 256777431812. OLD KAMPALA.0.309598,32.625124. FTTH_40_M | Bugolobi | MTNFTTH70556688 | Enetworks | 2023-04-12 | 2023-04-12 | 769437.4 | 275850 | 676234 | 1045287.4 | 0 | Done | 2023-04-14 | On Air | 2023-04-14 | 2 | 2 |  |  | 4
GABRIEL KWEBA. 256777997326. Salaama Road. 0.264957,32.595752. FTTH_10_M | Ggaba | MTNFTTH75871707 | ROntech | 2023-04-03 | 2023-04-08 | 789529 | 677079 | 1201241 | 1466608 | 0 | Done | 2023-04-10 | On Air | 2023-04-14 | 11 | 6 | Delayed due to Customer unavailability |  | 5
ADAN HEYDAAR SULEBAN. 256783915716. 0.279903,32.545092. FTTH_40_M | Rubaga | MTNFTTH77715578 | Chrif | 2023-03-27 | 2023-04-11 | 0 | 527281 | 527281 | 1155762 | 0 | Done | 2023-04-13 | On Air | 2023-04-13 | 17 | 2 |  |  | 3
null null. 256760722388. null. 0.385682,32.60279.FTTH_10_M | Kisaasi | MTNFTTH48846652 | Enetworks | 2023-03-21 | 2023-04-11 | 0 | 831346.6 | 617674 | 831346.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-12 | 22 | 1 |  |  | 0
null null. 256787498060. OLD KAMPALA.0.32049532.546112. FTTH_40_M | Rubaga | MTNFTTH28874644 | Rontech | 2023-04-02 | 2023-04-02 | 847329 | 781157 | 1381303 | 1628520 | 0 | Done | 2023-04-04 | On Air | 2023-04-18 | 16 | 16 | Customer not ready for commissioning |  | 2
null null. 256789464969. Muyenga Stage.0.29073,32.621418. FTTH_20_M | Muyenga | MTNFTTH16446450 | Rontech | 2023-04-04 | 2023-04-04 | 1689592 | 1089021 | 2306053 | 2778612 | 10 | Done | 2023-04-06 | On Air | 2023-04-15 | 11 | 1 | Scheduled installation on 14th April |  | 2
MARK BBOSA. 256776802287. Amazon Guest House.0.28657,32.561957. FTTH_10_M | Muyenga | MTNFTTH36461030 | Rontech | 2023-04-06 | 2023-04-06 | 2108663 | 995435 | 2856881 | 3104099 | 0 | Done | 2023-04-08 | On Air | 2023-04-16 | 10 | 10 | Delayed HLS |  | 4
BAKHET ELSADIG. 256761379395. Busiga.0.25,32.616667. FTTH_10_M | Ggaba | MTNFTTH74645671 | Rontech | 2023-04-07 | 2023-04-07 | 2536523 | 727343 | 2977155 | 3263866 | 0 | Done | 2023-04-09 | On Air | 2023-04-17 | 10 | 10 | Delayed HLS |  | 5
PATRICK BYEKWASO. 256774638220. OLD KAMPALA.0.327578,32.604478. FTTH_10_M | Kololo | MTNFTTH23362708 | Enetworks | 2023-04-08 | 2023-04-08 | 1374566.8 | 602031 | 1247184 | 1976597.4 | 0 | Done | 2023-04-10 | On Air | 2023-04-17 | 9 | 9 | ROW with Forest Mall mgt |  | 0
DAPHINE SENTONGO. 256784716836. Kalema houses.0.369538,32.679484. FTTH_10_M | Bweyogerere | MTNFTTH27603838 | Enetworks | 2023-04-08 | 2023-04-08 | 0 | 914302.6 | 691834 | 914302.6 | 0 | Done | 2023-04-10 | On Air | 2023-04-15 | 7 | 7 |  |  | 4
OLIVIA GANKUBA AYESIGA. 256783939117. Canon Road.0.359258,32.620362. FTTH_10_M | Ntinda Bukoto | MTNFTTH28440288 | Enetworks | 2023-04-09 | 2023-04-09 | 2011672 | 531031 | 1984520 | 2542702.6 | 0 | Done | 2023-04-11 | On Air | 2023-04-16 | 7 | 7 | ROW issue |  | 12
SATISH THITTAYAL AYYAR. 256776067553. OLD KAMPALA.0.236107,32.565298. FTTH_40_M | Najjanankumbi | MTNFTTH85288261 | Rontech | 2023-04-08 | 2023-04-08 | 789529 | 807866 | 1308573 | 1597395 | 0 | Done | 2023-04-10 | On Air | 2023-04-17 | 9 | 9 | ROW issue |  | 8
ALLAN SEWALU. 256785457763. OLD KAMPALA.0.254659,32.538511. FTTH_10_M | Najjanankumbi | MTNFTTH70801081 | Rontech | 2023-04-09 | 2023-04-09 | 2537014 | 740681 | 3009613 | 3277695 | 0 | Done | 2023-04-11 | On Air | 2023-04-16 | 7 | 7 | ROW with neighbour |  | 25
ISSA MOITI. 256771611355. Kyaliwajjala - Naalya Road.0.365371,32.637602. FTTH_10_M | Kira | MTNFTTH82417361 | Enetworks | 2023-04-11 | 2023-04-11 | 0 | 927019.6 | 697954 | 927019.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-16 | 5 | 5 |  |  | 24
PAUL MUSAAZI. 256782027689. OLD KAMPALA.0.256884,32.626156. FTTH_10_M | Ggaba | MTNFTTH27471221 | Rontech | 2023-04-11 | 2023-04-11 | 2143405 | 751615 | 2631677 | 2895020 | 0 | Done | 2023-04-13 | On Air | 2023-04-18 | 7 | 7 | ROW with neighbour |  | 5
FRED KAWUKI. 256778385953. Kyaliwajjala Trading Center.0.380597,32.646819. FTTH_10_M | Kira | MTNFTTH18226883 | Enetworks | 2023-04-11 | 2023-04-11 | 0 | 771468.6 | 562194 | 771468.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-16 | 5 | 5 |  |  | 4
Onesimas Mukane. 256779728077. Ndawula Road.0.361001,32.630797. FTTH_20_M | Kisaasi | MTNFTTH24363475 | Enetworks | 2023-04-11 | 2023-04-11 | 909529.2 | 407231 | 861220 | 1316759.8 | 0 | Done | 2023-04-13 | On Air | 2023-04-17 | 6 | 6 |  |  | 10
MUWONGE SADATI. 256772878593. Buwate.0.405059,32.619267. FTTH_10_M | buwate | MTNFTTH57577307 | Enetworks | 2023-04-11 | 2023-04-11 | 473757.6 | 225450 | 426895 | 699207.6 | 0 | Done | 2023-04-13 | On Air | 2023-04-14 | 3 | 3 |  |  | 0
CHRISTINE JOY TUSIIME. 256774773350. Bukasa Close.0.300549,32.611328. FTTH_10_M | Muyenga | MTNFTTH14387136 | Rontech | 2023-04-11 | 2023-04-12 | 1686807 | 816386 | 1444745 | 2503195 | 0 | Done | 2023-04-14 | On Air | 2023-04-18 | 7 | 6 | ROW with the Landlord |  | 5
AARON ERON KABASEKE. 256775931445. Kirabo Complex.0.353465,32.597825. FTTH_10_M | Ntinda Bukoto | MTNFTTH37458522 | Enetworks | 2023-04-12 | 2023-04-13 | 733950.6 | 282750 | 687214 | 1016700.6 | 0 | Done | 2023-04-15 | On Air | 2023-04-16 | 4 | 3 |  |  | 6
NSUBUGA GAKUWA. 256788737821. Kampala City View Guest House (Child Welfare Guest House).0.338399,32.583935. FTTH_10_M | Kololo | MTNFTTH45827222 | Chrif | 2023-04-13 | 2023-04-13 | 974819 | 469834 | 1086579 | 1444653 | 0 | Done | 2023-04-15 | On Air | 2023-04-18 | 5 | 5 |  |  | 3
BAKER MUNTU. 256780599008. OLD KAMPALA.0.388221,32.594461. FTTH_10_M | Kisaasi | MTNFTTH83251384 | Enetworks | 2023-04-13 | 2023-04-13 | 2247045.2 | 627231 | 2202520 | 2874275.8 | 0 | Done | 2023-04-15 | On Air | 2023-04-18 | 5 | 5 |  |  | 20
FRANK KAMANZI. 256780652228. OLD KAMPALA.0.311051,32.641698. FTTH_10_M | Bugolobi | MTNFTTH37054263 | Enetworks | 2023-04-13 | 2023-04-13 | 1546567 | 517231 | 1579429 | 2063797.6 | 0 | Done | 2023-04-15 | On Air | 2023-04-17 | 4 | 4 |  |  | 9
JOSHUA BUSINGE. 256786293950. OLD KAMPALA.0.348313,32.615074. FTTH_20_M | Ntinda Bukoto | MTNFTTH22515468 | Enetworks | 2023-04-13 | 2023-04-13 | 0 | 676707.6 | 404395 | 676707.6 | 0 | Done | 2023-04-15 | On Air | 2023-04-17 | 4 | 4 |  |  | 34
ISAAC NOEL APITTA. 256777111279. OLD KAMPALA.0.322866,32.62506. FTTH_10_M | Ggaba | MTNFTTH42107700 | Rontech | 2023-04-13 | 2023-04-13 | 878658 | 676246 | 1384727 | 1645904 | 0 | Done | 2023-04-15 | On Air | 2023-04-18 | 5 | 5 |  |  | 7
ALFRED KIBUKA MUSOKE. 256785544530. Luzira:Port Bell road. 0.307089,32.641345. FTTH_40_M | Luzira | MTNFTTH77758372 | Enetworks | 2022-06-18 | 2023-04-05 | 0 | 620450.1 | 412275 | 620450.1 | 0 | Done | 2023-04-07 | On Air | 2023-04-17 | 303 | 12 | System issue |  | 0
ANTHONY MUKAMBYA 256782931380 Kungu Trading Center 0.394644, 32.61349 | Buwate | MTNFTTH43471461 | Enetworks | 2023-04-14 | 2023-04-14 | 0 | 952204.6 | 556015 | 952204.6 | 0 | Done | 2023-04-16 | On Air | 2023-04-17 | 3 | 3 |  |  | 22
. 256772247439. Mbarara Municipality.-0.60716,30.654502. FTTH_20_M | Mbarara | MTNFTTH30230478 | Rontech | 2023-04-15 | 2023-04-15 | 2745239 | 797981 | 3269791 | 3543220 | 0 | Done | 2023-04-17 | On Air | 2023-04-18 | 3 | 3 |  |  | 4
VENICE OWACGIU. 256772286418. China Star Construction (Africa) Co., Ltd.0.366385,32.707215. FTTH_10_M | Seeta | MTNFTTH01184827 | Enetworks | 2023-04-14 | 2023-04-14 | 2095980.6 | 538481 | 1809900 | 2438380.6 | 0 | Done | 2023-04-16 | On Air | 2023-04-17 | 3 | 3 |  |  | 6
HILDA AKOTH. 256780332639. Buwate.0.405059,32.619267. FTTH_20_M | Buwate | MTNFTTH67211208 | Enetworks | 2023-04-14 | 2023-04-14 | 0 | 234750 | 234750 | 234750 | 0 | Done | 2023-04-16 | On Air | 2023-04-18 | 4 | 4 |  |  | 0
SHEILLA TAYEBWA. 256777459899. Kisaasi - Kyanja Road.0.383743,32.594464. FTTH_10_M | Kisaasi | MTNFTTH44767526 | Enetworks | 2023-04-14 | 2023-04-14 | 0 | 615150.6 | 408075 | 615150.6 | 0 | Done | 2023-04-16 | On Air | 2023-04-17 | 3 | 3 |  |  | 0
ERIAS SABITI. 256781229838. Sayuuni Complex.0.35822,32.611215. FTTH_20_M | Ntinda Bukoto | MTNFTTH62322178 | Enetworks | 2023-04-14 | 2023-04-14 | 0 | 678744.6 | 458475 | 678744.6 | 0 | Done | 2023-04-16 | On Air | 2023-04-18 | 4 | 4 |  |  | 10
Charlotte Luzuka. 256762928541. 8JXV 524, Kamuli Rd, Kampala, Uganda.0.347724,32.64201. FTTH_20_M | Bweyogerere | MTNFTTH60070807 | Enetworks | 2023-04-14 | 2023-04-14 | 0 | 0 | 1,289,919 | 1,638,463.60 | 0 | Done | 2023-04-16 | On Air | 2023-04-18 | 4 | 4 |  |  | 10
null null. 256775216460. Dashen Heights Residential Apartments. 0.297216,32.585227. FTTH_10_M | Nsambya | MTNFTTH08603667 | Rontech | 2023-04-04 | 2023-04-10 | 789529 | 796953 | 1321115 | 1586482 | 0 | Done | 2023-04-12 | On Air | 2023-04-18 | 14 | 8 | ROW with neighbour |  | 20
PATIENCE AUMA.256775720015.Akright Estate bwebajja.0.157488,32.544707.FTTH_20_M | Bwebajja | MTNFTTH65740548 | Chrif | 2023-04-16 | 2023-04-16 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-18 | On Air | 2023-04-17 | 1 | 1 |  |  | 2
HARRIET NALUTAAYA.256763673493.Akright City.0.167522.32.523131.FTTH_20_M | Bwebajja | MTNFTTH13011521 | Chrif | 2023-04-16 | 2023-04-16 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-18 | On Air | 2023-04-17 | 1 | 1 |  |  | 1
ISAAC KAGOBE.256775071686.Akright City.0.167522.32.523131.FTTH_20_M | Bwebajja | MTNFTTH35260402 | Chrif | 2023-04-16 | 2023-04-16 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-18 | On Air | 2023-04-17 | 1 | 1 |  |  | 1
PATRICK KINTU.256779711793.Akright City.0.167522,32.523131.FTTH_20_M | Bwebajja | MTNFTTH56771163 | Chrif | 2023-04-16 | 2023-04-16 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-18 | On Air | 2023-04-17 | 1 | 1 |  |  | 2
HARRIET AKOT.256783738994.Akright City.0.167522,32.523131.FTTH_20_M | Bwebajja | MTNFTTH16850778 | Chrif | 2023-04-14 | 2023-04-15 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-17 | On Air | 2023-04-17 | 3 | 2 |  |  | 2
MERCY NAMULONDO.256775614622.Akright City.0.167522,32.523131.FTTH_20_M | Bwebajja | MTNFTTH68141607 | Chrif | 2023-04-12 | 2023-04-15 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-17 | On Air | 2023-04-17 | 5 | 2 |  |  | 3
KATHRINE ADONGO.256772848459.Akright City.0.167522,32.523131.FTTH_20_M | Bwebajja | MTNFTTH02843528 | Chrif | 2023-04-14 | 2023-04-15 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-17 | On Air | 2023-04-17 | 3 | 2 |  |  | 3
INNOCENT KILAMA.256774297003.Akright City.0.167522,32.523131.FTTH_20_M | Bwebajja | MTNFTTH81211776 | Chrif | 2023-04-14 | 2023-04-15 | 286375.75 | 153729 | 11111224.5 | 4905402.1667 | 0 | Done | 2023-04-17 | On Air | 2023-04-17 | 3 | 2 |  |  | 6
ASAD KASAJJA.256785626465.Kyanja Supermarket.0.396528,32.593531.FTTH_10_M | Kisaasi | MTNFTTH02560040 | Enetworks | 2023-04-14 | 2023-04-15 | 1133217 | 524131 | 1172979 | 1657347.6 | 0 | Done | 2023-04-17 | On Air | 2023-04-17 | 3 | 2 |  |  | 16
HUDSON BARIGYE.256772121868.Kisaasi:Bahai Road.0.359815,32.599658.FTTH_10_M | Kisaasi | MTNFTTH28321822 | Enetworks | 2021-10-20 | 2023-04-08 | 1468060 | 512531 | 1424150 | 1980590.6 | 0 | Done | 2023-04-10 | On Air | 2023-04-15 | 542 | 7 | ROW with one Pole |  | 8
JOSEPHAT WEFAFA. 256761914440. OLD KAMPALA.0.344065,32.59282. FTTH_10_M | Ntinda bukoto | MTNFTTH50667083 | Enetworks | 2023-04-05 | 2023-04-05 | 1551289 | 517231 |  | 2068520 | 0 | Done | 2023-04-07 | On Air | 2023-04-19 | 14 | 14 | Client wasn’t in my cluster (bukoto), I just picked him up after delay in system |  | 8
NELSON KYAMBOGO. 256782709103. Kiwatule.0.365298,32.624919. FTTH_10_M | Ntinda kiwatule | MTNFTTH60751570 | Enetworks | 2023-04-05 | 2023-04-05 | 0 | 1043761 | 771450 | 1043761.3 | 5 | Done | 2023-04-07 | On Air | 2023-04-23 | 18 | 13 | ROW with Apartment Management |  | 16
. 256760616797. Bukasa Close.0.300549,32.611328. FTTH_10_M | Muyenga | MTNFTTH74520488 | Rontech | 2023-04-07 | 2023-04-10 | 1224129 | 779212 | 1720383 | 2003341 | 0 | Done | 2023-04-12 | On Air | 2023-04-20 | 13 | 10 | Delayed by customer unavailability |  | 6
ROBINAH NTEGE NALUMANSI. 256772402564. Zana.0.262405,32.557071. FTTH_20_M | Najjanankumbi | MTNFTTH50214634 | Rontech | 2023-04-08 | 2023-04-08 | 2446369 | 706135 | 2916457 | 3152504 | 0 | Done | 2023-04-10 | On Air | 2023-04-20 | 12 | 12 | ROW issues |  | 5
IMMACULATE KAMBABAZI. 256783674460. Ndere Cultural Centre.0.363351,32.605806. FTTH_10_M | Ntinda Kiwatule | MTNFTTH02016288 | Enetworks | 2023-04-11 | 2023-04-11 | 2768537.4 | 531031 | 2584569 | 3299568 | 0 | Done | 2023-04-13 | On Air | 2023-04-19 | 8 | 8 | Delayed by Customer¦¦ they had a patient |  | 16
NAMAWENJJE CATHERINE. 256784874503. Nicodemus Pork Joint.0.337374,32.563271. FTTH_20_M | Makerere | MTNFTTH38622336 | Chrif | 2023-04-12 | 2023-04-12 | 643350 | 560816 | 865150 | 1204166 | 0 | Done | 2023-04-14 | On Air | 2023-04-24 | 12 | 12 | Reassignment |  | 4
ASRAPH BUSULWA. 256775454247. OLD KAMPALA.0.351294,32.605266. FTTH_10_M | Ntinda bukoto | MTNFTTH41681858 | Enetworks | 2023-04-12 | 2023-04-12 | 2291810 | 517230.6 | 1834640 | 2809040.6 | 0 | Done | 2023-04-14 | On Air | 2023-04-22 | 10 | 10 | Client wasn’t in my cluster (kitante), I just picked him up. |  | 10
MOSES SERUNJOGI. 256770726598. OLD KAMPALA.0.239818,32.558112. FTTH_10_M | Najjanankumbi | MTNFTTH28740010 | Rontech | 2023-04-13 | 2023-04-13 | 789529 | 758283 | 1282445 | 1547812 | 0 | Done | 2023-04-15 | On Air | 2023-04-19 | 6 | 6 | Delayed by customer unavailability |  | 0
Pius Muhumuza. 256783657011. Alternative Care Initiatives.0.287333,32.630628. FTTH_10_M | Muyenga | MTNFTTH37052133 | Rontech | 2023-04-13 | 2023-04-13 | 2123173 | 668251 | 2534033 | 2791424 | 0 | Done | 2023-04-15 | On Air | 2023-04-21 | 8 | 8 | ROW with the Landlord |  | 7
PAUL MAURICE GGOWA. 256781067408. KITGUM.0.395165,32.580929. FTTH_20_M | Gayaza | MTNFTTH35554788 | Enetworks | 2023-04-13 | 2023-04-13 | 2281809 | 517231 | 2140699 | 2725939.6 | 0 | Done | 2023-04-15 | On Air | 2023-04-21 | 8 | 8 | Cluster reallocation |  | 5
EVA BIRUNGI. 256786460439. OLD KAMPALA.0.32118,32.555187. FTTH_10_M | Rubaga | MTNFTTH55271607 | Rontech | 2023-04-13 | 2023-04-13 | 2123173 | 668251 | 2534033 | 2791424 | 0 | Done | 2023-04-15 | On Air | 2023-04-24 | 11 | 11 | Delayed by customer unavailability |  | 7
CHURCHHILL ADETI. 256776429351. OLIVE APARTMENTS MUYENGA.0.287509,32.620775. FTTH_20_M | Muyenga | MTNFTTH84442268 | Rontech | 2023-04-14 | 2023-04-14 | 789529 | 727953 | 1234524 | 1517482 | 0 | Done | 2023-04-16 | On Air | 2023-04-20 | 6 | 6 | Delayed by customer unavailability |  | 3
Isaac KISASI. 256776128778. 8b Muwanga Rd, Kampala, Uganda Kisaasi.0.372475,32.605012. FTTH_10_M | Kisaasi | MTNFTTH16334671 | Enetworks | 2023-04-15 | 2023-04-15 | 400273 | 547531 | 637375 | 947803.6 | 0 | Done | 2023-04-17 | On Air | 2023-04-20 | 5 | 5 |  |  | 13
CLINTON AGABA. 256772753530. Kyanja Estates.0.391083,32.59178. FTTH_10_M | Kisaasi | MTNFTTH66250515 | Enetworks | 2023-04-15 | 2023-04-15 | 0 | 787762.6 | 563095 | 787762.6 | 0 | Done | 2023-04-17 | On Air | 2023-04-21 | 6 | 6 | System issue |  | 17
EBOKU COLIN. 256780322993. OLD KAMPALA.0.391741,32.625096. FTTH_10_M | Kira | MTNFTTH74101034 | Enetworks | 2023-04-16 | 2023-04-16 | 0 | 796240.6 | 567,175 | 796240.6 | 0 | Done | 2023-04-18 | On Air | 2023-04-24 | 8 | 8 |  |  | 3
MAGAMBO ROSETTE. 256774400177. OLD KAMPALA.0.382923,32.612659. FTTH_10_M | Kisaasi | MTNFTTH61805273 | Enetworks | 2023-04-16 | 2023-04-16 | 0 | 602828.6 | 391355 | 602828.6 | 0 | Done | 2023-04-18 | On Air | 2023-04-19 | 3 | 3 |  |  | 2
Yarmah M Abraham. 256772441528. Kyeyune Exhaust Ltd.0.324234,32.562876. FTTH_10_M | Makerere | MTNFTTH65004224 | Chrif | 2023-04-16 | 2023-04-16 | 0 | 620941 | 391875 | 620941 | 0 | Done | 2023-04-18 | On Air | 2023-04-20 | 4 | 4 |  |  | 6
NORBERT OTOK. 256777808686. OLD KAMPALA.0.287123,32.621603. FTTH_20_M | Ggaba | MTNFTTH46148836 | Rontech | 2023-04-16 | 2023-04-16 | 789529 | 747407 | 1248114 | 1536936 | 0 | Done | 2023-04-18 | On Air | 2023-04-19 | 3 | 3 |  |  | 5
OSCAR TIBIGAMBWA. 256778097935. OLD KAMPALA.0.342925,32.661368. FTTH_10_M | Bweyogerere | MTNFTTH64742577 | Enetworks | 2023-04-16 | 2023-04-16 | 1775359 | 517231 | 1707349 | 2292589.6 | 0 | Done | 2023-04-18 | On Air | 2023-04-20 | 4 | 4 |  |  | 4
LAWRENCE TUMUSIIME. 256772589338. OLD KAMPALA.0.375899,32.643693. FTTH_10_M | Kira | MTNFTTH80457156 | Enetworks | 2023-04-17 | 2023-04-17 | 0 | 625749.6 | 416475 | 625749.6 | 0 | Done | 2023-04-19 | On Air | 2023-04-22 | 5 | 5 |  |  | 0
JOSEPHINE BATENGA. 256762987920. Lungujja.0.309657,32.540489. FTTH_20_M | RUBAGA | MTNFTTH78365735 | Pavicon | 2023-04-17 | 2023-04-17 | 424506 | 373752 | 545786 | 798258 | 0 | Done | 2023-04-19 | On Air | 2023-04-23 | 6 | 6 | Re-assigned to Pavicon on 23-APRIL |  | 12
Kosmas Malinga. 256779060176. Liquids Betina.0.433811,33.205624. FTTH_10_M | Jinja | MTNFTTH62848524 | Enetworks | 2023-04-17 | 2023-04-17 | 2268499 | 495731 | 1717159 | 2172679.6 | 0 | Done | 2023-04-19 | On Air | 2023-04-23 | 6 | 6 | Faced challenges on manhole constructions where we had to engage the concerned people |  | 3
MAHADEV SOPAN MANDHARE. 256760954870. Tungo Courts.0.317869,32.642497. FTTH_10_M | Luzira | MTNFTTH31610464 | Enetworks | 2023-04-15 | 2023-04-15 | 0 | 0 | 478,555 | 701,023.60 | 0 | Done | 2023-04-17 | On Air | 2023-04-18 | 3 | 3 |  |  | 8
Bob Ssebuliba. 256773302885. Nsamizi Road.0.066489,32.467086. FTTH_10_M | Entebbe | MTNFTTH11013518 | Chrif | 2023-04-17 | 2023-04-17 | 0 | 559170.6 | 341100 | 559170.6 | 0 | Done | 2023-04-19 | On Air | 2023-04-19 | 2 | 2 |  |  | 4
GEORGE WAMALA. 256778045620. Mutundwe.0.280748,32.540416. FTTH_10_M | Rubaga | MTNFTTH51304036 | Rontech | 2023-04-17 | 2023-04-17 | 1097500 | 1086604 | 2184104 | 2383677 | 0 | Done | 2023-04-19 | On Air | 2023-04-25 | 8 | 8 | Delayed Access to Mutundwe Switch |  | 8
FRANCIS BITATURE KISEMBO. 256782619561. Kisaasi.0.361441,32.596655. FTTH_10_M | Kisaasi | MTNFTTH03254847 | Soliton | 2023-04-17 | 2023-04-17 | 2096839 | 385916 | 1801035 | 2482755 | 0 | Done | 2023-04-19 | On Air | 2023-04-20 | 3 | 3 |  |  | 7
DERICK YAWE DDUMBA. 256785444804. OLD KAMPALA.0.36364,32.643721. FTTH_10_M | Kira | MTNFTTH34043012 | Soliton | 2023-04-17 | 2023-04-17 | 0 |  | 0 | 0 | 0 | Done | 2023-04-19 | On Air | 2023-04-20 | 3 | 3 |  |  | 0
TEDDY FLORENCE NALWANGA. 256774522619. OLD KAMPALA.0.314737,32.57775. FTTH_20_M | Old Park | MTNFTTH68641202 | Enetworks | 2023-04-18 | 2023-04-18 | 0 | 793813 | 518570 | 793813.3 | 0 | Done | 2023-04-20 | On Air | 2023-04-25 | 7 | 7 | Client wasn’t in my cluster (Downtown), I just picked him up after raising his complain |  | 0
Seghani Lalji Jitendra. 256771454054. OLD KAMPALA.0.36506,32.6015. FTTH_10_M | Kisaasi | MTNFTTH87037670 | Soliton | 2023-04-18 | 2023-04-18 | 0 | 610085.6 | 356316 | 610085.6 | 0 | Done | 2023-04-20 | On Air | 2023-04-18 | 0 | 0 |  |  | 0
ANITAH AMPURIRE. 256772691659. Kololo Hospital.0.334182,32.588881. FTTH_20_M | Kololo | MTNFTTH24651637 | Rak | 2023-04-18 | 2023-04-18 | 1735816 | 366734 | 1832866 | 2102549.6 | 0 | Done | 2023-04-20 | On Air | 2023-04-21 | 3 | 3 |  |  | 6
JULIET NYAKUZA. 256770953370. Entebbe.0.051184,32.463708. FTTH_10_M | Entebbe | MTNFTTH35361031 | Chrif | 2023-04-18 | 2023-04-18 | 0 | 559170.6 | 341100 | 559170.6 | 0 | Done | 2023-04-20 | On Air | 2023-04-21 | 3 | 3 |  |  | 4
EVERLYNE AKOT.256784880375.OLD KAMPALA.0.34832,32.615049.FTTH_10_M | Ntinda Kiwatule | MTNFTTH51175687 | Soliton | 2023-04-19 | 2023-04-19 | 0 | 559871.6 | 329972 | 559871.6 | 0 | Done | 2023-04-21 | On Air | 2023-04-20 | 1 | 1 | High BOQ |  | 0
EDDY KASIRYE.256782935561.OLD KAMPALA.0.365842,32.60219. FTTH_10_M | Kisaasi | MTNFTTH66376007 | Soliton | 2023-04-17 | 2023-04-19 | 0 | 572.988.8 | 321219 | 572.988.8 | 0 | Done | 2023-04-21 | On Air | 2023-04-19 | 2 | 0 | High BOQ |  | 0
EVA NANGOKA.256788618414.Najjera Progressive Primary School.0.382794,32.626509. FTTH_20_M | Kira | MTNFTTH77474101 | Enetworks | 2023-04-06 | 2023-04-19 | 1073570 | 451231 | 961180 | 1524800.6 | 0 | Done | 2023-04-21 | On Air | 2023-04-19 | 13 | 0 |  |  | 9
NATHAN EPUDU.256773230699.OLD KAMPALA.0.371235,32.659709.FTTH_10_M | Bweyogerere | MTNFTTH80176702 | Enetworks | 2023-04-19 | 2023-04-19 | 680697 | 487030.6 | 809654 | 1167727.6 | 0 | Done | 2023-04-21 | On Air | 2023-04-20 | 1 | 1 |  |  | 2
JOSEPH ASIIMWE. 256785666139. Lweza Estate.0.221346,32.549294. FTTH_10_M | Najjanankumbi | MTNFTTH25541283 | Rontech | 2023-04-19 | 2023-04-19 | 789529 | 761238 | 1267809 | 1550767 | 0 | Done | 2023-04-21 | On Air | 2023-04-24 | 5 | 5 |  |  | 18
IVY KEMIGISHA. 256777968985. OLD KAMPALA.0.371974,32.60555. FTTH_10_M | Kisaasi | MTNFTTH67876605 | Soliton | 2023-04-20 | 2023-04-20 | 0 | 755358 | 326209 | 755358 | 0 | Done | 2023-04-22 | On Air | 2023-04-23 | 3 | 3 |  |  | 0
VICTOR IMMANUEL OLOO. 256786126308. OLD KAMPALA.0.355505,32.642645. FTTH_10_M | Bweyogerere | MTNFTTH26428512 | Enetworks | 2023-04-18 | 2023-04-19 | 725485 | 509030.6 | 649275 | 1234515.6 | 0 | Done | 2023-04-21 | On Air | 2023-04-22 | 4 | 3 |  |  | 10
SHALLOTE NAYEBARE. 256774332377. OLD KAMPALA.0.378875,32.59163. FTTH_10_M | Kisaasi | MTNFTTH77075463 | Soliton | 2023-04-20 | 2023-04-20 | 0 | 561399 | 340920 | 561399 | 0 | Done | 2023-04-22 | On Air | 2023-04-22 | 2 | 2 |  |  | 0
FATUMA MOHAMED AHMED. 256777221765. OLD KAMPALA.0.373703,32.601656. FTTH_10_M | Kisaasi | MTNFTTH07225744 | Soliton | 2023-04-20 | 2023-04-20 | 0 | 563772.6 | 340920 | 563772.6 | 0 | Done | 2023-04-22 | On Air | 2023-04-22 | 2 | 2 |  |  | 0
ALI LALIAOUI. 256762712407. OLD KAMPALA.0.311862,32.646941. FTTH_10_M | Luzira | MTNFTTH06534565 | Enetworks | 2023-04-20 | 2023-04-20 | 0 | 866528.6 | 657254 | 866528.6 | 0 | Done | 2023-04-22 | On Air | 2023-04-22 | 2 | 2 |  |  | 6
JEMIMA KARIUKI. 256772123355. Lubowa Terrace.0.237438,32.564759. FTTH_20_M | Najjanankumbi | MTNFTTH57015682 | Rontech | 2023-04-20 | 2023-04-20 | 4451314 | 1200620 | 4756204 | 5651934 | 0 | Done | 2023-04-22 | On Air | 2023-04-24 | 4 | 4 | Approved by Carol |  | 5
Arnold Tingu. 256777175752. OLD KAMPALA.0.332016,32.668891. FTTH_20_M | Bweyogerere | MTNFTTH23814465 | Enetworks | 2023-04-20 | 2023-04-20 | 1358309 | 523230.6 | 1188199 | 1881539.6 | 0 | Done | 2023-04-22 | On Air | 2023-04-24 | 4 | 4 |  |  | 2
Jude Kigozi. 256783893650. Kitetika gayaza Road,uganda.0.344219,32.582511. FTTH_20_M | Gayaza | MTNFTTH52118342 | Soliton | 2023-04-15 | 2023-04-19 | 1471745 | 406547 | 1624093 | 1878292 | 0 | Done | 2023-04-21 | On Air | 2023-04-24 | 9 | 5 |  |  | 0
KENNETH OTUKOL. 256772624742. FezaTel ltd.0.349641,32.61829. FTTH_10_M | Ntinda Kyambogo | MTNFTTH40015521 | Soliton | 2023-04-20 | 2023-04-20 | 0 | 1042832.6 | 353363 | 1042832.6 | 0 | Done | 2023-04-22 | On Air | 2023-04-22 | 2 | 2 |  |  | 0
Margaret Nyanjura. 256773267578. 0°23\\\'02.5\\.0.384,32.6251. FTTH_10_M | Kisaasi | MTNFTTH60685177 | Soliton | 2023-04-20 | 2023-04-20 | 0 | 561432.8 | 331533 | 561432.8 | 0 | Done | 2023-04-22 | On Air | 2023-04-23 | 3 | 3 |  |  | 0
JUDE HERBIE SSENYONJO. 256778084078. OLD KAMPALA.0.231132,32.543461. FTTH_20_M | Nalumunye | MTNFTTH18348330 | Rak | 2023-04-20 | 2023-04-20 | 208750 | 561551 | 546056 | 770300.6 | 0 | Done | 2023-04-22 | On Air | 2023-04-24 | 4 | 4 | Not in que |  | 2
CAROL NAKATO. 256787251229. Luwafu, makindye.0.269742,32.592372. FTTH_10_M | MAKINDYE | MTNFTTH14724435 | Pavicon | 2023-04-19 | 2023-04-19 | 1458936 | 131,650 | 1,590,586 | 2,333,351 | 0 | Done | 2023-04-21 | On Air | 2023-04-23 | 4 | 4 | ROW to Access Luwafu site |  | 2
Chris Mukuru. 256775783056. KITGUM.0.343807,32.621317. FTTH_20_M | Ntinda Kyambogo | MTNFTTH22844552 | Soliton | 2023-04-19 | 2023-04-19 | 1567069 | 387477 | 1722431 | 1954546 | 0 | Done | 2023-04-21 | On Air | 2023-04-21 | 2 | 2 |  |  | 0
Patrick Winyi. 256773125633. OLD KAMPALA.0.385439,32.602797. FTTH_10_M | Kisaasi | MTNFTTH86787011 | Soliton | 2023-04-21 | 2023-04-21 | 0 | 562262.6 | 337466 | 562262.6 | 0 | Done | 2023-04-23 | On Air | 2023-04-22 | 1 | 1 |  |  | 0
DONNIE BYARUHANGA. 256775690138. Kisaasi.0.361441,32.596655. FTTH_10_M | Kisaasi | MTNFTTH50428361 | Soliton | 2023-04-21 | 2023-04-21 | 0 |  | 0 | 0 | 0 | Done | 2023-04-23 | On Air | 2023-04-23 | 2 | 2 |  |  | 4
JOHN ZZIWA. 256781282573. JINJA.0.432779,33.21193. FTTH_10_M | Jinja | MTNFTTH08378462 | Enetworks | 2023-04-21 | 2023-04-21 | 2078760 | 495730.6 | 1816290 | 2574490.6 | 0 | Done | 2023-04-23 | On Air | 2023-04-23 | 2 | 2 |  |  | 9
null null.256778942153.Lubowa Terrace.0.237438,32.564759.FTTH_10_M | Najjanankumbi | MTNFTTH82540637 | Rontech | 2023-03-06 | 2023-04-13 | 0 | 1585180 | 1319813 | 1585180 | 0 | Done | 2023-04-15 | On Air | 2023-04-20 | 45 | 7 | Delayed by customer - had existing service |  | 7
BALISANYUKA PETER.256782942972.ican Resort Hotel.0.229229,32.54397.FTTH_40_M | Najjanankumbi | MTNFTTH03381273 | Rontech | 2023-04-19 | 2023-04-19 | 1719388 | 681962 | 2143313 | 2401349 | 0 | Done | 2023-04-21 | On Air | 2023-04-20 | 1 | 1 |  |  | 10
EMMANUEL MUGISHA 774774042 Kisaasi:Bahai Road 0.37247,0.37247 FTTH_20_M | Kisaasi | MTNFTTH27178676 | Soliton | 2022-06-21 | 2023-04-11 | 630979 | 767630 | 959239 | 1398609 | 0 | Done | 2023-04-13 | On Air | 2023-04-20 | 303 | 9 | Delayed by customer unavailability |  | 0
JOSELYNE AYEBALE. 256774102692. Katale Seguku.0.233668,32.545845. FTTH_10_M | Najjanankumbi | MTNFTTH41447737 | Rontech | 2023-04-05 | 2023-04-05 | 2250511.7778 | 396258.8889 | 2572838.8889 | 2646770.6667 | 0 | Done | 2023-04-07 | On Air | 2023-04-27 | 22 | 22 | The client had ROW issuess (Among the consolidated clients) |  | 9
BENARD WAKYAYA. 256785229880. OLD KAMPALA.0.24584,32.538307. FTTH_10_M | Najjanankumbi | MTNFTTH74613053 | Rontech | 2023-04-05 | 2023-04-05 | 2250511.7778 | 396258.8889 | 2572838.8889 | 2646770.6667 | 20 | Done | 2023-04-07 | On Air | 2023-04-27 | 22 | 2 | ROW not resolved |  | 9
EMMANUEL PETIT. 256782041452. OLD KAMPALA.0.387718,32.640524. FTTH_10_M | Kira | MTNFTTH54535633 | Enetworks | 2023-04-05 | 2023-04-05 | 0 | 432214.5 | 115632 | 432214.5 | 23 | Done | 2023-04-07 | On Air | 2023-04-28 | 23 | 0 | To be commissioned in May |  | 15
Fredrick Ndiwalana. 256777767693. Seguku.0.237516,32.541173. FTTH_10_M | Najjanankumbi | MTNFTTH16287342 | Rontech | 2023-04-07 | 2023-04-07 | 2250511.7778 | 396258.8889 | 2572838.8889 | 2646770.6667 | 14 | Done | 2023-04-09 | On Air | 2023-04-27 | 20 | 6 | Fredrick Ndiwalana. 256777767693. Seguku. (0.237516,32.541173). FTTH_10_M. |  | 9
Kifude Isma. 256772924318. Seguku.0.237516,32.541173. FTTH_10_M | Najjanankumbi | MTNFTTH62877153 | Rontech | 2023-04-07 | 2023-04-07 | 2250511.7778 | 396258.8889 | 2572838.8889 | 2646770.6667 | 14 | Done | 2023-04-09 | On Air | 2023-04-27 | 20 | 6 | Fredrick Ndiwalana. 256777767693. Seguku. (0.237516,32.541173). FTTH_10_M. |  | 8
SIMON OKANYA. 256762900506. OLD KAMPALA.0.363241,32.647513. FTTH_10_M | Bweyogerere | MTNFTTH33365680 | Enetworks | 2023-04-10 | 2023-04-14 | 2070065 | 2070065 | 2057700 | 2587295.6 | 0 | Done | 2023-04-16 | On Air | 2023-04-27 | 17 | 13 | Above DOA , 5 poles |  | 5
ANDEMARIAM YEHDEGO. 256761992532. OLD KAMPALA.0.29722,32.585229. FTTH_20_M | NSAMBYA | MTNFTTH04153371 | Pavicon | 2023-04-12 | 2023-04-12 | 233750 | 327123 | 332590 | 560873 | 7 | Done | 2023-04-14 | On Air | 2023-04-25 | 13 | 6 | not feasible |  | 3
BADIRIA NASSAZI. 256779808402. Lugala.0.31351,32.54081. FTTH_10_M | RUBAGA | MTNFTTH78053075 | Pavicon | 2023-04-14 | 2023-04-14 | 2260536 | 359774 | 1886156 | 2620310 | 0 | Done | 2023-04-16 | On Air | 2023-04-25 | 11 | 11 | Quotation Approved on 24-Apr, He paid before we started MTN works |  | 2
Elizabeth Nakayima. 256772693778. OLD KAMPALA.0.314206,32.581651. FTTH_20_M | Kira | MTNFTTH83018583 | Soliton | 2023-04-15 | 2023-04-15 | 0 | 580083.8 | 335604 | 580083.8 | 0 | Done | 2023-04-17 | On Air | 2023-04-27 | 12 | 12 | Cluster reassignment |  | 8
. 256775317008. OLD KAMPALA.0.194049,32.539572. FTTH_10_M | Kajjansi | MTNFTTH28055134 | Chrif | 2023-04-16 | 2023-04-16 | 2336978 | 526300 | 2069513 | 2863278 | 5 | Done | 2023-04-18 | On Air | 2023-04-25 | 9 | 4 |  |  | 3
LODU ANTHONY. 256776517420. Buwate Masjid.0.399006,32.621158. FTTH_10_M | Buwate | MTNFTTH18006433 | Enetworks | 2023-04-14 | 2023-04-14 | 1714339 | 524131 | 1588369 | 2238469.6 | 0 | Done | 2023-04-16 | On Air | 2023-04-28 | 14 | 14 | ROW challenges, client fully participated in the resolutions |  | 5
DAISY MASEMBE. 256788107728. Mbalwa.0.365182,32.653176. FTTH_10_M | Bweyogerere | MTNFTTH05217706 | Enetworks | 2023-04-18 | 2023-04-18 | 662768 | 388030.6 | 702254 | 1050798.6 | 5 | Done | 2023-04-20 | On Air | 2023-04-26 | 8 | 3 | Pending Council Permit |  | 2
Godfrey Kakembo Mukasa. 256777810655. OLD KAMPALA.0.175037,32.533146. FTTH_20_M | Bwebajja | MTNFTTH47866536 | Chrif | 2023-04-19 | 2023-04-19 | 255,150 | 341446 | 596596 | 1193192 | 0 | Done | 2023-04-21 | On Air | 2023-04-25 | 6 | 6 | ROW with neighbour |  | 5
ALEX NTAMBI. 256788840171. Shell.0.33873,32.56347. FTTH_20_M_O | Makerere | MTNFTTH30844663 | Rak | 2023-04-17 | 2023-04-20 | 208750 | 422428 | 391540 | 631177 | 7 | Done | 2023-04-22 | On Air | 2023-04-27 | 10 | 0 |  |  | 0
. 256789967784. OLD KAMPALA.0.290592,32.611671. FTTH_20_M | Muyenga | MTNFTTH10734663 | Rontech | 2023-04-20 | 2023-04-20 | 1752466 | 133690 | 1886156 | 2620310 |  | Done | 2023-04-22 | On Air | 2023-04-25 | 5 | 5 |  |  | 0
VANESSA BASALWA. 256788704141. Mukono.0.354866,32.752014. FTTH_10_M | Mukono | MTNFTTH35101042 | Enetworks | 2023-04-20 | 2023-04-20 | 1355679 | 545730.6 | 1355679 | 1984159.6 |  | Done | 2023-04-22 | On Air | 2023-04-26 | 6 | 6 |  |  | 5
MINORITA TUMWEBAZE. 256778866306. OLD KAMPALA.0.175443,32.538055. FTTH_10_M | Bwebajja | MTNFTTH36481327 | Chrif | 2023-04-19 | 2023-04-19 | 208750 | 556476.6 | 213800 | 765226.6 | 6 | Done | 2023-04-21 | On Air | 2023-04-26 | 7 | 1 | Client on Voice mall, r.ow from mgt was concluded as of 25.4.2023, tobe commissioned toaday. |  | 0
. 256778973162. OLD KAMPALA.0.351019,32.593887. FTTH_10_M | Ntinda Bukoto | MTNFTTH21463065 | Rak | 2023-04-19 | 2023-04-19 | 2023076 | 358095 | 1789386 | 2381170 | 0 | Done | 2023-04-21 | On Air | 2023-04-27 | 8 | 8 | Customer had civil works and there was ROW issues with the Landlords |  | 0
PETER ODONGHO. 256762309189. Kyambogo.0.346537,32.628731. FTTH_10_M | Ntinda Kyambogo | MTNFTTH37461666 | Soliton | 2023-04-24 | 2023-04-24 | 0 | 563020.6 | 327046 | 563020.6 | 0 | Done | 2023-04-26 | On Air | 2023-04-26 | 2 | 2 |  |  | 0
ERON KWAGALA. 256777075940. Nabe Road.0.366421,32.630475. FTTH_10_M | Ntinda Kyambogo | MTNFTTH70644725 | Soliton | 2023-04-24 | 2023-04-24 | 0 | 5782217.2 | 338598 | 5782217.2 | 0 | Done | 2023-04-26 | On Air | 2023-04-26 | 2 | 2 |  |  | 6
TONNY NANGOSHA. 256787713506. Rubis Ntinda Service Station.0.359061,32.617412. FTTH_20_M | Ntinda Kiwatule | MTNFTTH85053256 | Soliton | 2023-04-25 | 2023-04-25 | 1836579 | 395324 | 2635603 | 2231903 | 0 | Done | 2023-04-27 | On Air | 2023-04-26 | 1 | 1 |  |  | 5
DEOGRATIAS NTAGANIRA. 256776136049. Station Road.0.057091,32.47465. FTTH_10_M | Entebbe | MTNFTTH76130685 | Chrif | 2023-04-25 | 2023-04-25 | 420756 | 424115.6 | 615806 | 844871.6 | 0 | Done | 2023-04-27 | On Air | 2023-04-27 | 2 | 2 |  |  | 5
JUSTUS MUCHUNGUZI. 256785933023. OLD KAMPALA.0.381427,32.597538. FTTH_10_M | Kisaasi | MTNFTTH73386116 | Soliton | 2023-04-19 | 2023-04-19 | 0 | 749708.2 | 518594 | 749708.2 | 4 | Done | 2023-04-21 | On Air | 2023-04-28 | 9 | 5 | System isue |  | 0
KENETH ISABIRYE. 256772384031. OLD KAMPALA.0.35732,32.648787. FTTH_20_M | Bweyogerere | MTNFTTH34637218 | Enetworks | 2023-04-26 | 2023-04-26 | 0 | 707817.6 | 483150 | 707817.6 | 0 | Done | 2023-04-28 | On Air | 2023-04-28 | 2 | 2 |  |  | 12
SHARLOT NALUBOWA. 256772876252. Kisaasi - Kyanja Road.0.383743,32.594464. FTTH_10_M | Kisaasi | MTNFTTH68048062 | Soliton | 2023-04-26 | 2023-04-26 | 0 | 555702.2 | 329448 | 555702.2 | 0 | Done | 2023-04-28 | On Air | 2023-04-27 | 1 | 1 |  |  | 6
NZIZA RURANGIRWA. 256779915620. Mutungo Hill.0.319589,32.6447. FTTH_20_M | Luzira | MTNFTTH72004547 | Enetworks | 2023-04-26 | 2023-04-26 | 1421529 | 426727.6 | 1105079 | 1848256.6 | 0 | Done | 2023-04-28 | On Air | 2023-04-27 | 1 | 1 |  |  | 3
FRANCIS KASUJJA.256773397908. 0.305162,32.559526.FTTH_10_M | RUBAGA | MTNFTTH13628774 | Pavicon | 2023-04-25 | 2023-04-25 | 424506 | 361035 | 539666 | 785541 | 0 | Done | 2023-04-27 | On Air | 2023-04-26 | 1 | 1 |  |  | 3
EVA ALIGAWEESA.256788008143.Butikiro Road.0.310608,32.564316.FTTH_10_M_O | RUBAGA | MTNFTTO43157037 | Pavicon | 2023-04-25 | 2023-04-25 | 424506 | 369513 | 543746 | 794019 | 0 | Done | 2023-04-27 | On Air | 2023-04-26 | 1 | 1 |  |  | 0
null null.256774115480.Zana Community Church.0.252712,32.562844.FTTH_10_M | Najjanankumbi | MTNFTTH64333324 | Rontech | 2023-04-04 | 2023-04-23 | 789529 | 693611 | 1217773 | 1483140 | 0 | Done | 2023-04-25 | On Air | 2023-04-26 | 22 | 3 |  |  | 15
DANIEL LUMONYA.256772501793.OLD KAMPALA.0.083231,32.468889.FTTH_40_M | Entebbe | MTNFTTH70178666 | Chrif | 2023-04-07 | 2023-04-18 | 874730 | 503096 | 943520 | 1377825.6 | 6 | Done | 2023-04-20 | On Air | 2023-04-26 | 19 | 2 | BW issues |  | 1
TIMOTHY BAREIRE AINE. 256780230910. Buwate Police Post.0.406821,32.619745. FTTH_10_M | Buwate | MTNFTTH71646864 | Soliton | 2023-04-26 | 2023-04-26 | 1187696 | 386234 | 1092413 | 1573930 | 0 | Done | 2023-04-28 | On Air | 2023-04-28 | 2 | 2 |  |  | 0
GRACE NANNYONGA. 256782245447. Buwate.0.405059,32.619267. FTTH_10_M | Buwate | MTNFTTH36470805 | Soliton | 2023-04-27 | 2023-04-27 | 1122599 | 394460 | 1090874 | 1517059 | 0 | Done | 2023-04-29 | On Air | 2023-04-28 | 1 | 1 |  |  | 3
Galiwango Florence. 256788591026. Ojogoi Lane.0.385655,32.645688.FTTH_10_M | Kira | MTNFTTH85644083 | Soliton | 2023-04-26 | 2023-04-26 | 0 | 550113.8 | 321429 | 550113.8 | 0 | Done | 2023-04-28 | On Air | 2023-04-26 | 0 | 0 |  |  | 0
CHARLIE ATEENYI SEKAKONI.256772845007.Seguku.0.237516,32.541173.FTTH_10_M | Najjanankumbi | MTNFTTH85742418 | Rontech | 2023-04-27 | 2023-04-27 | 2250511.7778 | 396258.8889 | 2572838.8889 | 2646770.6667 | 0 | Done | 2023-04-29 | On Air | 2023-04-27 | 0 | 0 |  |  | 9
SYLVIA NANSIMBI JAGWE. 256778697071. Muyenga.0.296898,32.615028. FTTH_20_M | Muyenga | MTNFTTH77581888 | Rontech | 2023-04-11 | 2023-04-11 | 2108663 | 725737 | 2587183 | 2834401 | 18 | Done | 2023-04-13 | On Air | 2023-04-29 | 18 | 0 | To be activated at tne end of the month |  | 12
FOUM ASMAHAN. 256788006888. Lugala.0.31351,32.54081. FTTH_10_M | Rubaga | MTNFTTH74480536 | Chrif | 2023-04-16 | 2023-04-16 | 2479714 | 499521 | 2544929 | 2979234 | 16 | Done | 2023-04-18 | On Air | 2023-05-02 | 16 | 0 | Client has been upcountry, survey confirmed for tomorrow. |  | 5
. 256770837382. OLD KAMPALA.0.098334,32.504918. FTTH_40_M | Kitala | MTNFTTH74017851 | Chrif | 2023-04-16 | 2023-04-16 | 2359268.6667 | 445603.6667 | 1996225.3333 | 2804872.6 | 8 | Done | 2023-04-18 | On Air | 2023-04-30 | 14 | 6 | Customer is shifting |  | 8
ANITA BALIKOBAKU. 256773308355. OLD KAMPALA.0.189074,32.540132. FTTH_40_M | ENTEBBE | MTNFTTH83478834 | Pavicon | 2023-04-11 | 2023-04-18 | 1444326 | 368252 | 1041596 | 1812578 | 0 | Done | 2023-04-20 | On Air | 2023-04-30 | 19 | 12 | Re-assigned to Pavicon on 26-APRIL from Chrif Group |  | 4
JOLLY KAWEESI. 256760689594. 8a Nganda Ln.0.316399,32.647156. FTTH_10_M | Luzira | MTNFTTH84557253 | Enetworks | 2023-04-22 | 2023-04-22 | 2327169 | 461326 | 1954439 | 2788494.6 | 0 | Done | 2023-04-24 | On Air | 2023-05-02 | 10 | 10 |  |  | 13
JACKLINE NAMATOVU. 256774535258. OLD KAMPALA.0.098826,32.505979. FTTH_10_M | Kitala | MTNFTTH62035031 | Chrif | 2023-04-22 | 2023-04-22 | 2359268.6667 | 445603.6667 | 1996225.3333 | 2804872.6 | 3 | Done | 2023-04-24 | On Air | 2023-04-30 | 8 | 5 | ROW |  | 13
Masereka Nuhaimu. 256787421129. Sahara Primary School.0.25402,32.606338. FTTH_10_M | Ggaba | MTNFTTH87847208 | Rontech | 2023-04-24 | 2023-04-24 | 997342 | 712651 | 1456912 | 1709993 | 0 | Done | 2023-04-26 | On Air | 2023-04-29 | 5 | 5 |  |  | 12
ANNET NAMPIIMA. 256771651683. Mutundwe.0.280748,32.540416. FTTH_10_M | RUBAGA | MTNFTTH05707770 | Pavicon | 2023-04-25 | 2023-04-25 | 1824056 | 351296 | 1564506 | 2175352 | 0 | Done | 2023-04-27 | On Air | 2023-04-30 | 5 | 5 |  |  | 5
MTN UGANDA LTD null. 256772123321. Wash Masters Najjera.0.380308,32.625985. FTTH_10_M | Ntinda Kiwatule | MTNFTTH31220507 | Soliton | 2023-04-24 | 2023-04-24 | 0 |  | 0 | 0 | 0 | Done | 2023-04-26 | On Air | 2023-05-01 | 7 | 7 |  |  | 0
MUKUNDANE MICHAEL KYAKAMARA. 256772415358. Seguku.0.237516,32.541173. FTTH_20_M | Najjanankumbi | MTNFTTH68383352 | Rontech | 2023-04-25 | 2023-04-25 | 1224129 | 682434 | 1623605 | 1906563 | 0 | Done | 2023-04-27 | On Air | 2023-04-29 | 4 | 4 |  |  | 5
LUCIA ANIENDE. 256775108919. OLD KAMPALA.0.355407,32.648277. FTTH_20_M | Bweyogerere | MTNFTTH45036616 | Enetworks | 2023-04-25 | 2023-04-25 | 2421868 | 700904.2 | 2304438 | 3122772.2 | 0 | Done | 2023-04-27 | On Air | 2023-04-28 | 3 | 3 |  |  | 6
BRENDA NASSALI. 256760170397. OLD KAMPALA.0.338179,32.596747. FTTH_10_M | Ntinda Bukoto | MTNFTTH11417144 | Rak | 2023-04-25 | 2023-04-25 | 208750 | 437545 | 400060 | 646294 | 0 | Done | 2023-04-27 | On Air | 2023-04-29 | 4 | 4 |  |  | 13
GEORGE WAIBALE WANDERA. 256762063075. Kamuli Road.0.35479,32.644415. FTTH_10_M | Bweyogerere | MTNFTTH47620535 | Enetworks | 2023-04-25 | 2023-04-25 | 949981 | 464381 | 1142049 | 1414362 | 0 | Done | 2023-04-27 | On Air | 2023-04-29 | 4 | 4 |  |  | 3
ELIJAH WAISANKA. 256784851148. JINJA.0.424655,33.2107. FTTH_10_M | Jinja | MTNFTTH57015272 | Enetworks | 2023-04-27 | 2023-04-27 | 1502834 | 337005.5 | 1362699 | 1839839.5 | 0 | Done | 2023-04-29 | On Air | 2023-04-29 | 2 | 2 |  |  | 20
ACHAALI ISRAEL TINKASIMIIRE. 256774123888. OLD KAMPALA.0.370048,32.647122. FTTH_20_M | Kira | MTNFTTH62143171 | Soliton | 2023-04-27 | 2023-04-29 | 0 |  | 0 | 0 | 0 | Done | 2023-05-01 | On Air | 2023-04-30 | 3 | 1 |  |  | 0
Brian Seremba. 256776075354. OLD KAMPALA.0.362043,32.601072. FTTH_10_M | Kisaasi | MTNFTTH87686736 | Soliton | 2023-04-28 | 2023-04-28 | 0 |  | 0 | 0 | 0 | Done | 2023-04-30 | On Air | 2023-05-01 | 3 | 3 |  |  | 7
Owen Paul. 256763475339. 9J5Q H26, Kampala, Uganda Next to wamala girls hostel Kabaka farm.0.3585,32.6371. FTTH_20_M | Ntinda Kyambogo | MTNFTTH28121877 | Soliton | 2023-04-29 | 2023-04-29 | 1937669 | 495523.6 | 2,391,689.0 | 2887212.6 | 0 | Done | 2023-05-01 | On Air | 2023-04-30 | 1 | 1 |  |  | 12
MUWANGA MARVIN.256782363433.Mutundwe.0.280748,32.540416.FTTH_10_M | RUBAGA | MTNFTTH83516581 | Pavicon | 2023-04-28 | 2023-04-29 | 233750 | 420002 | 401280 | 653752 | 0 | Done | 2023-05-01 | On Air | 2023-04-30 | 2 | 1 |  |  | 11
YAHYE SHARIF HAMOD.256773284552.Lubiri Secondary School.0.304802,32.548941.FTTH_10_M | RUBAGA | MTNFTTH46537884 | Pavicon | 2023-04-27 | 2023-04-29 | 233750 | 407285 | 395160 | 641035 | 0 | Done | 2023-05-01 | On Air | 2023-04-30 | 3 | 1 |  |  | 22
SAMUEL OBACI.256760851054.ndeeba road uganda.0.299245,32.575208. FTTH_10_M | RUBAGA | MTNFTTH36313258 | Pavicon | 2023-04-30 | 2023-04-30 | 233750 | 360655.6 | 372720 | 594405.6 | 0 | Done | 2023-05-02 | On Air | 2023-04-30 | 0 | 0 |  |  | 4
ZURAH NANTONGO.256772247355.OLD KAMPALA.0.392081,32.660769.FTTH_10_M | Kisaasi | MTNFTTH86033852 | Enetworks | 2023-04-04 | 2023-04-05 | 2247488 | 502120.6 | 2142378 | 2749608.6 | 0 | Done | 2023-04-07 | On Air | 2023-04-30 | 26 | 25 | ROW |  | 6
MARK TUSUBIRA.256780433195.Kagoma Holdings Company limited.0.424767,33.21064.FTTH_20_M | Jinja | MTNFTTH53766745 | Enetworks | 2023-04-18 | 2023-04-26 | 150283 | 337005.5 | 1362699 | 1839839.5 | 0 | Done | 2023-04-28 | On Air | 2023-04-30 | 12 | 4 |  |  | 20
Sushil Sharma.256782419161.dfcu BANK Entebbe Town Branch, Entebbe, Uganda entebbe town dfcu bank.0.0604,32.4719.FTTH_10_M | Entebbe | MTNFTTH06286174 | Chrif | 2023-04-14 | 2023-04-27 | 208750 | 411470.6 | 402150 | 620220.6 | 0 | Done | 2023-04-29 | On Air | 2023-04-29 | 15 | 2 |  |  | 0
STEPHEN MUGISA.256782885759.Kisaasi:Komamboga Road.0.377237,32.589764.FTTH_10_M | Kisaasi | MTNFTTH80800675 | Soliton | 2022-10-01 | 2023-04-27 | 0 | 578592.8 | 336543 | 578592.8 | 0 | Done | 2023-04-29 | On Air | 2023-04-29 | 210 | 2 |  |  | 0
ADAIR KANZIRA. 256772122653. CARGEN.0.318982,32.598145. FTTH_10_M | Ntinda Kiwatule | MTNFTTH04261723 | Soliton | 2023-04-29 | 2023-04-29 | 0 | 557819.1 | 327920 | 557819.1 | 0 | Done | 2023-05-01 | On Air | 2023-05-01 | 2 | 2 |  |  | 0
NAWIIRA NAKIRANDA.256763810930.Location.0.353511,32.620643. FTTH_10_M | Ntinda Bukoto | MTNFTTH17437670 | Rak | 2023-03-28 | 2023-04-27 | 208750 | 405150 | 378660 | 613900 | 0 | Done | 2023-04-29 | On Air | 2023-05-02 | 35 | 5 |  |  | 0
SUZAN MWEBE NDWADEWAZIBWA. 256789222634. Mpererwe,Namere.0.383356,32.57661. FTTH_10_M | Gayaza | MTNFTTH48572186 | Enetworks | 2023-04-05 | 2023-04-05 | 0 | 0 | 220562.5 | 1101712.5 | 24 | Done | 2023-04-07 | On Air | 2023-05-05 | 30 | 6 | Requested to be commissioned at the end of month |  | 8
DEBORAH NANSUBUGA. 256782729549. Lukuli Water Pump.0.282059,32.593541. FTTH_10_M | Ggaba | MTNFTTH23158236 | Rontech | 2023-04-17 | 2023-04-17 | 2551033 | 736899 | 3026231 | 3287932 | 6 | Done | 2023-04-19 | On Air | 2023-05-02 | 15 | 9 | Pending consolidation |  | 8
NABBANJA RITAH. 256785236222. OLD KAMPALA.0.364251,32.636107. FTTH_10_M | Ntinda Kyambogo | MTNFTTH38327553 | Soliton | 2023-04-19 | 2023-04-19 | 0 |  | 0 | 0 | 0 | Done | 2023-04-21 | On Air | 2023-05-02 | 13 | 13 |  |  | 4
ISAAC SSEGAWA. 256782186538. OLD KAMPALA.0.316493,32.574214. FTTH_20_M | Old Park | MTNFTTH42535770 | Rak | 2023-04-26 | 2023-04-26 | 241735 | 504204 | 535546 | 745939 | 0 | Done | 2023-04-28 | On Air | 2023-05-03 | 7 | 7 |  |  | 6
PAUL KAHERU. 256776500656. OLD KAMPALA.0.367528,32.635595. FTTH_20_M | Ntinda Kyambogo | MTNFTTH40440805 | Soliton | 2023-04-27 | 2023-04-27 | 0 | 583675.2 | 358393 | 583675.2 | 0 | Done | 2023-04-29 | On Air | 2023-05-03 | 6 | 6 |  |  | 0
KYEMBA HENRY. 256772324744. OLD KAMPALA.0.250483,32.615204. FTTH_10_M | Najjanankumbi | MTNFTTH01161874 | Rontech | 2023-04-28 | 2023-04-28 | 0 | 0 | 0 | 0 | 0 | Done | 2023-04-30 | On Air | 2023-05-02 | 4 | 4 |  |  | 10
SHIFAH NAMATA. 256777136668. Bwaise roundabout.0.350182,32.562908. FTTH_10_M | MAKERERE | MTNFTTH25172850 | Pavicon | 2023-04-30 | 2023-04-30 | 324300 | 206601 | 1102828 | 530901 | 0 | Done | 2023-05-02 | On Air | 2023-05-03 | 3 | 3 |  |  | 2
SYDNEY TENDO. 256778664523. Ntinda.0.350605,32.615769. FTTH_10_M | Makerere | MTNFTTH53156427 | Rak | 2023-04-30 | 2023-04-30 | 324300 | 206601 | 1102828 | 530901 | 0 | Done | 2023-05-02 | On Air | 2023-05-03 | 3 | 3 | Customer undecided where he wants the service |  | 3
Harriet Nattabi. 256783212124. Lungujja Kitunzi.0.310005,32.540332. FTTH_10_M |  | MTNFTTH28412407 | Pavicon | 2023-04-28 | 2023-04-28 | 3043016 | 359774 | 2549726 | 3402790 | 2 | Done | 2023-04-30 | Not On Air |  | 0 | 0 | High BOQ |  | 9
GEORGE GUMISIRIZA.256788742973.Najjanankumbi:Lweza.0.220727,32.548955.FTTH_10_M | Najjanankumbi | MTNFTTH24763623 | Rontech | 2022-11-04 | 2023-04-24 | 0 | 0 | 0 | 0 | 0 | Done | 2023-04-26 | On Air | 2023-05-02 | 179 | 8 |  |  | 5
PETER CLAVER MBIDDE.256772856485.Location.0.418311.32.61694. FTTH_20_M | Kira | MTNFTTH88037011 | Soliton | 2023-02-04 | 2023-04-29 | 0 | 0 | 0 | 0 | 0 | Done | 2023-05-01 | On Air | 2023-05-04 | 89 | 5 |  |  | 4
ANTHONY BUSULWA.256775530345.OLD KAMPALA.0.286729,32.630654.FTTH_10_M | Muyenga | MTNFTTH05506558 | Rontech | 2023-04-27 | 2023-04-27 | 0 | 0 | 0 | 0 | 0 | Done | 2023-04-29 | On Air | 2023-05-03 | 6 | 6 |  |  | 15
Ndugwa Ukasha.256789416335.Kampala Muyenga Bukasa.0.3189,32.5981.FTTH_10_M | Muyenga | MTNFTTH58524820 | Rontech | 2023-04-06 | 2023-04-24 | 0 | 0 | 0 | 0 | 0 | Done | 2023-04-26 | On Air | 2023-05-03 | 27 | 9 |  |  | 17
null null. 256783007198. UMA multi purpose hall.0.32904232.609918. FTTH_20_M |  | MTNFTTH30650716 | Enetworks | 2023-04-03 | 2023-04-03 | 0 | 2203425.4 | 1762300 | 2203425.4 | 7 | ROW delay | 2023-04-05 | Not on air |  |  |  | ROW from UMA
null null. 256772623151. Kasubi Market.0.33293232.555834. FTTH_10_M |  | MTNFTTH42624621 | Rontech | 2023-04-04 | 2023-04-04 | 0 | 0 | 0 | 0 | 10 | Customer Delay | 2023-04-06 | Not on air |  |  |  | Not aware of the service
null null. 256779574052. OLD KAMPALA.0.360956,32.653666. FTTH_20_M | Bweyogerere | MTNFTTH84503127 | Enetworks | 2023-04-04 | 2023-04-04 | 0 | 0 | 685630 | 2971829.3333 | 25 | Done | 2023-04-06 | On Air | 2023-05-08 |  |  | To be commissioned in May
SHAMIM NAKANJAKO. 256789860887. OLD KAMPALA.0.238015,32.539745. FTTH_10_M |  | MTNFTTH16423004 | Rontech | 2023-04-05 | 2023-04-05 | 0 | 0 | 124437 | 3723149.5 | 10 | Customer delay | 2023-04-07 | Not on air |  |  |  | Alternative number got. Contractor is in touch with the client
NASIIBAH NAKAJUBI. 256773426018. OLD KAMPALA.0.377486,32.589764. FTTH_20_M |  | MTNFTTH03064411 | Enetworks | 2023-04-06 | 2023-04-06 | 0 | 0 | 542026.2 | 3105744.2 | 4 | Customer delay | 2023-04-08 | Not on air |  |  |  | On hold. Waiting for caretaker's support
Jane Kasubo. 256772380505. OLD KAMPALA.0.210373,32.536037. FTTH_10_M |  | MTNFTTH84237385 | Chrif | 2023-04-09 | 2023-04-09 | 0 | 0 | 0 | 0 | 8 | Customer delay | 2023-04-11 | Not on air |  |  |  | Doesnt pick up calls
JOSHUA KISOZI. 256781778716. Kajjansi.0.207025,32.540103. FTTH_20_M |  | MTNFTTH01202420 | Chrif | 2023-04-11 | 2023-04-11 | 0 | 0 | 0 | 0 | 10 | Customer delay | 2023-04-13 | Not on air |  |  |  | Not picking
LILLIAN AKOYO. 256779208956. Canon Road.0.359258,32.620362. FTTH_20_M |  | MTNFTTH62648327 | Enetworks | 2023-04-11 | 2023-04-11 | 0 | 0 | 2127524.5 | 2740402 | 21 | Done | 2023-04-13 | Not on air |  |  |  | Requested to be commissioned at the end of the month
JOAN KANYUNYUZI. 256784357127. Makindye Division.0.272835,32.617492. FTTH_10_M |  | MTNFTTH12724485 | Rontech | 2023-04-11 | 2023-04-11 | 0 | 0 | 473518 | 3982093 | 6 | On Hold | 2023-04-13 | Not on air |  |  |  | client consolidated but BOQ is still High.
DIANA ABAA. 256789676392. Buziga Waterpump.0.267611,32.614307. FTTH_10_M |  | MTNFTTH48680207 | Rontech | 2023-04-12 | 2023-04-12 | 0 | 0 | 545349.5 | 4156832 | 7 | On Hold | 2023-04-14 | Not on air |  |  |  | Consolidation, but high BOQ.
KASENGE FLAVIA ELEANOR. 256772212176. Buziga Waterpump.0.267611,32.614307. FTTH_20_M |  | MTNFTTH51655332 | Rontech | 2023-04-11 | 2023-04-13 | 0 | 0 | 545349.5 | 4156832 | 6 | On Hold | 2023-04-15 | Not on air |  |  |  | Consolidation, but high BOQ.
ELIJAH BEESIGOMWE. 256775656227. OLD KAMPALA.0.287448,32.577613. FTTH_10_M |  | MTNFTTH36145374 | Rontech | 2023-04-13 | 2023-04-13 | 0 | 0 | 473518 | 3982093 | 7 | On Hold | 2023-04-15 | Not on air |  |  |  | client consolidated but BOQ is still High.
SUMAYYA NANYANZI. 256778078645. KITGUM.0.31942,32.599046. FTTH_10_M | Mbale | MTNFTTH73082235 | Rontech | 2023-04-13 | 2023-04-13 | 0 | 0 | 0 | 0 | 0 | WIP | 2023-04-15 | Not on air |  |  |  | Mobilizing to start Civil works
CATHERINE NAKIBONEKA. 256772122979. OLD KAMPALA.0.373713,32.660416. FTTH_10_M | Bweyogerere | MTNFTTH65468760 | Enetworks | 2023-04-16 | 2023-04-16 | 0 | 0 | 2581749 | 3599389.6 | 14 | Done | 2023-04-18 | On air | 2023-05-06 |  |  | Mobilizing to start Civil works, High BOQ |  | 11
KIRABO DERRICK. 256772066847. OLD KAMPALA.0.322231,32.574971. FTTH_10_M | Rubaga | MTNFTTH54084315 | Chrif | 2023-04-17 | 2023-04-17 | 0 | 0 | 0 | 0 | 23 | WIP | 2023-04-19 | Not on air |  |  |  | Delayed by client(Not picking calls).
KORYOM AWET ALOR KUOL. 256782000121. Bukasa.0.29886,32.62068. FTTH_10_M |  | MTNFTTH88633713 | Rontech | 2023-04-18 | 2023-04-18 | 0 | 0 | 0 | 0 | 5 | On Hold | 2023-04-20 | Not on air |  |  |  | Contact not available
Clarke Means. 256771046678. 5b Lukuli 8105, Kampala, Uganda.0.278393,32.593113. FTTH_10_M |  | MTNFTTH43556460 | Pavicon | 2023-04-20 | 2023-04-20 | 0 | 0 | 0 | 0 | 6 | On Hold | 2023-04-22 | Not on air |  |  |  | He needs 4 Poles - Looking for consolidation
JOSEPH MAKAWA. 256784185800. Kawaala Health Center 3.0.340881,32.553713. FTTH_10_M_O |  | MTNFTTH62787108 | Rontech | 2023-04-15 | 2023-04-19 | 0 | 0 | 0 | 0 |  | WIP | 2023-04-21 | Not on air |  |  |  | Assigned to pavicon
. 256777515585. OLD KAMPALA.0.099566,32.505626. FTTH_10_M | Rubaga | MTNFTTH26564258 | Chrif | 2023-04-22 | 2023-04-22 | 0 | 0 | 0 | 0 | 3 | On Hold | 2023-04-24 | Not on air |  |  |  | Consolidation done.Delayed by client as they are not ready for activation.
. 256760805523. Najjanankumbi Stella Stage.0.283561,32.569361. FTTH_10_M | Najjanankumbi | MTNFTTH54571815 | Rontech | 2023-04-24 | 2023-04-24 | 2314758 | 607796 | 2703876 | 0 | 14 | Done | 2023-04-26 | (On Air) | 2023-05-08 |  |  | Client unavailable
SOPHIA ELIZABETH NAKIGANDA SONKO. 256786843080. Bwebajja Dundu.0.164019,32.54788. FTTH_10_M | Bwebajja | MTNFTTH87817381 | Chrif | 2023-04-24 | 2023-04-24 | 0 | 0 | 0 | 0 | 15 | WIP | 2023-04-26 | Not on air |  |  |  | Third person paid, WIP.
BARBRA NAMUYIGA. 256777132868. Salaama Road.0.264957,32.595752. FTTH_20_M | Ggaba | MTNFTTH22553585 | Rontech | 2023-04-25 | 2023-04-25 | 744462 | 563425 | 1024386 | 0 |  | WIP | 2023-04-27 | Not on air |  |  |  | Mobilizing to start Civil works
JASBIR SINGH GHATAURA.256772684070.Bugolobi:Mbuya Road.0.310649,32.622283.FTTH_40_M | Bugolobi | MTNFTTH02853530 | Enetworks | 2023-01-11 | 2023-04-18 | 0 | 0 | 1402930 | 2182750.6 | 8 | Done | 2023-04-20 | On air | 2023-05-07 |  |  | Burried Manhole - ZTE team supporting |  | 7
CAROL KHARONO. 256784078332. OLD KAMPALA.0.232107,32.533479. FTTH_20_M | Najjanankumbi | MTNFTTH28138770 | Rontech | 2023-04-24 | 2023-04-24 | 7079766 | 1551902 | 8071615 | 0 |  | WIP | 2023-04-26 | Not on air |  |  |  | consolidated with other two clients
DESMOND KOPIO. 256772943165. HOTEL LA VENA.0.225834,32.536923. FTTH_20_M | Najjanankumbi | MTNFTTH07688407 | Rontech | 2023-04-25 | 2023-04-25 | 2131859 | 725202 | 2597104 | 0 |  | WIP | 2023-04-27 | Not on air |  |  |  | ROW
RONALD ATWINE. 256779073615. Mulawa Mall.0.406403,32.641768. FTTH_10_M | Bulindo | MTNFTTH76136458 | Soliton | 2023-04-25 | 2023-04-25 | 0 | 0 | 0 | 0 |  | Refund | 2023-04-27 | Not on air |  |  |  | Due to ROW issue with Landlord, the client requests for a refund.
Brian Kikonyogo. 256772950713. Lubowa Terrace.0.237438,32.564759. FTTH_20_M |  | MTNFTTH38773523 | Rontech | 2023-04-26 | 2023-04-26 | 1929520 | 761175 | 2436514 | 0 |  | WIP | 2023-04-28 | Not on air |  |  |  | Client unavailable
ATANASIO OMONY. 256783970418. Gulu Town Primary School.2.784314,32.309013. FTTH_40_M |  | MTNFTTH77888126 | Pavicon | 2023-04-26 | 2023-04-26 | 0 | 0 | 0 | 0 | 5 | On Hold | 2023-04-28 | Not on air |  |  |  | Not responding to appointments
EUNICE ACHIRO. 256779228534. TotalEnergies Najjera Service Station.0.385521,32.625953. FTTH_10_M | Kiwatule | MTNFTTH80211204 | Soliton | 2023-04-26 | 2023-04-26 | 0 | 0 | 0 | 0 | 13 | On hold | 2023-04-28 | Not on air |  |  |  | The site is out of DOA range, pending consolidation.
. 256786681015. MBALE.1.075127,34.176149. FTTH_10_M | MBALE. | MTNFTTH17364262 | Rontech | 2023-04-26 | 2023-04-26 | 0 | 1360163 | 1147572 | 0 | 12 | Done | 2023-04-28 | On air | 2023-05-06 |  |  | ZTE for support |  | 10
AISHA NAMUTEBI. 256772444883. Mile 8 Masjid, Gayaza Road.0.419642,32.596998. FTTH_20_M | Gayaza | MTNFTTH24354483 | Soliton | 2023-04-26 | 2023-04-26 | 0 | 0 | 0 | 0 |  | Refund | 2023-04-28 | Not on air |  |  |  | The site is out of DOA range(1km about 12 poles)
ROBERT DEAN WESTMORELAND. 256778445254. OLD KAMPALA.0.258417,32.630429. FTTH_10_M | Ggaba | MTNFTTH74304223 | Rontech | 2023-04-27 | 2023-04-27 | 0 | 0 | 0 | 0 |  | Done | 2023-04-29 | On air | 2023-05-06 |  |  | Mobilizing to start Civil works |  | 10
PHIONA KAMPIRE. 256779945553. Muyenga Tank Hill.0.292953,32.609375. FTTH_20_M |  | MTNFTTH80000257 | Rontech | 2023-04-27 | 2023-04-27 | 0 | 0 | 0 | 0 |  | WIP | 2023-04-29 | Not on air |  |  |  | High BOQ
ANTHONY BUSULWA. 256775530345. OLD KAMPALA.0.286729,32.630654. FTTH_10_M | Muyenga | MTNFTTH05506558 | Rontech | 2023-04-27 | 2023-04-27 | 1886092 | 710301 | 2343312 | 0 | 5 | Done | 2023-04-29 | On air | 2023-05-03 |  |  | Delayed by contractor |  | 15
SIMON NYONJO. 256783070779. OLD KAMPALA.0.29223,32.608673. FTTH_20_M | Muyenga | MTNFTTH46745770 | Rontech | 2023-04-25 | 2023-04-28 | 860779 | 563314 | 1135271 | 0 | 11 | Done | 2023-04-30 | On air |  |  |  | Not picking calls |  | 8
FARIDAH NALUTAYA. 256788694179. Noble wigs and Hair Pieces Kampala.0.254192,32.626498. FTTH_10_M | Ggaba | MTNFTTH78805028 | Rontech | 2023-04-28 | 2023-04-28 | 2119086 | 662373 | 2534276 | 0 | 8 | Done | 2023-04-30 | On air | 2023-05-06 |  |  | Client will let contractor know when to install service |  | 8
GOMEZ HAJARA NAZIRI. 256778636213. Entebbe Road.0.310404,32.580304. FTTH_10_M | Entebbe | MTNFTTH35678773 | Pavicon | 2023-04-30 | 2023-04-30 | 0 | 0 | 0 | 0 |  | WIP | 2023-05-02 | Not on air |  |  |  | Mobilizing to start Civil works
BRIAN WALUSIMBI.256774409697.tinda (Kiwatule - Naalya):Naalya Road.0.365544,32.645383. FTTH_10_M | Ntinda Kyambogo | MTNFTTH81160061 | Soliton | 2022-07-04 | 2023-04-28 | 0 | 0 | 0 | 0 |  | Done | 2023-04-30 | On air | 2023-05-06 |  |  | Mobilizing to start Civil works |  | 0
Magala Charles.256774921728.null.0.316055,32.652236.FTTH_10_M |  | MTNFTTH78416062 | Enetworks | 2023-03-02 | 2023-04-30 | 0 | 0 | 0 | 0 |  | Refunded | 2023-05-02 | Not on Air |  |  |  | Mobilizing to start Civil works
Phoebe Nalubiri.256788522435.munyonyo.0.3189.32.5981. FTTH_10_M | Ggaba | MTNFTTH54715322 | Rontech | 2023-04-11 | 2023-04-28 | 0 | 0 | 0 | 0 |  | Done | 2023-04-30 | Not on Air | 2023-04-08
NEEMA MARIANA MBONIGABA.256780637600.Ggaba:Wavamuno Road.0.248949,32.622962.FTTH_20_M | Ggaba | MTNFTTH07253602 | Pavicon | 2023-04-11 | 2023-04-28 | 0 | 0 | 0 | 0 |  | Done | 2023-04-30 | Not on Air | 2023-04-08
Formulas:
Planned End Date = [Date of payment/Start Date]+2