## Master List
Customer Details | Date | Requests | Work Order # | Survey delay due to customer | On-site surve | BOQ | Business Case Approved | Customer Commitment/Payment | Summary remarks | Remarks
null null. 256788254548. Bwebajja:Arkright City.0.183424,32.539219 . FTTH_20_M_O | 2022-12-31 | FTTO | MTNFTTO44422416 | 0 | Completed | UGX 3,357,296.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256779703720. Kigo:Ndejje.0.247394,32.545792 . FTTH_20_M_O | 2022-12-31 | FTTO | MTNFTTO36283144 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Customer is far from cable
null null. 256783018888. Namuwongo:Namuwongo Road.0.300298,32.621032 . FTTH_20_M_O | 2022-12-30 | FTTO | MTNFTTO38215204 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible
null null. 256760962789. Rubaga:Stensera Road.0.298869,32.601517 . FTTH_20_M_O | 2022-12-30 | FTTO | MTNFTTO41666061 | 0 | Completed | UGX 4,612,624.60 | Office Internet approved | Office Internet (APP.) Pending
null null. 256788120774. Kisaasi:Kyanja Ring Road.0.394091,32.598952 . FTTH_40_M_O | 2022-12-30 | FTTO | MTNFTTO21572815 | 0 | Completed | UGX 3,466,029 | Office Internet approved | Office Internet (APP.) Paid
null null. 256788800515. Luzira:Old Butabika Road.0.315045,32.654657 . FTTH_20_M_O | 2022-12-29 | FTTO | MTNFTTO14081067 | 0 | Completed | UGX 13,337,838.8 | Pending Review | Office Internet (APP.) Paid |  | Consolidated Null null(772122602), Null null(0772120227) , Null null(0788800515), null null (0787255904),
ERIA BENJAMINE JJAGWE. 256782356690. Najjanankumbi:Kampala Entebbe Road.0.283677,32.568446 . FTTH_20_M_O | 2022-12-29 | FTTO | MTNFTTO47650540 | 0 | Completed | UGX 2,070,277.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256775078511. Ntinda Bukoto:Naguru Drive.0.351552,32.601759 . FTTH_20_M_O | 2022-12-29 | FTTO | MTNFTTO27382182 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | No Fiber Access
null null. 256773344238. Ntinda (Kyambogo - Min Village):Martyrs Way.0.355279,32.616217 . FTTH_40_M_O | 2022-12-28 | FTTO | MTNFTTO17766834 | 2 | Completed | UGX 4,290,700 | Office Internet approved | Office Internet (APP.) Paid
null null. 256775586397. Kololo:KAR Road.0.323461,32.599648 . FTTH_40_M_O | 2022-12-28 | FTTO | MTNFTTO51645103 | 0 | Completed | UGX 2,531,863.00 | Office Internet approved | Office Internet (APP.) Pending
null null. 256783740055. Namuwongo:Kisugu Road.0.337853,32.543086 . FTTH_20_M_O | 2022-12-28 | FTTO | MTNFTTO43267232 | 0 | Completed | UGX 6,688,824.20 | Office Internet approved | Office Internet (APP.) Paid
null null. 256786216613. Rubaga:Kabusu Road.0.298534,32.535853 . FTTH_20_M_O | 2022-12-30 | FTTO | MTNFTTO13817162 | 0 | Completed |  | Office Internet approved | Office Internet (APP.) Paid
null null. 256789367180. Rubaga:Wankulukuku Road.0.316275,32.585628 . FTTH_20_M_O | 2022-12-28 | FTTO | MTNFTTO21303414 | 2 | Completed | UGX 6,688,824.20 | Office Internet rejected |  |  | not feasible-760m, 11 poles
null null. 256762660651. Arua:Arua Hill.3.518897,31.322353 . FTTH_20_M_O | 2022-12-27 | FTTO | MTNFTTO28634411 | 2 | Completed |  | Office Internet rejected |  | Not interested | CLIENT MADE APPOINTMENT WITH BUT WAS MAKING THE NUMBER BUSY AND STANDARD SMS WAS SENT
null null. 256772486101. Entebbe:Hill Lane.0.063109,32.473702 . FTTH_20_M_O | 2022-12-24 | FTTO | MTNFTTO44818626 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Not feasible, client about 420m from the fiber node
null null. 256787956761. Mbarara:Ntare Road.-0.407562,29.775718 . FTTH_20_M_O | 2022-12-22 | FTTO | MTNFTTO76541610 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Rukungiri
EMMANUEL TUMUHEIRWE. 256776566004. Kisaasi:Bahai Road.0.36246,32.589253 . FTTH_40_M_O | 2022-12-21 | FTTO | MTNFTTO75337521 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | NOT FEASIBLE- 1166M (0.36234525 , 32.58921403)
null null. 256771211261. Makerere:Makerere Hill Road.0.350234,32.575659 . FTTH_20_M_O | 2022-12-21 | FTTO | MTNFTTO75852507 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | No Fiber Access
null null. 256772746557. Old Park:Luwum Street.0.307432,32.570534 . FTTH_40_M_O | 2022-12-21 | FTTO | MTNFTTO78510556 | 1 | Completed | UGX 2,049,221.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773115002. Ggaba:Salaama Road.0.263849,32.603744 . FTTH_20_M_O | 2022-12-20 | FTTO | MTNFTTO53330086 |  | Completed |  | Office Internet rejected |  | Not reachable | number not available-msg sent
null null. 256772281468. Mbarara:Buremba Road.-0.607999,30.664978 . FTTH_20_M_O | 2022-12-20 | FTTO | MTNFTTO35872234 |  | Completed |  | Office Internet rejected |  | Not reachable | number cant be reached
null null. 256776541560. Luzira:Commercial Road.0.310334,32.635304 . FTTH_20_M_O | 2022-12-19 | FTTO | MTNFTTO76025777 |  | Completed |  | Office Internet rejected |  | Not interested | client already has service
null null. 256772970641. Ntinda (Kiwatule - Naalya):Flamingo Close.0.357614,32.619044 . FTTH_40_M_O | 2022-12-19 | FTTO | MTNFTTO81816555 | 0 | Completed | UGX 1,818,380 | Office Internet approved | Office Internet (APP.) Paid
null null. 256785137637. Rubaga:Rubaga Road.0.296561,32.556695 . FTTH_20_M_O | 2022-01-01 | FTTO | MTNFTTO37156304 | 3 | Completed | UGX 2,137,119.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256782361437. Buwate:Seeta Kasangati.0.419565,32.618779 . FTTH_20_M_O | 2022-01-01 | FTTO | MTNFTTO52688335 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | NOT FEASIBLE- 420M (0.41840982 , 32.61772022)
null null. 256781461023. Makerere:Bombo Road.0.34057,32.570327 . FTTH_20_M_O | 2023-01-02 | FTTO | MTNFTTO87780878 | 0 | Completed | UGX 3,789,082.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772259133. Makindye:Lukuli Road.0.284591,32.577416 . FTTH_40_M_O | 2023-01-02 | FTTO | MTNFTTO45316826 | 2 | Completed | UGX 3,668,920.60 | Office Internet approved | Office Internet (APP.) Pending
null null. 256783152627. Ntinda Bukoto:Saddler Way.0.341104,32.59937 . FTTH_20_M_O | 2023-01-02 | FTTO | MTNFTTO84778351 | 0 | Completed | UGX 2,828,060.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256779044605. Rubaga:Kabusu Road.0.298436,32.535966 . FTTH_20_M_O | 2023-01-02 | FTTO | MTNFTTO58608580 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-400m 5poles
null null. 256778542478. Rubaga:Lungujja.0.298393,32.536057 . FTTH_20_M_O | 2023-01-02 | FTTO | MTNFTTO32811822 | 1 | Completed | UGX 2,719,529.60 | Office Internet approved | Office Internet (APP.) Paid
ROBERT TURAHE. 256777968471. Kisaasi:Bahai Road.0.356995,32.583103 . FTTH_20_M_O | 2023-01-02 | FTTO | MTNFTTO24836711 | 1 | Completed | UGX 3,799,911 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773155598. Najjanankumbi:Kampala Entebbe Road.0.295037,32.572762 . FTTH_40_M_O | 2023-01-02 | FTTO | MTNFTTO05000357 | 0 | Completed | UGX 3,792,869.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256785936985. Mbarara:Ntare Road.-0.604294,30.643679 . FTTH_40_M_O | 2023-01-02 | FTTO | MTNFTTO87076426 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-9 poles
null null. 256773879175. Luzira:Mutungo Ring Road.0.338189,32.622669 . FTTH_20_M_O | 2023-01-02 | FTTO | MTNFTTO21486772 | 1 | Completed | UGX 4,091,795.0 | Office Internet approved | Office Internet (APP.) Paid
CIPLA QUALITY CHEMICALS. 256772789725. KANYANYA.0.369885,32.58359 . FTTH_40 | 2023-01-03 | FTTO ( Postpaid ) | MTNFTTP08235775 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256779976697. Ggaba:Ggaba Road.0.292326,32.605508 . FTTH_40_M_O | 2023-01-03 | FTTO | MTNFTTO54716870 | 2 | Completed | UGX 3,330,552.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256775999995. Mbale:Republic Street.1.071768,34.181573 . FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO01026102 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-600m
Robert Mugga. 256772517141. Kisaasi:Bahai Road.0.371402,32.596808 . FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO10731528 | 0 | Completed | UGX 2,010,375 | Office Internet approved | Office Internet (APP.) Pending
null null. 256783307541. Luzira:Port Bell road.0.353921,32.607822 . FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO32174637 | 0 | Completed | UGX 2,363,651.0 | Office Internet approved | Office Internet (APP.) Paid
PETROLEUM AUTHORITY OF UGANDA. 256785980600. SALAAMA MUNYONYO.0.244253,32.617981 . FTTH_20 | 2023-01-03 | FTTO ( Postpaid ) | MTNFTTP63121465 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256776170588. Luzira:Port Bell road.0.304387,32.635765 . FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO87845404 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256775166621. Makerere:Sir Apollo Kaggwa Road.0.308021,32.570305 . FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO86380554 | 0 | Completed | UGX 4,261,624 | Office Internet approved | Office Internet (APP.) Paid
Poly. 256775947910. Rubaga:Rubaga Road.0.314548,32.574478 . FTTH_40_M_O | 2023-01-04 | FTTO | MTNFTTO57156056 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Not feasible
Peace. 256777529692. Kampala Downtown:Nabugabo Road.0.314536,32.574488 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO51247584 |  | Completed |  | Office Internet rejected |  | Not reachable | Not picking calls, standard sms was shared
BRENDA ATUHEIRE. 256770339278. Kisaasi:Kyanja Ring Road.0.383757,32.593577 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO33607484 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256772694769. Nsambya:Nsambya Estate Road.0.30089,32.593472 . FTTH_40_M_O | 2023-01-04 | FTTO | MTNFTTO51744653 | 3 | Completed | UGX 1,469,070.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256783869342. Nsambya:Kabega Road.0.2976,32.590401 . FTTH_40_M_O | 2023-01-04 | FTTO | MTNFTTO50080167 | 2 | Completed | UGX 2,495,620.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772432832. Bwebajja:Arkright City.0.353464,32.613416.FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO72740213 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256776291440. Bwebajja:Arkright City.0.353464,32.613416.FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO57158533 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256783216649. Kisaasi:Kulambiro.0.379161,32.617861 . FTTH_20_M_O | 2023-01-03 | FTTO | MTNFTTO81778468 | 3 | Completed | UGX 1,336,890 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773229296. Nsambya:Nsambya Estate Road.0.300941,32.593395 . FTTH_40_M_O | 2023-01-03 | FTTO | MTNFTTO25311312 | 3 | Completed | UGX 4,659,398.50 | Office Internet approved | Office Internet (APP.) Pending
null null. 256762436320. Kisaasi:Komamboga Road.0.418082,32.57174 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO81758572 |  | Completed |  | Office Internet rejected |  | Not reachable | CLIENT NOT PICK UP CALLS FOR 2AND STANDARD SMS WAS SENT
null null. 256781414239. Rubaga:Mutundwe Road.0.279898,32.546996 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO17168581 | 0 | Completed | UGX 7,537,048.20 | Office Internet approved | Office Internet (APP.) Pending |  | Consolidated with null null. 256788155648. Rubaga:Mutundwe Road.0.276184,32.546289 . FTTH_20_M 30-Dec-22 FTTH (APP.) MTNFTTH75128764 Completed P1 Viable Location 0 UGX 7,537,048.20 FTTH Approved FTTH (APP.) Pending
null null. 256762429152. Bwebajja:Kitende.0.058778,32.473499 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO75636180 | 2 | Completed | UGX 9,124,566.20 | Office Internet approved | Office Internet (APP.) Paid |  | To be consolidated
null null. 256762486291. Bwebajja:Kitende.0.404778,32.543815 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO60246283 | 2 | Completed |  | Office Internet approved | Office Internet (APP.) Paid |  | Survey scheduled for monday 16.1.2023
IVAN SSERUBIRI. 256787686486. Entebbe:Station Road.0.091931,32.499613 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO10685232 | 2 | Completed |  | Office Internet rejected |  | Not reachable | Doesnt pick
null null. 256773805845. Entebbe:Bugonga Road.0.053028,32.469192 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO28166804 | 2 | Completed | UGX 2,811,716.10 | Office Internet approved | Office Internet (APP.) Paid |  | survey re-scheduled for Monday (09/01/2023
null null. 256770944590. Ggaba:Ggaba Road.0.274553,32.616103 . FTTH_40_M_O | 2023-01-04 | FTTO | MTNFTTO54725762 | 2 | Completed | UGX 2,025,879.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256786994911. Namuwongo:Namuwongo Road.0.301003,32.609552 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO63547238 |  | Completed |  | Office Internet rejected |  | Not interested | just making phone busy-sms sent
null null. 256777302395. Ntinda (Kiwatule - Naalya):.0.371424,32.619916 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO47661562 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | NOT FEASIBLE- 560M (0.3714287 , 32.61992533)
null null. 256760055140. Bugolobi:Port Bell road.0.189375,32.529319 . FTTH_40_M_O | 2023-01-04 | FTTO | MTNFTTO70042242 | 2 | Completed | UGX 3,491,332.2 | Office Internet approved | Office Internet (APP.) Paid
null null. 256783012719. Makerere:Bombo Road.0.38816,32.534269 . FTTH_20_M_O | 2023-01-04 | FTTO | MTNFTTO47383152 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Out of GPON Coverage - Kagoma
null null. 256762175631. Jinja:Jinja Catholic.0.590751,33.449039 . FTTH_40_M_O | 2023-01-04 | FTTO | MTNFTTO58783002 |  | Completed |  | Office Internet rejected |  | Not interested | was testing service
null null. 256776905013. Rubaga:Kabusu Road.0.304454,32.558098 . FTTH_40_M_O | 2023-01-05 | FTTO | MTNFTTO14704858 | 3 | Completed | UGX 4,327,807.10 | Office Internet approved | Office Internet (APP.) Pending |  | client re-scheduled survey for tusday(10/01/2023)
null null. 256775964372. Najjanankumbi:Kampala Entebbe Road.0.284155,32.572033 . FTTH_20_M_O | 2023-01-05 | FTTO | MTNFTTO12776601 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-400m
null null. 256770800322. Jinja:Radio Road.0.435306,33.212561 . FTTH_20_M_O | 2023-01-05 | FTTO | MTNFTTO37584626 | 2 | Completed | UGX 1,872,697.6 | Office Internet approved | Office Internet (APP.) Pending
null null. 256782604522. Entebbe:Church Road.0.100781,32.508746 . FTTH_20_M_O | 2023-01-05 | FTTO | MTNFTTO78760388 | 2 | Completed | UGX 5,412,482.10 | Office Internet rejected |  | Not feasible, EBU to pitch SME | Addittional neighbours needed
null null. 256779703720. Entebbe:Hill Lane.0.266709,32.615463 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO36283144 |  | Completed | UGX 4,988,321.60 | Office Internet approved | Office Internet (APP.) Paid
Margaretha Wilhelmina Geluka. 256787745145. Makindye:Kizungu Road.0.340207,32.588781 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO40145407 | 4 | Completed | UGX 4,251,680.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256787676280. Muyenga:Tank Hill Road.0.297135,32.608681 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO55206022 | 2 | Completed | UGX 2,389,592.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773145145. Makerere:Sir Apollo Kaggwa Road.0.370672,32.555834 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO01618038 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
Drake Francis Lubega. 256772429520. Kampala Downtown:Kikuubo Street.0.316874,32.57339 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO47160143 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | No Fiber Access
null null. 256785538779. Ntinda (Kyambogo - Min Village):Martyrs Road.0.342538,32.618264 . FTTH_40_M_O | 2023-01-12 | FTTO | MTNFTTO72033876 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256778525503. Kampala Downtown:Kyaggwe Road.0.313145,32.609905 . FTTH_40_M_O | 2023-01-10 | FTTO | MTNFTTO64273583 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
null null. 256776455072. Kampala Upper CBD:Kampala Road.0.31626,32.575555 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO77661103 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | No Fiber Access Nyumba Kubwa building
null null. 256775833909. Fort Portal:Fort Portal Mpondwe Road.0.652979,30.27168 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO80180604 | 2 | Completed | UGX 3,156,177.10 | Office Internet approved | Office Internet (APP.) Paid |  | survey rescheduled for 16.01.2023
null null. 256772576598. Bwebajja:Arkright City.0.12444,32.530733 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO23450272 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
null null. 256789491350. Kisaasi:.0.337197,32.561824 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO36007017 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE 1KM (0.39491862 , 32.58683726)
null null. 256771090439. Ggaba:Ggaba ByPass Road.0.264685,32.63085 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO41768666 | 1 | Completed | UGX 2,889,032.10 | Office Internet approved | Office Internet (APP.) Paid
Brandon. 256782129261. Ntinda (Kyambogo - Min Village):Kyambogo Road.0.342282,32.629379 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO63355241 | 2 | Completed | UGX 4,217,391.0 | Office Internet approved | Office Internet (APP.) Paid |  | Survey ongoing
null null. 256772575884. Rubaga:Lubowa Terrace Road.0.287964,32.563066 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO26785186 | 2 | Completed | UGX 2,048,323.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256788945597. Namuwongo:Muwayire Road.3.032652,30.923984 . FTTH_20_M_O | 2023-01-10 | FTTO | MTNFTTO62422335 |  | Completed | UGX 2,114,920.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256771135914. Rubaga:Lungujja.0.306122,32.5476 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO08513551 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256787021216. Nakasero Hill:Lumumba Avenue.0.324977,32.576469 . FTTH_40_M_O | 2023-01-11 | FTTO | MTNFTTO72003143 | 2 | Completed | UGX 2,167,637 | Office Internet approved | Office Internet (APP.) Paid
null null. 256779044605. Rubaga:Kabusu Road.0.298462,32.536002 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO58608580 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-400m 5poles
SSesanga Ronald. 256779513909. Ggaba:Ggaba Road.0.288248,32.606751 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO74053867 | 2 | Completed | UGX 4,706,822.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256782541119. Bugolobi:Port Bell road.0.318535,32.627569 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO70114023 | 2 | Completed | UGX 3,149,483.0 | Office Internet approved | Office Internet (APP.) Paid
null null. 256781816622. Ntinda (Kyambogo - Min Village):Martyrs Road.0.350048,32.621917 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO27160352 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible. A lot of right of way
null null. 256777084306. Kigo:Lubugumu.0.25555,32.573507 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO12740335 |  | Completed |  | Office Internet rejected |  | Not reachable | Number currently off.
null null. 256789872394. Kira:Mamerito Mugerwa Road.0.320404,32.586636 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO53108337 |  | Completed |  | Office Internet rejected |  | Not reachable | CLIENTS NOT PICKING CALLS FOR 3DAYS STANDARD SMS SENT
null null. 256774661505. Ntinda (Kyambogo - Min Village):Martyrs Road.0.351928,32.619791 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO31282151 | 0 | Completed | 8041257.1 | Office Internet approved | Office Internet (APP.) Paid | Not reachable | CLIENT NOT REACHABALE STANDARD SMS SENT
null null. 256772502949. Ntinda (Kyambogo - Min Village):Martyrs Road.0.351896,32.619769 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO85556705 | 0 | Completed |  | Office Internet approved | Office Internet (APP.) Paid | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE 353M (0.35191669 , 32.61975702)
null null. 256778891442. Muyenga:Kansanga Kiwafu Road.0.287562,32.620918 . FTTH_40_M_O | 2023-01-11 | FTTO | MTNFTTO67556307 | 3 | Completed | UGX 2,114,920.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256784340770. Nsambya:Nsambya Estate Road.0.299329,32.591531 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO66455111 | 2 | Completed | UGX 3,482,660.60 | Office Internet approved | Office Internet (APP.) Paid
Aaron Seppuuya Mpagi. 256773056556. Makindye:Luwafu Road.0.30236,32.583238 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO72516050 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
null null. 256788076016. Kisaasi:Kulambiro.0.368283,32.604678 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO48876555 | 2 | Completed |  | Office Internet rejected |  | Not interested | CLIENT IS NOT READY FOR THE SERVICE
null null. 256783012719. Bugolobi:Luthuli Road.0.321364,32.612439 . FTTH_40_M_O | 2023-01-11 | FTTO | MTNFTTO47383152 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid |  | Survey partially done, to be completed when the building manager is available
null null. 256789728926. Entebbe:Nakiwogo Road.0.088973,32.49926 . FTTH_40_M_O | 2023-01-11 | FTTO | MTNFTTO65751287 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
null null. 256775992403. Najjanankumbi:Kampala Entebbe Road.0.370595,32.514113 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO34617675 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-9poles, 1000m
null null. 256783803956. Entebbe:Church Road.0.097286,32.505394 . FTTH_40_M_O | 2023-01-11 | FTTO | MTNFTTO62203754 | 3 | Completed | UGX 2,847,412.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256394003967. Bwebajja:Arkright City.0.171733,32.546202 . FTTH_40_M_O | 2023-01-12 | FTTO | MTNFTTO01116403 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Client wants the services at Nsambya, Survey re scheduled for Thursday 19.1.2023
SUMANT KUMAR KUMAR. 256775543208. Ntinda Bukoto:Old Kira Road.0.348805,32.59889 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO81554683 | 2 | Completed | UGX 2,045,966.5 | Office Internet approved | Office Internet (APP.) Paid
null null. 256788704517. Kampala Upper CBD:Kampala Road.0.310639,32.582779 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO12561307 | 2 | Completed | UGX 2,354,876.00 | Office Internet approved | Office Internet (APP.) Pending
null null. 256772468653. Nakasero Hill:Buganda Road.0.317475,32.577042 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO61508487 | 2 | Completed | UGX 2,265,989 | Office Internet approved | Office Internet (APP.) Paid
null null. 256762778221. Ntinda (Kiwatule - Naalya):Majwala Road.0.366952,32.614851 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO00305133 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE [O.3641039 32.6130069]
Tusiime Eseza. 256770643625. Nakasero Hill:Buganda Road.0.317548,32.576783 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO67322645 | 2 | Completed | UGX 2,426,134 | Office Internet approved | Office Internet (APP.) Paid
null null. 256774231254. Kampala Upper CBD:Kampala Road.0.331018,32.593107 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO42521362 | 2 | Completed | UGX 2,129,292 | Office Internet approved | Office Internet (APP.) Paid
Ramathan Sitina. 256783778720. Rubaga:Rubaga Road.0.307928,32.563186 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO05661211 | 2 | Completed | UGX 2,048,323.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256787441429. Rubaga:Mengo.0.321932,32.562543 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO25762412 | 2 | Completed | UGX 3,580,272.10 | Office Internet approved | Office Internet (APP.) Paid
KANSARA PRASHANTKUMAR. 256772723045. Bweyogerere:Jinja Road.0.358312,32.658942 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO21132060 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | far from service. His installation requires 3 to 4 consolidations
null null. 256784538185. Ggaba:Kalungu Road.0.279587,32.623863 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO04535387 | 0 | Completed | UGX 2,347,972.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256788114341. Muyenga:Bukasa Road.0.292107,32.605711 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO01177462 | 2 | Completed | UGX 3,854,504.60 | Office Internet approved | Office Internet (APP.) Pending
null null. 256783731574. Ntinda (Kiwatule - Naalya):Naalya Road.0.368414,32.621563 . FTTH_20_M_O | 2023-01-12 | FTTO | MTNFTTO74245542 | 2 | Completed | UGX 3,774,890 | Office Internet approved | Office Internet (APP.) Pending
null null. 256772098079. Luzira:Lake Drive.0.291659,0.291659 . FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO12840180 | 2 | Completed | UGX 10,817,761.2 | Pending review
null null.256782319798. Luzira:Lake Drive. 0.291588,32.659613.FTTH_20_M_O | 2023-01-14 | FTTO | MTNFTTO84553680 | 2 | Completed |  | Pending review
null null. 256788850863. Muyenga:Tank Hill Road.0.295648,32.622383 . FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO68278702 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-5poles, 390m
null null. 256781829601. Makerere:Bombo Road.0.390934,32.57695 . FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO18121180 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | High BOQ client needs 5 poles with 400m cable
null null. 256788433249. Kampala Downtown:Kyaggwe Road.0.263398,32.598598 . FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO01005304 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | To reapply from the correct location
NYAGUANDE JOCK CHUOL. 256775505157. Nsambya:Nsambya Estate Road.0.263143,32.601072 . FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO81085232 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Number currently off.
null null. 256784825791. Najjanankumbi:Kigo Road.0.241905,32.529688 . FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO06513103 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Not feasible, client approximately 3km from the fiber node
SYLVIA ACEN. 256773533115. Kampala Upper CBD:Kampala Road.0.314058,32.588746 . FTTH_40_M_O | 2023-01-14 | FTTO | MTNFTTO60288631 | 0 | Completed | UGX 2,318,422 | Office Internet approved | Office Internet (APP.) Paid
null null. 256782319798. Luzira:Lake Drive.0.291588,32.659613 . FTTH_20_M_O | 2023-01-14 | FTTO | MTNFTTO84553680 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | far from service. Needs a consolidation of 3 clients
null null. 256789484807. Makindye:Lukuli Road.0.353995,32.607849 . FTTH_20_M_O | 2023-01-14 | FTTO | MTNFTTO75532734 | 2 | Completed | UGX 3,357,296.60 | Office Internet approved | Office Internet (APP.) Pending
null null. 256778907842. Entebbe:Church Road.0.199483,32.540986 . FTTH_20_M_O | 2023-01-14 | FTTO | MTNFTTO48124175 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | she is not around she will call us on 19/01/2023
null null. 256787527936. Bugolobi:Port Bell road.0.327587,32.612277 . FTTH_40_M_O | 2023-01-14 | FTTO | MTNFTTO48350857 | 1 | Completed | UGX 2,460,692 | Office Internet approved | Office Internet (APP.) Paid
IVAN SSERUBIRI. 256787686486. Entebbe:Station Road.0.093655,32.500674 . FTTH_20_M | 2023-01-14 | FTTO | MTNFTTO10685232 |  | Completed |  | Office Internet rejected |  | Not reachable | Doesnt pick up
null null. 256782140211. Kampala Upper CBD:Kampala Road.0.348326,32.55442 . FTTH_20_M_O | 2023-01-15 | FTTO | MTNFTTO75120225 |  | Completed |  | Office Internet rejected | Office Internet rejected | Not feasible, EBU to pitch SME | Not feasible, EBU to pitch SME
SULAIMAN AGABA. 256777069580. Ntinda Bukoto:Semawata Road.0.346906,32.615575 . FTTH_20_M_O | 2023-01-16 | FTTO | MTNFTTO71584144 | 0 | Completed | UGX 2,041,152.6 | Office Internet approved | Office Internet (APP.) Paid
null null.256775380000.Kololo:KAR Road.0.324178,32.598766.FTTH_20_M_O | 2023-01-13 | FTTO | MTNFTTO67375568 |  | Completed | UGX 1,729,360 | Office Internet approved | Office Internet (APP.) Paid
DERRICK ASEDRI. 256784114200.Luzira:Port Bell road.0.312327,32.636447.FTTH_20_M_O | 2023-01-14 | FTTO | MTNFTTO54175525 | 0 | Completed | UGX 3,003,053.4 | Office Internet approved | Office Internet (APP.) Paid
null null. 256770687648. Masaka:Broadway Road.0.250861,32.479805 . FTTH_40_M_O | 2023-01-16 | FTTO | MTNFTTO23318070 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | the client is in BUDDO KISOZI kampala-not our cluster
null null. 256772540528. Makindye:Lukuli Road.0.290429,32.585524 . FTTH_20_M_O | 2023-01-16 | FTTO | MTNFTTO15703036 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256775337752. Ggaba:Ggaba Road.0.295348,32.605454 . FTTH_20_M_O | 2023-01-16 | FTTO | MTNFTTO66133267 | 1 | Completed | UGX 3,750,646 | Office Internet approved | Office Internet (APP.) Paid |  | survey scheduled for tomorrow(18/01/2023
null null. 256782910091. Bweyogerere:Kirinya Bukasa Road.0.332239,32.6756 . FTTH_20_M_O | 2023-01-16 | FTTO | MTNFTTO37007642 | 0 | Completed | UGX 2,260,687.0 | Office Internet approved | Office Internet (APP.) Pending
null null. 256770726476. Makindye:Luwafu Road.0.270587,32.590308 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO76854434 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256779009049. Kampala Downtown:Kampala Road.0.296415,32.575752 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO25471668 |  | Completed |  | Office Internet rejected | Office Internet rejected | Not feasible, EBU to pitch SME | This client’s survey cannot be completed today due to too much congestion around the market place, We have agreed with the client to complete this survey tomorrow morning
null null. 256780132370. Nakasero Hill:Yusuf Lule Road.0.317226,32.593334 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO60335660 | 0 | Completed | UGX 1,747,753 | Office Internet approved | Office Internet (APP.) Pending
null null. 256772544610. Kampala Upper CBD:.0.295369,32.572048 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO43547887 | 2 | Completed | UGX 3,796,775.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256783375364. Entebbe:Hill Lane.0.225029,32.555774 . FTTH_40_M_O | 2023-01-17 | FTTO | MTNFTTO47763203 | 1 | Completed | UGX 2,181,517.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256771428163. Kololo:.0.338164,32.596614 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO17842142 | 0 | Completed | UGX 1,739,518 | Office Internet approved | Office Internet (APP.) Pending
null null. 256778406753. Ggaba:Ggaba Road.0.280948,32.608785 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO41435663 |  | Completed | UGX 5,005,652.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256789500722. Mbarara:Boma Road.-0.607096,30.669088 . FTTH_20_M_O | 2023-01-17 | FTTO | MTNFTTO60527531 | 0 | Completed | UGX 10,271,304.20 | Office Internet approved | Office Internet (APP.) Paid
null null. 256776472799. Mbarara:Kabale - Mbarara Road.-0.603693,30.66286 . FTTH_20_M_O | 2023-01-18 | FTTO | MTNFTTO58204152 | 0 | Completed |  | Office Internet approved | Office Internet (APP.) Paid
null null. 256784693787. Najjanankumbi:Kampala Entebbe Road.0.285279,32.569266 . FTTH_20_M_O | 2023-01-18 | FTTO | MTNFTTO13745626 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
SAHIL BARKATALI KOTADIA. 256788727544. Ntinda Bukoto:Kira Road.0.342971,32.591531 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO55585325 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256782863490. Mbale:Masaba Road.1.07712,34.177356 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO87624815 | 2 | Completed | UGX 4,393,972 | Office Internet approved | Office Internet (APP.) Paid
ALFRED MUBANGIZI. 256785135285. Bugolobi:Mbuya Road.0.313577,32.627922 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO53522646 | 3 | Completed | UGX 4,837,195 | Office Internet approved | Office Internet (APP.) Pending | Not feasible, EBU to pitch SME | Not feasible, EBU to pitch SME
null null. 256778145842. Muyenga:Muyenga Road.0.299162,32.602148 . FTTH_20_M_O | 2023-01-18 | FTTO | MTNFTTO18647220 | 0 | Completed | UGX 2,644,868.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256775234342. Kisaasi:Kulambiro.0.323084,32.47454 . FTTH_20_M_O | 2023-01-18 | FTTO | MTNFTTO56126358 | 0 | Completed | UGX 1,909,380 | Office Internet approved | Office Internet (APP.) Paid
null null. 256778078045.Buwate:Seeta Kasangati.0.330231,32.619174.FTTH_20_M_O | 2023-01-16 | FTTO | MTNFTTO88352566 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256785257555. Ntinda (Kyambogo - Min Village):Kyambogo Road.0.353824,32.616053 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO85441388 | 0 | Completed | UGX 2,064,773 | Office Internet approved | Office Internet (APP.) Paid
null null. 256787472442. Lira:Dokolo Road.2.241063,32.894451 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO48025386 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Not feasible, client is about 1.2km from fiber.
null null. 256774699135. Rubaga:Kabusu Road.0.301788,32.556475 . FTTH_40_M_O | 2023-01-19 | FTTO | MTNFTTO66658670 | 2 | Completed | UGX 2,114,920 | Office Internet approved | Office Internet (APP.) Paid
null null. 256774514268. Kampala Downtown:Kampala Road.0.267478,32.603605 . FTTH_40_M_O | 2023-01-19 | FTTO | MTNFTTO58215014 |  | Completed |  | Office Internet rejected | Not feasible, EBU to pitch SME | Not feasible, EBU to pitch SME
RONALD NYAKAHUMA. 256772722190. Rubaga:Mutundwe Road.0.294483,32.552784 . FTTH_40_M_O | 2023-01-19 | FTTO | MTNFTTO48333343 | 2 | Completed | UGX 3,982,172 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772423085. Kololo:Lugogo Bypass.0.327891,32.609569 . FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO12132081 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256779044605. Rubaga:Kabusu Road.0.30355,32.573636 . FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO58608580 | 0 | Completed | N/A | Office Internet rejected |  | Not feasible, EBU to pitch SME | not feasible-400m 5poles
null null. 256784847773. Seeta:Bukerere Road.0.37974,32.708415 . FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO00480264 | 2 | Completed | UGX 15,174,467 | Office Internet approved | Office Internet (APP.) Paid |  | Consolidated with null null. 256779079975. Seeta:Bukerere Road.0.376981,32.70949 . FTTH_20_M
Kemigabo Teddy. 256781585769. Seeta:Bukerere Road.0.394095,32.703068 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO46880485 | 2 | Completed |  | Office Internet approved | Office Internet (APP.) Paid |  | Consolidated with null null. 256779079975. Seeta:Bukerere Road.0.376981,32.70949 . FTTH_20_M
null null. 256772612113. Muyenga:Kansanga Kiwafu Road.0.2912,32.615466 . FTTH_20_M_O | 2023-01-20 | FTTO | MTNFTTO18441358 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | >280m
null null. 256787966598. Ntinda Bukoto:Bukoti Ntunda Road.0.353653,32.603956 . FTTH_20_M_O | 2023-01-20 | FTTO | MTNFTTO06721141 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | far from service. He needs 8poles to be installed
null null. 256788602150. Lira:Dokolo Road.2.241592,32.89463 . FTTH_40_M_O | 2023-01-20 | FTTO | MTNFTTO15434674 | 0 | Completed | UGX 4,119,158.00 | Office Internet approved | Office Internet (APP.) Pending
null null. 256783570970. Makerere:Sir Apollo Kaggwa Road.0.353988,32.60785 . FTTH_20_M_O | 2023-01-20 | FTTO | MTNFTTO06158827 | 0 | Completed | UGX 2,741,967.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256775888502. Kololo:Tufnell Drive.0.338423,32.584446 . FTTH_20_M_O | 2023-01-20 | FTTO | MTNFTTO51142400 | 2 | Completed | UGX 2,557,240.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773040776. Makerere:Bombo Road.0.348119,32.564702 . FTTH_20_M_O | 2023-01-20 | FTTO | MTNFTTO78451547 | 0 | Completed | UGX 2,683,767.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256786774673. Ntinda Bukoto:Kira Road.0.341922,32.595292 . FTTH_40_M_O | 2023-01-20 | FTTO | MTNFTTO66235020 | 0 | Completed | UGX 2,734,546.20 | Office Internet approved | Office Internet (APP.) Pending
TSIGEREDA TESFAY FISEHATSION. 256773186805. Muyenga:Tank Hill Road.0.288141,32.610687 . FTTH_20_M_O | 2023-01-20 | FTTO | MTNFTTO63758767 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
ATC Uganda - JUANITA KARAMAGI. 256787370808. Ggaba:Kalungu.0.272501,32.616971 . FTTH_20 | 2023-01-21 | FTTO | MTNFTTP37673388 | 0 | Completed | UGX 1,387,672.30 | Office Internet approved | Office Internet (APP.) Paid
null null. 256788083456. Ntinda Bukoto:Semawata Road.0.349234,32.616722 . FTTH_20_M_O | 2023-01-21 | FTTO | MTNFTTO82610608 | 2 | Completed | UGX 2,799,195.8 | Office Internet approved | Office Internet (APP.) Pending
null null. 256776574064. Soroti:Soroti - Moroto Road.1.721037,33.615654 . FTTH_20_M_O | 2023-01-21 | FTTO | MTNFTTO11234458 | 3 | Completed | UGX 5,035,539.80 | Office Internet approved | Office Internet (APP.) Paid
null null. 256787889109. Soroti:Market Lane.1.714303,33.62055 . FTTH_20_M_O | 2023-01-22 | FTTO | MTNFTTO01351086 |  | Completed | UGX 6,981,584.60 | Office Internet rejected |  | Not feasible, EBU to pitch SME | Addittional neighbour needed
null null. 256786214223. Gulu:Gulu Senior Quarters.3.264873,31.953177 . FTTH_40_M_O | 2023-01-23 | FTTO | MTNFTTO66038565 |  | Completed |  | Office Internet rejected |  | Not interested | Client relocated to Juba and will not need services for now.
null null. 256775572915. Luzira:Port Bell road.0.296646,32.655033 . FTTH_40_M_O | 2023-01-23 | FTTO | MTNFTTO00020736 | 0 | Completed | UGX 4,687,855.0 | Office Internet approved | Office Internet (APP.) Paid
null null. 256762678662. Rubaga:Musajja Alumbwa Road.0.353989,32.607846 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO78666274 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256762578291. Kololo:Acacia Avenue.0.338325,32.59669 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO24814088 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256783819004. Rubaga:Lungujja.0.310527,32.527729 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO32585382 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Addittional neighbour needed
null null. 256773145145. Makerere:Sir Apollo Kaggwa Road.0.371765,32.552612 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO01618038 | 0 | Completed | UGX 3,728,549.60 | Office Internet approved | Office Internet (APP.) Pending
null null. 256772616260. Bwebajja:Bwebajja Entebbe Road.0.186155,32.532854 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO17228246 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | far from service. He needs 8poles to be installed
null null. 256780257568. Kampala Upper CBD:Kampala Road.0.328572,32.573974 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO00318565 | 0 | Completed | UGX 1,320,699.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256779082166. Nakasero Hill:Mackinnon Road.0.321513,32.585279 . FTTH_40_M_O | 2023-01-23 | FTTO | MTNFTTO01686470 | 0 | Completed | UGX 1,167,289.60 | Office Internet approved | Office Internet (APP.) Paid
IBRAHIM MOHAMED FARAH. 256776501681. Kololo:Mawanda Road.0.34028,32.573756 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO14104416 | 0 | Completed | UGX 1,321,349.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772535508. Ntinda Bukoto:Ntinda Road.0.343632,32.615737 . FTTH_40_M_O | 2023-01-23 | FTTO | MTNFTTO08200106 | 0 | Completed | UGX 2,403,747.0 | Office Internet approved | Office Internet (APP.) Pending
null null. 256779044605. Rubaga:Kabusu Road.0.298427,32.535995 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO58608580 |  | Completed | UGX 5,706,980.60 | Office Internet rejected |  | Not feasible, EBU to pitch SME | Addittional neighbour needed
null null. 256773097543. Rubaga:Lungujja Makamba Road.0.278865,32.480513 . FTTH_40_M_O | 2023-01-23 | FTTO | MTNFTTO00864573 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Not feasible due to r.o.w and severely damaged underground route.
null null. 256772473282. Tororo:Malaba Lane.0.353988,32.607847 . FTTH_40_M_O | 2023-01-24 | FTTO | MTNFTTO34087018 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
null null. 256778272965. Seeta:Seeta Town.51.218908,-0.145291 . FTTH_20_M_O | 2023-01-24 | FTTO | MTNFTTO60201307 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | client a kilometer far from service
null null. 256781088363. Bugolobi:Luthuli Avenue.0.353988,32.607839 . FTTH_20_M_O | 2023-01-24 | FTTO | MTNFTTO24556322 | 2 | Completed | UGX 1,722,344.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256762917689. Makindye:Lukuli Road.0.257653,32.61776 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO01775713 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256786993999. Namuwongo:Namuwongo Road.0.306027,32.612582 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO31776022 | 0 | Completed | 3,128,656.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256785132572. Arua:Arua Hill.0.354942,32.61584 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO20236554 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | CLIENT IS IN KAMPALA AND THE CONTACT PERSON IS ALSO NOT AROUND AND WILL BE BACK ON SUNDAY
REHEMA WANYANA. 256787263042. Buwate:Buwate Road.0.500815,32.614822 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO48318728 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE 1KM
null null. 256777396809. Kira:Namugongo Road.0.386444,32.643817 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO10651260 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | CLIENT NOT REACHABALE STANDARD SMS SENT
null null. 256775888785. Buwate:Seeta Kasangati.0.328652,32.619949 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO28135044 |  | Completed | 18134278 | Office Internet approved | Office Internet (APP.) Paid |  | Consolidated as; null null. 256776610690. Buwate:Seeta Kasangati.0.415646,32.614145 . FTTH_40_M_O null null. 256784964814. Buwate:Seeta Kasangati.0.417627,32.615911 . FTTH_20_M null null. 256778078045. Buwate:Seeta Kasangati.0.414345,32.626862 . FTTH_20_M null null. 256775888785. Buwate:Seeta Kasangati.0.328652,32.619949 . FTTH_20_M_O
null null. 256781056122. Muyenga:Kansanga Kiwafu Road.0.280184,32.614145 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO88185027 |  | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256776890891. Luzira:Port Bell road.0.306803,32.633325 . FTTH_40_M_O | 2023-01-25 | FTTO | MTNFTTO08481502 | 0 | Completed | UGX 4,847,702.8 | Office Internet approved | Office Internet (APP.) Paid
null null,256780319933 Kololo:Lugogo Bypass 0.322074,32.608492 FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO64750754 |  | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null 256788390274 Nsambya:Gogonya Road 0.328373,32.574669 FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO06822045 |  | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256771450113. Bweyogerere:Kirinya Bukasa Road.0.330811,32.663888 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO66630260 | 2 | Completed | UGX 2,135,391.0 | Office Internet approved | Office Internet (APP.) Pending
AMUZA DONGO. 256788346788. Ntinda (Kiwatule - Naalya):Clovis Road.0.353987,32.607847 . FTTH_20_M_O | 2023-01-26 | FTTO | MTNFTTO48887504 | 2 | Completed | UGX 2,214,590 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773438364. Ntinda (Kiwatule - Naalya):Naalya Namugongo Road.0.360668,32.572801 . FTTH_20_M_O | 2023-01-26 | FTTO | MTNFTTO26714754 |  | Completed | UGX 9,187,937 | Office Internet approved | Office Internet (APP.) Paid | EBU to follow up, client to communicate | CLIENT NOT REACHABALE STANDARD SMS SENT
null null. 256760969380. Ntinda (Kiwatule - Naalya):Naalya Namugongo Road.0.400042,32.665774 . FTTH_20_M_O | 2023-01-23 | FTTO | MTNFTTO86672360 |  | Completed |  | Office Internet approved | Office Internet (APP.) Paid
FERDINAND TUKEI. 256781181500. Najjanankumbi:Kampala Entebbe Road.0.264078,32.566412 . FTTH_40_M_O | 2023-01-27 | FTTO | MTNFTTO16533100 |  | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256760209168. Seeta:Seeta Town.25.270996,55.302875 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO41742782 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Client not answering calls. A message was sent and to be tried again
null null. 256760756728. Fort Portal:Fort Portal Mpondwe Road.1.431227,31.34893 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO65646186 |  | On Hold
null null. 256787476867. Bweyogerere:Kabaka Road.0.353935,32.607803 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO61214344 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Phone not reacheable. To be tried again
null null. 256786301521. Ntinda (Kyambogo - Min Village):Charles Lwanga Road.0.35107,32.614498 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO11551407 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256783564019. Ntinda Bukoto:Bukoti Ntunda Road.0.343526,32.61568 . FTTH_40_M_O | 2023-01-27 | FTTO | MTNFTTO73723215 | 0 | Completed | UGX 2,808,747.0 | Office Internet approved | Office Internet (APP.) Paid
null null. 256777864915. Gulu:Gulu CBD.2.763301,32.299987 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO35573205 | 7 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Paid
null null. 256780476925. Bweyogerere:Jinja Road.0.350172,32.654769 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO75451540 | 2 | Completed | UGX 2,437,224.60 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256772541748. Kampala Upper CBD:Kampala Road.0.353931,32.60779 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO25330165 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Customer not feasible needs service in Kavule
null null. 256770899944. Luzira:Port Bell road.0.342442,32.633455 . FTTH_20_M_O | 2023-01-27 | FTTO | MTNFTTO02636201 |  | Completed |  | Office Internet rejected |  | Not interested | Not interested
ATC Uganda Ltd. 256774483950. Bulabira Road.0.379306,32.622278 . FTTH_20 | 2023-01-27 | FTTO | MTNFTTP18000742 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256777898050. Ntinda (Kyambogo - Min Village):Ntinda Avenue.0.352692,32.614486 . FTTH_40_M_O | 2023-01-28 | FTTO | MTNFTTO73431828 | 0 | Completed | UGX 2,796,368.6 | Office Internet approved | Office Internet (APP.) Paid
Kabuga Paul. 256787387245. Kira:Mbogo Road.0.394894,32.642404 . FTTH_40_M_O | 2023-01-28 | FTTO | MTNFTTO15081378 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE 563m
null null. 256785437600. Rubaga:Nateete.0.357294,32.567453 . FTTH_20_M_O | 2023-01-28 | FTTO | MTNFTTO78235627 | 4 | Completed | UGX 1,895,783.80 | Office Internet approved | Office Internet (APP.) Pending
null null. 256775193838. Najjanankumbi:Kampala Entebbe Road.0.353994,32.607845 . FTTH_40_M_O | 2023-01-28 | FTTO | MTNFTTO38587217 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256773840603. Buwate:Kasangati.0.353987,32.607848 . FTTH_20_M_O | 2023-01-28 | FTTO | MTNFTTO47737457 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT IS IN AN AREA WHERE THERE IS NO FIBER INERTNET SO THE CLIENT NOT FEASIBLE
null null. 256392558204. Kololo:KAR Road.0.324196,32.598788 . FTTH_40_M_O | 2023-01-28 | FTTO | MTNFTTO53574020 | 1 | Completed | UGX 1,827,908.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256762054222. Kololo:Kira Road.0.343165,32.633212 . FTTH_40_M_O | 2023-01-28 | FTTO | MTNFTTO83425266 | 1 | Completed | UGX 2,760,508.00 | Office Internet approved | Office Internet (APP.) Pending
null null. 256773411542. Makindye:Lukuli Road.0.27029,32.611318 . FTTH_20_M_O | 2023-01-28 | FTTO | MTNFTTO28188128 |  | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256777680580 Ntinda (Kyambogo - Min Village):Martyrs Way.0.355209, 32.61611.FTTH_40_M_O | 2023-01-30 | FTTO | MTNFTTO87543000 | 0 | Completed | UGX 3,344,724.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256771939043. Rubaga:Mengo.0.353992,32.607849 . FTTH_40_M_O | 2023-01-30 | FTTO | MTNFTTO07456208 | 2 | Completed | UGX 4,495,128.60 | Office Internet approved | Office Internet (APP.) Paid
null null. 256787421472. Entebbe:Church Road.0.35393,32.607799 . FTTH_20_M_O | 2023-01-30 | FTTO | MTNFTTO81601378 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Not feasible, client is about 600m from fiber
null null. 256774510277. Makerere:Gaddafi Road.0.353951,32.607809 . FTTH_20_M_O | 2023-01-30 | FTTO | MTNFTTO75821078 |  | Completed |  | Office Internet rejected |  | Not reachable | Customers number not available
null null. 256776193822. Seeta:Seeta Town.0.35392,32.607867 . FTTH_20_M_O | 2023-01-30 | FTTO | MTNFTTO84618063 |  | Completed |  | Office Internet rejected |  | Not reachable | CLIENT NOT REACHABALE STANDARD SMS SENT
Mark Philip Draper. 256777072261. Ntinda Bukoto:Kira Road.0.340235,32.588791 . FTTH_40_M_O | 2023-01-30 | FTTO | MTNFTTO41611583 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256786917512. Kisaasi:Bahai Road.32.61611,32.598017 . FTTH_40_M_O | 2023-01-30 | FTTO | MTNFTTO11054685 | 2 | Completed | UGX 4,174,622 | Office Internet approved | Office Internet (APP.) Paid
null null. 256761293973. Ntinda Bukoto:Naguru Drive.0.343178,32.600637 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO60127544 | 0 | Completed | UGX 4,472,203.1 | Office Internet approved | Office Internet (APP.) Pending |  | Same as MTNFTTO36816026
null null. 256778099176. Ntinda Bukoto:Bukoto Kisaasi Road.0.355384,32.594488 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO10767561 | 0 | Completed | UGX 5,584,721 | Office Internet approved | Office Internet (APP.) Paid
Akullo Judith. 256777108453. Ntinda Bukoto:Bukoto Kisaasi Road.0.355366,32.594517 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO10424742 | 0 | Completed |  | Office Internet approved | Office Internet (APP.) Paid
null null. 256773563820. Entebbe:Nakiwogo Road.0.056582,32.457909 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO68565563 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256779044605. Rubaga:Kabusu Road.0.298484,32.536061 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO58608580 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256788602141. Kisaasi:Kyanja Ring Road.0.352973,32.614849 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO35481401 |  | Completed |  | Office Internet rejected |  | Not reachable | CLIENTS PHONE NOT REACHABLE FOR TWO DAYS SMS SENT
null null. 256771595270. Ntinda Bukoto:Semawata Road.0.351875,32.613882 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO15266141 | 0 | Completed | UGX 1,901,680 | Office Internet approved | Office Internet (APP.) Pending
Kaitale Dennis. 256779919850. Ntinda (Kiwatule - Naalya):Majwala Road.0.361695,32.620729 . FTTH_40_M_O | 2023-01-31 | FTTO | MTNFTTO78114604 | 0 | Completed | UGX 1,781,282 | Office Internet approved | Office Internet (APP.) Paid
null null. 256774641694. Kampala Upper CBD:Kampala Road.0.353929,32.607801 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO76861873 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Wrong location
HOSEA LUWHANO. 256779639590. Kisaasi:Bahai Road.0.376551,32.596737 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO06217523 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256788193601. Najjanankumbi:Kampala Entebbe Road.0.227407,32.549118 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO82802477 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256789800700. Ntinda (Kyambogo - Min Village):Charles Lwanga Road.0.349314,32.619444 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO37630848 | 0 | Completed | 4521270 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772896954. Kigo:Kigo Road.0.236272,32.564671 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO38062672 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256761323231. Rubaga:Kabusu Road.0.308042,32.570322 . FTTH_40_M_O | 2023-01-31 | FTTO | MTNFTTO35816545 | 3 | Completed | UGX 4,495,128.60 | Office Internet approved | Office Internet (APP.) Pending
null null. 256783357571. Ntinda Bukoto:Kira Road.0.341986,0.341986 . FTTH_40_M_O | 2023-01-31 | FTTO | MTNFTTO44527421 | 3 | Completed | UGX 5,209,052 | Office Internet approved | Office Internet (APP.) Paid
null null,256773012711,Bwebajja:Arkright City 0.157046,32.529971 FTTH_40_M | 2023-01-31 | FTTO | MTNFTTH03148077 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
BADRU MUSISI. 256771135914. Rubaga:Lungujja.0.306122,32.5476 . FTTH_20_M_O | 2023-01-11 | FTTO | MTNFTTO08513551 | 2 | Completed | UGX 2,120,320.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256761617003. Mukono:Mukono Hill.0.584874,32.538158 . FTTH_20_M_O | 2023-01-15 | FTTO | MTNFTTO66648066 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Wrong location, to reapply
null null. 256761354523. Mbale:Bungokho Road.1.142066,34.260393 . FTTH_20_M_O | 2023-01-18 | FTTO | MTNFTTO37744877 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Buwalasi
null null. 256778677672. Rubaga:Wakaliga Road.0.304038,32.546226 . FTTH_20_M_O | 2023-01-18 | FTTO | MTNFTTO28338603 | 2 | Completed | UGX 2,117,620.10 | Office Internet approved | Office Internet (APP.) Paid
null null. 256787758851. Lira:Dokolo Road.2.241561,32.894692 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO41411305 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256785172676. Ntinda Bukoto:Bukoti Ntunda Road.0.363747,32.609552 . FTTH_40_M_O | 2023-01-18 | FTTO | MTNFTTO34842010 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Far from cable
SHALLON AINEMUKAMA. 256789290911. Bugolobi:Spring Road.0.319477,32.614403 . FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO13445253 | 2 | Completed | 4,986,490.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772395949. Rubaga:Kabusu Road.0.296977,32.553713 . FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO71286305 | 2 | Completed | UGX 2,275,713.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256788768106. Najjanankumbi:Kampala Entebbe Road.0.286989,32.569797 . FTTH_20_M_O | 2023-01-19 | FTTO | MTNFTTO56285554 | 2 | Completed | 2099173 | Office Internet approved | Office Internet (APP.) Pending
Kasozi Samuel. 256784034670. Kira:Mamerito Mugerwa Road.0.396219,32.643831 . FTTH_20_M_O | 2023-01-24 | FTTO | MTNFTTO16234272 | 2 | Completed | UGX 12,335,829 | Office Internet approved | Office Internet (APP.) Pending
null null. 256786666349. Kira:Mbogo Road.0.395975,32.644012 . FTTH_20_M_O | 2023-01-25 | FTTO | MTNFTTO23702320 | 2 | Completed | UGX 12,335,829 | Office Internet approved | Office Internet (APP.) Pending
Ogang Samuel. 256783833806. Kira:Mbogo Road.0.396197,32.643625 . FTTH_40_M_O | 2023-01-28 | FTTO | MTNFTTO35055836 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE 563m
null null. 256772425672. Entebbe:Church Road.0.272904,32.565732 . FTTH_20_M_O | 2023-01-26 | FTTO | MTNFTTO46875383 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
Mpanga Edward. 256760603943. Ntinda Bukoto:Ntinda II.0.350527,32.608927 . FTTH_40_M_O | 2023-01-26 | FTTO | MTNFTTO84620114 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256772418778. Kampala Upper CBD:.0.353931,32.607794 . FTTH_40_M_O | 2023-01-27 | FTTO | MTNFTTO30642780 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
Twesigye Dorothy. 256782900523. Kira:Namugongo Road.0.394758,32.666469 . FTTH_20_M_O | 2023-01-30 | FTTO | MTNFTTO71652714 | 2 | Completed | UGX 2,358,778 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256772425049. Kisaasi:Kulambiro.0.376427,32.605312 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO70256664 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256785873695. Bugolobi:Younger Avenue.0.319884,32.617465 . FTTH_20_M_O | 2023-01-31 | FTTO | MTNFTTO48217653 | 2 | Completed | 1707242.2 | Office Internet approved | Office Internet (APP.) Paid
null null. 256788498589. Muyenga:Bukasa Road.0.298796,32.622587 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO00662236 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
ERASMUS KAMUSIIME. 256772525978. Muyenga:Tank Hill Road.0.293286,32.617041 . FTTH_40_M_O | 2023-02-01 | FTTO | MTNFTTO73720641 | 0 | Completed | 3057849 | Office Internet approved | Office Internet (APP.) Paid
null null. 256775843128. Rubaga:Nateete.0.353927,32.60757 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO01644456 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256772563795. Kira:Namugongo Road.0.35392,32.607784 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO34330084 |  | Completed |  | Office Internet rejected |  | EBU to follow up, client to communicate | Wrong location, to reapply
Nuwahereza Christine. 256785468371. Ntinda (Kiwatule - Naalya):Dr LuLwiya Road.0.372034,32.626954 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO22028828 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
Kwiyi Asheihk. 256786360840. Ntinda (Kiwatule - Naalya):Dr LuLwiya Road.0.371878,32.624389 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO53786256 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256770899944. Luzira:Port Bell road.0.341571,32.633221 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO02636201 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256775858551. Makerere:Sir Apollo Kaggwa Road.0.32678,32.565037 . FTTH_20_M_O | 2023-02-01 | FTTO | MTNFTTO46161172 | 2 | Completed | UGX 2,268,208.00 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256761651368. Ntinda (Kyambogo - Min Village):Muwafu Road.0.353993,32.607838 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO32687282 | 2 | Completed | UGX 5,927,140 | Office Internet rejected |  | Not feasible, EBU to pitch SME | High BOQ
null null. 256781827343. Kira:Mbogo Road.0.353842,32.607832 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO27571785 | 2 | Completed | UGX 5,455,762 | Office Internet rejected |  | Not feasible, EBU to pitch SME | High BOQ
null null. 256786450770. Bweyogerere:Kireka Road.0.3469,32.648908 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO23677484 | 2 | Completed | 3183088.2 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256782559025. Najjanankumbi:.0.353984,0.353984 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO86155685 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Wrong coordinates
Abdullahi Muhammed. 256786839268. Rubaga:Musajja Alumbwa Road.0.30461,32.568913 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO33426105 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256780245294. Kisaasi:Kyanja Ring Road.0.353984,32.60785 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO78488168 | 0 | Completed | UGX 4,065,510 | Office Internet approved | Office Internet (APP.) Pending
null null. 256781499133. Makindye:Lukuli Road.0.353985,32.607847 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO26775745 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256760905149. Kisaasi:Kisaasi Kira Road.0.3064,32.644021 . FTTH_40_M_O | 2023-02-02 | FTTO | MTNFTTO08557276 | 0 | Completed | UGX 1,286,080.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256785171304. Ntinda (Kyambogo - Min Village):Martyrs Crescent.0.355016,32.615091 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO02216724 | 0 | Completed | UGX 2,828,481 | Office Internet approved | Office Internet (APP.) Paid
null null. 256761059303. Makerere:.0.320062,32.563457 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO60745042 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256776116611. Ntinda Bukoto:Semawata Road.0.349081,32.615558 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO06325560 | 0 | Completed | UGX 5,889,380 | Office Internet approved | Office Internet (APP.) Pending
null null. 256761197848. Makerere:Gaddafi Road.-0.528567,30.07537 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO68853826 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Coordinates drop in Bwera
null null. 256776153906. Najjanankumbi:Kampala Entebbe Road.0.261929,32.578785 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO50107701 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Nyanama
null null. 256762790073. Bwebajja:Kitende.0.353988,32.607848 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO80010317 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256777819996. Luzira:Port Bell road.0.357261,32.567378 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO28608154 |  | Completed | 1647502.8 | Office Internet approved | Office Internet (APP.) Pending | Not feasible, EBU to pitch SME
null null. 256785016644. Muyenga:Bukasa Road.0.302009,32.611725 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO56047002 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256775963938. Bwebajja:Arkright City.0.326518,32.56463 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO31416207 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256760756728. Fort Portal:Fort Portal Mpondwe Road.1.431227,31.34893 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO65646186 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Hoima
null null. 256781594859. Bugolobi:Port Bell road.0.313928,32.634958 . FTTH_40_M_O | 2023-02-03 | FTTO | MTNFTTO40168523 | 0 | Completed | UGX 2,121,738.9 | Office Internet approved | Office Internet (APP.) Pending
null null. 256778403190. Rubaga:Nateete.0.300625,32.52906 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO72438585 | 0 | Completed | UGX 2,654,215.10 | Office Internet approved | Office Internet (APP.) Pending
null null. 256773144537. Muyenga:Tank Hill Road.0.296635,32.60512 . FTTH_20_M_O | 2023-02-04 | FTTO | MTNFTTO13058146 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256761634048. Rubaga:Mengo.0.304004,32.574885 . FTTH_20_M_O | 2023-02-04 | FTTO | MTNFTTO33648647 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256776819896. Rubaga:Lubiri Ring Road.0.306698,32.565521 . FTTH_20_M_O | 2023-02-04 | FTTO | MTNFTTO07208640 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256784444189. Kigo:Kigo Road.0.353996,32.607838 . FTTH_20_M_O | 2023-02-05 | FTTO | MTNFTTO47065550 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256783432444. Bugolobi:Spring Road.0.35399,32.607847 . FTTH_20_M_O | 2023-02-05 | FTTO | MTNFTTO66038510 | 0 | Completed | UGX 3,578,053.8 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772924106. Ntinda Bukoto:Ntinda Road.0.351944,32.615267 . FTTH_40_M_O | 2023-02-06 | FTTO | MTNFTTO15306743 | 0 | Completed | 2212145.8 | Office Internet approved | Office Internet (APP.) Paid
null null. 256777147337. Rubaga:Stensera Road.0.302882,32.560654 . FTTH_40_M_O | 2023-02-06 | FTTO | MTNFTTO12477282 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256787487441. Ntinda (Kiwatule - Naalya):Majwala Road.0.362468,32.618737 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO52404434 | 0 | Completed | UGX2,760,232 | Office Internet approved | Office Internet (APP.) Pending
null null. 256786135354. Ggaba:Ggaba Road.0.241567,32.619797 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO20731731 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256785171304. Ntinda (Kyambogo - Min Village):.0.35481,32.615363 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO86000251 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256786028278. Rubaga:Stensera Road.0.305785,32.569283 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO33363133 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256772486307. Ntinda Bukoto:Upper Naguru East Road.0.340233,32.609942 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO61107816 | 0 | Completed | UGX 3,090,859.4 | Office Internet approved | Office Internet (APP.) Paid
null null. 256785106928. Entebbe:Church Road.0.252612,32.561843 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO26232027 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256776481202. Kololo:Acacia Avenue.0.341247,32.589745 . FTTH_20_M_O | 2023-02-06 | FTTO | MTNFTTO24487672 | 0 | Completed | 2109408 | Office Internet approved | Office Internet (APP.) Pending
null null. 256775983083. Entebbe:Bugonga Road.0.053692,32.459346 . FTTH_40_M_O | 2023-02-07 | FTTO | MTNFTTO68811030 | 0 | Completed | 3305989.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256762790073. Bwebajja:Kitende.0.353988,32.607848 . FTTH_20_M_O | 2023-02-07 | FTTO | MTNFTTO80010317 | 4 | Completed | UGX 2,211,120.80 | Office Internet approved | Office Internet (APP.) Pending
null null. 256776153906. Najjanankumbi:Kampala Entebbe Road.0.261929,32.578785 . FTTH_20_M_O | 2023-02-07 | FTTO | MTNFTTO50107701 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Client has fiber feasibility.
null null. 256760723435. Jinja:Queen Elizabeth Way.0.439919,33.21851 . FTTH_20_M | 2023-02-02 | FTTO | MTNFTTX66382407 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256781641075. Kololo:Kira Road.0.337351,32.583223 . FTTH_40_M | 2023-02-02 | FTTO | MTNFTTX51106761 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
Kamara Kizito. 256775842589. Ntinda Bukoto:Bukoto Kisaasi Road.0.354112,32.598245 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO47206436 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256774500466. Bugolobi:Port Bell road.0.317659,32.629087 . FTTH_20_M_O | 2023-02-02 | FTTO | MTNFTTO84813366 | 0 | Completed | UGX 3,702,645.8 | Office Internet approved | Office Internet (APP.) Paid
null null. 256782786099. Kololo:Acacia Avenue.0.339505,32.587832 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO81518443 | 0 | Completed | UGX 1,909,708.00 | Office Internet approved | Office Internet (APP.) Paid
null null. 256781035302. Rubaga:Rubaga Road.0.308333,32.569181 . FTTH_20_M_O | 2023-02-03 | FTTO | MTNFTTO46556271 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256761059303. Makerere:.0.320062,32.563457 . FTTH_20_M_O | 2023-02-07 | FTTO | MTNFTTO60745042 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256778050136. Ntinda (Kyambogo - Min Village):Kayodo Road.0.353914,32.607809 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO14355614 | 3 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256772656611. Buwate:Kungu.0.353991,32.607842 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO41815630 |  | Completed | UGX 6,787,956 | Office Internet rejected |  |  | BOQ above DOA
null null. 256788368768. Makerere:Makerere Hill Road.0.357064,32.532956 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO75063261 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256777666921. Rubaga:Rubaga Road.0.305717,32.559233 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO11413856 | 2 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Pending
null null. 256776608862. Kampala Upper CBD:Kampala Road.0.312573,32.585434 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO23260823 | 2 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Paid
null null. 256781649813. Fort Portal:Bwamba Road.0.657755,30.268439 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO18180848 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256786868420. Kololo:Mabua Road.0.373031,32.649567 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO83466443 | 0 | Completed | UGX 2,109,408.00 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256782935105. Entebbe:Church Road.0.092579,32.500026 . FTTH_40_M_O | 2023-02-08 | FTTO | MTNFTTO76172856 | 2 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Paid
null null. 256775674220. Kampala Downtown:Nakivubo Road.0.310007,32.57684 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO25158677 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256771077760. Entebbe:Church Road.0.307329,32.57059 . FTTH_40_M_O | 2023-02-08 | FTTO | MTNFTTO63876135 | 3 | Completed | UGX 1,983,827 | Office Internet Approved | Office Internet (APP.) Pending
null null. 256785185622. Bugolobi:Luthuli Avenue.0.313347,32.62541 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO01075162 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Onhold, Bugolobi flats building mamagement promised to call us after getting in touch with their residence.
null null. 256782750727. Bweyogerere:Kirinya Bukasa Road.0.327529,32.675953 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO28071144 | 2 | Completed | UGX 2,294,651.4 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256788297220. Ggaba:Ggaba Road.0.284654,32.608438 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO50040107 | 2 | Completed | UGX 1,816,649 | Office Internet approved | Office Internet (APP.) Paid
Baylor College of Medicine. 256779530901. Bukasa Muyenga.0,0 . FTTH_40 | 2023-02-09 | FTTO | MTNFTTP06356607 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | Client has no fiber feasibility
null null. 256394002313. Kira:Namugongo Road.0.396319,32.643848 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO52603102 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256763014545. Rubaga:Rubaga Road.0.307611,32.570357 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO45142471 | 0 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Paid
null null. 256779147142. Rubaga:Albert Cook Road.0.312593,32.554774 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO12166501 | 2 | Completed | UGX 2,159,318 | Office Internet Approved | Office Internet (APP.) Paid
null null. 256776286611. Ntinda (Kiwatule - Naalya):Majwala Road.0.329039,32.47781 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO34500343 | 3 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256763033839. Rubaga:Mengo.0.307508,32.570386 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO61271565 | 0 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Paid
null null. 256786405177. Luzira:Port Bell road.0.30412,32.635375 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO84434521 | 2 | Completed | UGX 2,309,961.8 | Office Internet Approved | Office Internet (APP.) Pending
null null. 256772402955. Rubaga:Lubiri Ring Road.32.47781,32.570288 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO61643144 | 0 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Pending
Nabagulanyi Sumaya. 256788241678. Rubaga:Mengo.0.305987,32.557561 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO16067462 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256770815869. Muyenga:Tank Hill Road.0.350122,32.60839 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO35663200 | 0 | Completed | UGX 4,176,341 | Office Internet approved | Office Internet (APP.) Paid
null null. 256763051615. Rubaga:Stensera Road.0.307356,32.570561 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO45163540 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256779354325. Kololo:Acacia Avenue.0.334277,32.586333 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO74024128 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256771907423. Rubaga:Kabusu Road.0.295726,32.553713 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO25204428 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256761424265. Rubaga:Lubiri Ring Road.0.313122,32.566834 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO10133644 | 0 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Pending
null null. 256763049100. Rubaga:Rubaga Road.0.307336,32.570593 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO74867516 | 2 | Completed | 2094822 | Office Internet approved | Office Internet (APP.) Pending
null null. 256763050668. Rubaga:Rubaga Road.0.307336,32.570591 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO72106507 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256782721247. Rubaga:Lubiri Ring Road.0.29857,32.535721 . FTTH_40_M_O | 2023-02-09 | FTTO | MTNFTTO36822140 | 0 | Completed | N/A | Office Internet Approved | Office Internet (APP.) Paid
null null. 256775570306. Kampala Downtown:Wilson Road.0.298509,32.600674 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO77018006 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256774228077. Kololo:Lugogo Bypass.0.326149,32.604008 . FTTH_40_M_O | 2023-02-03 | FTTO | MTNFTTO02428501 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256763020752. Rubaga:Nateete.0.301704,32.528136 . FTTH_40_M_O | 2023-02-08 | FTTO | MTNFTTO35055378 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256763039997. Ntinda Bukoto:Kira Road.0.343117,32.592262 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO71033208 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256788702074. Rubaga:Lungujja.0.306391,32.533615 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO21168235 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256763144244. Rubaga:Lungujja.0.301995,32.54463 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO58435204 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256786867914. Luzira:Port Bell road.0.322716,32.645233 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO16836064 | 2 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256763012154. Nsambya:Nsambya Estate Road.0.296248,32.600592 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO52641445 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256763009448. Rubaga:Nateete.0.298824,32.531669 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO88744267 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending |  | Number unavailable
null null. 256763070851. Rubaga:Stensera Road.0.352625,32.597538 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO63065573 | 2 | Completed | UGX 2,094,822 | Office Internet approved | Office Internet (APP.) Pending
null null. 256786471841. Mbarara:Mbaguta Street.-0.608234,30.662342 . FTTH_20_M_O | 2023-02-08 | FTTO | MTNFTTO44173684 |  | Completed |  | Office Internet rejected |  | Not feasible, EBU to pitch SME | High BOQ
null null. 256776796191. Bweyogerere:Kireka Kamuli.0.346613,32.648586 . FTTH_40_M_O | 2023-02-08 | FTTO | MTNFTTO26725545 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256774679190. Bwebajja:Kitende.0.194049,32.539572 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO80688110 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256760075816. Kampala Upper CBD:Kampala Road.-0.488683,31.65772 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO30840870 |  | Completed |  | Office Internet rejected |  |  | Wrong coordinates
null null. 256781804668. Ntinda (Kiwatule - Naalya):Naalya Road.0.370445,32.625487 . FTTH_20_M_O | 2023-02-09 | FTTO | MTNFTTO58784305 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256772605925. Ntinda Bukoto:Bukoto Kisaasi Road.0.353733,32.599615 . FTTH_20_M | 2023-02-13 | FTTO | MTNFTTH07747104 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256763078881. Kisaasi:Kyanja Ring Road.0.389471,32.605316 . FTTH_20_M_O | 2023-02-12 | FTTO | MTNFTTO83133464 |  | Completed | 7013144 | Office Internet rejected |  | Not feasible, EBU to pitch SME | CLIENT NOT FEASIBLE 392M
null null. 256779327888. Ntinda Bukoto:Bukoto Kisaasi Road.0.35091,32.59742 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO04523027 | 0 | Completed | UGX 1,906,680 | Office Internet approved | Office Internet (APP.) Paid
null null. 256762854834. Nsambya:Nsambya Estate Road.0.299477,32.596658 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO17474784 | 0 | Completed | 2272414 | Office Internet approved | Office Internet (APP.) Paid
null null. 256772602328. Ntinda (Kyambogo - Min Village):Charles Lwanga Road.0.348076,32.618737 . FTTH_40_M_O | 2023-02-13 | FTTO | MTNFTTO63834720 | 0 | Completed | UGX 3,142,500 | Office Internet approved | Office Internet (APP.) Paid
null null. 256782869688. Najjanankumbi:Kampala Entebbe Road.0.272158,32.569505 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO25285260 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256394506338. Bweyogerere:Banda.0.342392,32.632687 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO13271513 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256783558578. Kira:Namugongo Road.0.354044,32.607805 . FTTH_40_M_O | 2023-02-13 | FTTO | MTNFTTO34026448 | 0 | Completed | UGX 2,849,380.0 | Office Internet approved | Office Internet (APP.) Paid
null null. 256773179223. Bweyogerere:Jinja Road.0.352809,32.662378 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO84623143 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256780110929. Ntinda (Kyambogo - Min Village):Martyrs Way.0.220018,32.551593 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO27106487 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256775083636. Bweyogerere:Bweyogerere.0.353518,32.661228 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO81751351 | 2 | Completed | UGX 3,421,836.6 | Office Internet approved | Office Internet (APP.) Paid
null null. 256789976919. Mbarara:Boma Road.0.612846,30.659405 . FTTH_20_M_O | 2023-02-13 | FTTO | MTNFTTO18836868 | 3 | Completed |  | Office Internet approved | Office Internet (APP.) Paid
null null. 256770609016. Bugolobi:Luthuli Avenue.0.305675,32.627175 . FTTH_40_M_O | 2023-02-14 | FTTO | MTNFTTO14765385 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256787902737. Ntinda (Kyambogo - Min Village):Kigobe Road.0.345366,32.619184 . FTTH_40_M_O | 2023-02-14 | FTTO | MTNFTTO20071716 | 0 | Completed | UGX 1,744,680 | Office Internet approved | Office Internet (APP.) Paid
null null. 256785261262. Bweyogerere:Kireka Road.0.346714,32.650141 . FTTH_20_M_O | 2023-02-14 | FTTO | MTNFTTO08004084 | 0 | Completed | 1,736,575.0 | Office Internet approved | Office Internet (APP.) Pending
null null. 256772386230. Kololo:Lugogo Bypass.0.338977,32.598527 . FTTH_40_M_O | 2023-02-14 | FTTO | MTNFTTO77776278 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256762196675. Luzira:Port Bell road.0.30412,32.635376 . FTTH_40_M_O | 2023-02-14 | FTTO | MTNFTTO16281177 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256776744128. Kololo:Kololo Hill Drive.0.337856,32.588183 . FTTH_20_M_O | 2023-02-14 | FTTO | MTNFTTO10387154 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Paid
null null. 256780891662. Rubaga:Stensera Road.0.35742,32.567393 . FTTH_20_M_O | 2023-02-14 | FTTO | MTNFTTO82762501 | 0 | Completed | UGX 3,200,232 | Office Internet approved | Office Internet (APP.) Pending
null null. 256782576710. Bugolobi:Mbuya Road.0.325809,32.637767 . FTTH_20_M_O | 2023-02-15 | FTTO | MTNFTTO44816705 | 0 | Completed | UGX 4,250,569.4 | Office Internet approved | Office Internet (APP.) Pending
null null. 256780225982. Kololo:Wampewo Avenue.0.325748,32.597231 . FTTH_40_M_O | 2023-02-15 | FTTO | MTNFTTO33748786 | 0 | Completed | N/A | Office Internet approved | Office Internet (APP.) Pending
null null. 256789200996. Rubaga:Mutundwe Road.0.299412,32.537718 . FTTH_40_M_O | 2023-02-15 | FTTO | MTNFTTO07356087 | 0 | Completed | UGX 2,372,272 | Office Internet approved | Office Internet (APP.) Pending
null null. 256780238373. Mbale:Republic Street.0.313536,32.586683 . FTTH_40_M_O | 2023-02-08 | FTTO | MTNFTTO36538644 | 5 | Completed | UGX 3,888,643 | Office Internet approved | Office Internet (APP.) Pending

## Detailed summary
| Customer Name | Cluster | Work Order ID | Contractor | HP ( Cost) | HC ( Cost) | Service Cost | Total cost | FTTx type | Installation delay due to customer (days) | Installation Status | po | Date logged | Customer commitment/Payment date | Planned End Date | Date commissioned | Total MTTI (days) | MTTI after payment/Customer commitment | Remarks | Snag tracker | PAC Date | PAC status | FAC status | Homes Passed
January | null null. 256787478346. Mukono:Nasuuti.0.36048,32.745624 . FTTH_40_M_O | Mukono |  | Selmer |  |  |  | 4709799.6 | Office Internet | 0 | Done | Office Internet (on air) | 2022-12-19 | 2022-12-20 | 2022-12-22 | 2023-01-02 | 14 | 13 | Network Freeze |  |  | PAC Done
| LAURAH KAYAGA. 256782032264. Buwate:Kungu.0.310761,32.578064 . FTTH_20_M_O | Buwate |  | ATX |  |  |  | 3,247,312 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-12 | 2022-12-20 | 2022-12-22 | 2023-01-02 | 21 | 13 | Network Freeze |  |  | PAC Done
| FARHAN ABDI HASSAN. 256760592290. Rubaga:Kabusu Road.0.296088,32.551404 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2070522.1 | Office Internet | 0 | Done | Office internet (on air) | 2022-10-19 | 2022-12-26 | 2022-12-28 | 2022-12-30 | 72 | 4 | Network Freeze |  |  | PAC Done
| Sulaiman Nattimba Fatuma 256773427227 Entebbe:Church Road 0.048655 ,32.468981 FTTH_40_M_O | Entebbe |  | ATX |  |  |  | 5146096.2 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-23 | 2023-01-02 | 2023-01-04 | 2023-01-02 | 10 | 0 | Network Freeze |  |  | PAC Done
| null null. 256778154517. Mbarara:Kabale - Mbarara Road.0.616224,30.654322 . FTTH_20_M_O | Mbarara |  | ATX |  |  |  | 12,218,224 | Office Internet | 0 | Done | Office internet (on air) | 2022-11-28 | 2022-12-08 | 2022-12-10 | 2023-01-04 | 37 | 27 | Reassigned to ATX on 20th December. PO issue with ROntech |  |  | PAC Done
| null null. 256777444295. Mbarara:Buremba Road.0.607731,30.661851 . FTTH_20_M_O | Mbarara |  | ATX |  |  |  | 12,218,224 | Office Internet | 4 | Done | Office internet (on air) | 2022-11-24 | 2022-12-15 | 2022-12-17 | 2023-01-04 | 41 | 16 | Reassigned to ATX on 20th December. PO issue with ROntech |  |  | PAC Done
| SHARON NABUWULE. 256773687497. Kisaasi:Kyanja Ring Road.0.378259,32.599126 . FTTH_40_M_O | Kisaasi (Kyanja - Kulambiro) |  | Enetworks |  |  |  | 2,783,195.8 | Office Internet | 0 | Done | Office internet (on air) | 2022-11-03 | 2022-12-22 | 2022-12-24 | 2023-01-03 | 61 | 12 |  |  |  | PAC Done
| null null. 256781461023. Makerere:Bombo Road.0.34057,32.570327 . FTTH_20_M_O | Makerere |  | CoolWave |  |  |  | 3789082 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-04 | 2023-01-06 | 2023-01-05 | 3 | 1 |  |  |  | PAC Done
| null null. 256760962789. Rubaga:Stensera Road.0.298869,32.601517 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4612624.6 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-30 | 2023-01-03 | 2023-01-05 | 2023-01-06 | 7 | 3 |  | Cable to be tensioned |  | PAC Done
| null null. 256783307541. Luzira:Port Bell road.0.353921,32.607822 . FTTH_20_M_O | Luzira |  | Enetworks |  |  |  | 2363651 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-03 | 2023-01-05 | 2023-01-07 | 2023-01-06 | 3 | 1 |  |  |  | PAC Done
| CIPLA QUALITY CHEMICALS. 256772789725. KANYANYA.0.369885,32.58359 . FTTH_40 | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 0 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-01-03 | 2023-01-09 | 2023-01-11 | 2023-01-09 | 6 | 0 | User was active as prepaid now migrated to Postpaid |  |  | PAC Done
| null null. 256788254548. Bwebajja:Arkright City.0.183424,32.539219 . FTTH_20_M_O | Bwebajja |  | Chrif |  |  |  | 3357296.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-02 | 2023-01-04 | 2023-01-07 | 5 | 5 |  |  |  | PAC Done
| null null. 256773155598. Najjanankumbi:Kampala Entebbe Road.0.295037,32.572762 . FTTH_40_M_O | Najjanankumbi (Lubowa - Lweza) |  | ATX |  |  |  | 3792869.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-06 | 2023-01-08 | 2023-01-09 | 7 | 3 |  |  |  | PAC Done
| null null. 256773879175. Luzira:Mutungo Ring Road.0.338189,32.622669 . FTTH_20_M_O | Luzira |  | Enetworks |  |  |  | 4,091,795.0 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-06 | 2023-01-08 | 2023-01-07 | 5 | 1 |  |  |  | PAC Done
| null null. 256772970641. Ntinda (Kiwatule - Naalya):Flamingo Close.0.357614,32.619044 . FTTH_40_M_O | Ntinda (Kiwatule - Naalya ) |  | Seagate |  |  |  | 1818380 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-19 | 2023-01-04 | 2023-01-06 | 2023-01-06 | 18 | 2 |  |  |  | PAC Done
| PETROLEUM AUTHORITY OF UGANDA. 256785980600. SALAAMA MUNYONYO.0.244253,32.617981 . FTTH_20 | Ggaba |  | Rontech |  |  |  | 0 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2022-12-19 | 2023-01-09 | 2023-01-11 | 2023-01-09 | 21 | 0 | User was active as prepaid now migrated to Postpaid |  |  | PAC Done
| ERIA BENJAMINE JJAGWE. 256782356690. Najjanankumbi:Kampala Entebbe Road.0.283677,32.568446 . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | ATX |  |  |  | 2070277.6 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-29 | 2023-01-03 | 2023-01-05 | 2023-01-07 | 9 | 4 | civil works commenced today |  |  | PAC Done
| ROSEMARY KABASINGUZI. 256771270472. Entebbe:Nsamizi Road.0.06131,32.46136 . FTTH_40_M_O | Entebbe |  | Chrif |  |  |  | 4,480,683.80 | Office Internet | 0 | Done | Office internet (on air) | 2022-11-26 | 2022-11-29 | 2022-12-01 | 2023-01-07 | 42 | 39 | Pole erection and cable hauling done, traffic routing ongoing |  |  | PAC Done
| DANIEL ARINDA. 256775545901. Mbarara:High Street.-0.585049,30.678533 . FTTH_20_M_O | Mbarara |  | ATX |  |  |  | 12,218,224 | Office Internet | 4 | Done | Office internet (on air) | 2022-11-08 | 2022-12-15 | 2022-12-17 | 2023-01-05 | 58 | 17 | Access denied |  |  | PAC Done
| null null. 256762811678. Najjanankumbi:Kampala Entebbe Road.0.288558,32.570014 . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | ATX |  |  |  | 2114920.1 | Office Internet | 10 | Done | Office internet (on air) | 2022-11-25 | 2022-12-27 | 2022-12-29 | 2023-01-09 | 45 | 3 |  |  |  | PAC Done
| null null. 256775166621. Makerere:Sir Apollo Kaggwa Road.0.308021,32.570305 . FTTH_20_M_O | Makerere |  | CoolWave |  |  |  | 4,261,624 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-03 | 2023-01-04 | 2023-01-06 | 2023-01-06 | 3 | 2 |  |  |  | PAC Done
| null null. 256788800515. Luzira:Old Butabika Road.0.315045,32.654657 . FTTH_20_M_O | Luzira |  | Enetworks |  |  |  | 12389758.2 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-29 | 2023-01-04 | 2023-01-06 | 2023-01-06 | 8 | 2 | Above DOA >> Consolidated with null null. 256772122602. Luzira:Old Butabika Road.0.313644,32.653555 . FTTH_20_M who has not paid |  |  | PAC Done
| null null. 256772746557. Old Park:Luwum Street.0.307432,32.570534 . FTTH_40_M_O | Old park |  | Chrif |  |  |  | 2049221 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-21 | 2023-01-04 | 2023-01-06 | 2023-01-06 | 16 | 2 |  |  |  | PAC Done
| null null. 256782400722. Kampala Downtown:Kyaggwe Road.0.317983,32.573507 . FTTH_20_M_O | Kampala downtown |  | Chrif |  |  |  | 2,397,628.10 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-02 | 2022-12-28 | 2022-12-30 | 2023-01-08 | 37 | 11 |  |  |  | PAC Done
| ROBERT TURAHE. 256777968471. Kisaasi:Bahai Road.0.356995,32.583103 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | CoolWave |  |  |  | 0 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-05 | 2023-01-07 | 2023-01-09 | 7 | 4 | User was active as prepaid now migrated to Postpaid |  |  | PAC Done
| null null. 256772432832. Bwebajja:Arkright City.0.353464,32.613416.FTTH_20_M_O 3-Jan-23 FTTO MTNFTTO72740213 | Bwebajja |  | Chrif |  |  |  | 8,117,164.20 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-03 | 2023-01-05 | 2023-01-07 | 2023-01-10 | 7 | 5 |  |  |  | PAC Done
| null null. 256783216649. Kisaasi:Kulambiro.0.379161,32.617861 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 1336890 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-03 | 2023-01-09 | 2023-01-11 | 2023-01-10 | 7 | 1 |  |  |  | PAC Done
| null null. 256778542478. Rubaga:Lungujja.0.298393,32.536057 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2,719,529.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-05 | 2023-01-07 | 2023-01-09 | 7 | 4 |  |  |  | PAC Done
| null null. 256785137637. Rubaga:Rubaga Road.0.296561,32.556695 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2,137,119.10 | Office Internet | 0 | Done | Office internet (on air) | 2022-01-01 | 2023-01-07 | 2023-01-09 | 2023-01-09 | 373 | 2 |  |  |  | PAC Done
| null null. 256773344238. Ntinda (Kyambogo - Min Village):Martyrs Way.0.355279,32.616217 . FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 4290700 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-28 | 2023-01-05 | 2023-01-07 | 2023-01-09 | 12 | 4 |  | Manage slack on Pole 1&3, Place Joint Box higher on the pole, very close to the ground (wrong correction photo shared) |  | PAC DONE
| EZRA BALEERO DAVID MPAATA. 256789425020. Kampala Upper CBD:Kampala Road.0.314977,32.576966 . FTTH_40_M_O | Old park |  | Chrif |  |  |  | 2913408 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-19 | 2023-01-02 | 2023-01-04 | 2023-01-10 | 22 | 8 |  |  |  | PAC Done
| null null. 256789748052. Seeta:Seeta Town.0.371023,32.710549 . FTTH_20_M_O | Seeta |  | Chrif |  |  |  | 6,873,916.8 | Office Internet | 3 | Done | Office internet (on air) | 2022-12-12 | 2022-12-30 | 2023-01-01 | 2023-01-10 | 29 | 8 | Consolidation delayed by another customer who didnt pay on time ( null null. 256789748052. Seeta:Seeta Town.0.371023,32.710549 . FTTH_20_M_O null null. 256783378924. Seeta:Seeta Town.0.370774,32.710902 . FTTH_20_M_O) |  |  | PAC Done
| null null. 256783378924. Seeta:Seeta Town.0.370774,32.710902 . FTTH_20_M_O | Seeta |  | Chrif |  |  |  | 6,873,916.8 | Office Internet | 3 | Done | Office internet (on air) | 2022-12-05 | 2022-12-30 | 2023-01-01 | 2023-01-10 | 36 | 8 | Consolidation delayed by another customer who didnt pay on time ( null null. 256789748052. Seeta:Seeta Town.0.371023,32.710549 . FTTH_20_M_O null null. 256783378924. Seeta:Seeta Town.0.370774,32.710902 . FTTH_20_M_O) | 1. Need to reecoil on last pole 2. Remove cable from bush 3.Sharp curve due to jackfruit branch
| JULIET NANDUJJA. 256772088897. Ntinda Bukoto:Kira Road.0.356203,32.611431 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2025879.6 | Office Internet | 0 | Done | Office internet (on air) | 2022-10-17 | 2023-01-06 | 2023-01-08 | 2023-01-11 | 86 | 5 |  |  |  | PAC Done
| null null. 256770944590. Ggaba:Ggaba Road.0.274553,32.616103 . FTTH_40_M_O | Ggaba |  | Rontech |  |  |  | 2025879.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-04 | 2023-01-09 | 2023-01-11 | 2023-01-12 | 8 | 3 |  |  |  | PAC Done
| null null. 256788120774. Kisaasi:Kyanja Ring Road.0.394091,32.598952 . FTTH_40_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 3466029 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-30 | 2023-01-05 | 2023-01-07 | 2023-01-13 | 14 | 8 |  |  |  | PAC Done
| null null. 256788003468. Rubaga:Mengo.0.315243,32.564413 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 3494940 | Office Internet | 0 | Done | Office internet (on air) | 2022-11-18 | 2023-01-03 | 2023-01-05 | 2023-01-11 | 54 | 8 |  |  |  | PAC Done
| JAPHETH GALIWANGO. 256785787894. Bwebajja:Kajjansi.0.231136,32.541693 . FTTH_20_M_O | Bwebajja |  | Chrif |  |  |  | 1479343.6 | Office Internet | 0 | Done | Office internet (on air) | 2022-11-15 | 2023-01-05 | 2023-01-07 | 2023-01-12 | 58 | 7 |  |  |  | PAC Done
| null null. 256786216613. Rubaga:Kabusu Road.0.298534,32.535853 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 6,688,824 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-30 | 2023-01-12 | 2023-01-14 | 2023-01-15 | 16 | 3 |  |  |  | PAC Done
| null null. 256761134101. Kampala Upper CBD:Kampala Road.0.313745,32.580151 . FTTH_20_M_O | Old park |  | Chrif |  |  |  | 1467070.6 | Office Internet | 15 | Done | Office internet (on air) | 2022-12-12 | 2022-12-14 | 2022-12-16 | 2023-01-14 | 33 | 16 | Contact is not available |  |  | PAC Done
| ATC. 256780140632. Kasasiro Luzira.0,0 . FTTH_20 | Luzira |  | Enetworks |  |  |  | 8505005.6 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2022-11-29 | 2023-01-17 | 2023-01-19 | 2023-01-17 | 49 | 0 | Not available during the Weekend , to close on 10/01/23 |  |  | PAC Done
| null null. 256773805845. Entebbe:Bugonga Road.0.053028,32.469192 . FTTH_20_M_O | Entebbe |  | ATX |  |  |  | 2811716.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-04 | 2023-01-10 | 2023-01-12 | 2023-01-16 | 12 | 6 |  |  |  | PAC Done
| null null. 256774231254. Kampala Upper CBD:Kampala Road.0.331018,32.593107 . FTTH_20_M_O | Kololo |  | CoolWave |  |  |  | 2,129,292 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-16 | 2023-01-18 | 2023-01-17 | 5 | 1 |  |  |  | PAC Done
| SUMANT KUMAR KUMAR. 256775543208. Ntinda Bukoto:Old Kira Road.0.348805,32.59889 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2045966.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-16 | 2023-01-18 | 2023-01-17 | 5 | 1 |  |  |  | PAC Done
| null null. 256772575884. Rubaga:Lubowa Terrace Road.0.287964,32.563066 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2048323.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-16 | 2023-01-18 | 2023-01-18 | 8 | 2 |  |  |  | PAC Done
| BRENDA AMONG. 256776587629. Kira:Namugongo Road.0.365417,32.653672 . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 1989625 | Office Internet | 15 | Done | Office internet (on air) | 2022-12-02 | 2023-01-04 | 2023-01-06 | 2023-01-19 | 48 | 0 |  |  |  | PAC Done
| null null.256775380000.Kololo:KAR Road.0.324178,32.598766.FTTH_20_M_O | Kololo |  | CoolWave |  |  |  | 1,729,360 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-13 | 2023-01-16 | 2023-01-18 | 2023-01-18 | 5 | 2 |  |  |  | PAC Done
| Tusiime Eseza. 256770643625. Nakasero Hill:Buganda Road.0.317548,32.576783 . FTTH_20_M_O | Nakasero Hill |  | CoolWave |  |  |  | 2,426,134 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-17 | 2023-01-19 | 2023-01-19 | 7 | 2 |  |  |  | PAC Done
| null null. 256782541119. Bugolobi:Port Bell road.0.318535,32.627569 . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 3,149,483.0 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-11 | 2023-01-17 | 2023-01-19 | 2023-01-19 | 8 | 2 |  |  |  | PAC Done
| Brandon. 256782129261. Ntinda (Kyambogo - Min Village):Kyambogo Road.0.342282,32.629379 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 4217391 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-16 | 2023-01-18 | 2023-01-19 | 9 | 3 |  |  |  | PAC Done
| null null. 256775833909. Fort Portal:Fort Portal Mpondwe Road.0.652979,30.27168 . FTTH_20_M_O | Fort portal |  | ATX |  |  |  | 3,156,177.10 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-17 | 2023-01-19 | 2023-01-20 | 10 | 3 |  |  |  | PAC Done
| null null. 256782647213. Kampala Upper CBD:Colville Street.0.313432,32.583845.FTTH_20_M_O | Kampala Upper CBD |  | Chrif |  |  |  | 2670011.6 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-14 | 2022-12-29 | 2022-12-31 | 2023-01-19 | 36 | 21 | High BOQ, Get more Clients, 0786216613 yet to pay |  |  | PAC Done
| null null. 256760055140. Bugolobi:Port Bell road.0.189375,32.529319 . FTTH_40_M_O | Bugolobi |  | CoolWave |  |  |  | 3491332.2 | Office Internet | 7 | Done | Office internet (on air) | 2023-01-04 | 2023-01-11 | 2023-01-13 | 2023-01-19 | 15 | 1 |  |  |  | PAC Done
| null null. 256783869342. Nsambya:Kabega Road.0.2976,32.590401 . FTTH_40_M_O | Nsambya |  | Chrif |  |  |  | 2,495,620.60 | Office Internet | 4 | Done | Office internet (on air) | 2023-01-04 | 2023-01-10 | 2023-01-12 | 2023-01-20 | 16 | 6 | Onhold, r.o.w challenge, we’re handling with the client possibly tomorrow pole erection will resume |  |  | PAC Done
| null null. 256787676280. Muyenga:Tank Hill Road.0.297135,32.608681 . FTTH_20_M_O | Muyenga |  | ATX |  |  |  | 2,389,592.10 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-16 | 2023-01-18 | 2023-01-19 | 9 | 3 |  |  |  | PAC Done
| Ramathan Sitina. 256783778720. Rubaga:Rubaga Road.0.307928,32.563186 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2048323.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-17 | 2023-01-19 | 2023-01-19 | 7 | 2 |  |  |  | PAC Done
| Margaretha Wilhelmina Geluka. 256787745145. Makindye:Kizungu Road.0.340207,32.588781 . FTTH_20_M_O | Makindye |  | Chrif |  |  |  | 4,251,680.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-16 | 2023-01-18 | 2023-01-22 | 12 | 6 | Margeretha wilhelmina 256787745145- traffic routing ongoing with challenges, the f.a.t from where the client picks (Rwahana Rugunda) is full, so we're routing traffic, also r.o.w and heavy down pours challenged us, tomorrow he will be on air. |  |  | PAC Done
| SULAIMAN AGABA. 256777069580. Ntinda Bukoto:Semawata Road.0.346906,32.615575 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2,041,152.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-16 | 2023-01-19 | 2023-01-21 | 2023-01-21 | 5 | 2 |  |  |  | PAC Done
| null null. 256760757698. Ntinda Bukoto:Kira Road.0.343234,32.587644 . FTTH_40_M_O | Ntinda (Bukoto) |  | Chrif |  |  |  | 5996530.6 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-05 | 2022-12-06 | 2022-12-08 | 2023-01-23 | 49 | 48 | HIGH BOQ/Fiber extension to null null. 256781557267 and 256760757698. Kololo:Mawanda Road.0.340696,32.58565 (Crest hill) |  |  | PAC Done
| null null. 256762486291. Bwebajja:Kitende.0.404778,32.543815 . FTTH_20_M_O | Bwebajja |  | Chrif |  |  |  | 9,124,566.20 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-16 | 2023-01-18 | 2023-01-23 | 13 | 7 | Payment approved on 19th Jan, Consolidated with 256762429152 |  |  | PAC Done
| null null. 256783375364. Entebbe:Hill Lane.0.225029,32.555774 . FTTH_40_M_O | Entebbe |  | ATX |  |  |  | 2,181,517 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-17 | 2023-01-20 | 2023-01-22 | 2023-01-24 | 7 | 4 |  |  |  | PAC Done
| null null. 256787527936. Bugolobi:Port Bell road.0.327587,32.612277 . FTTH_40_M_O | Bugolobi |  | CoolWave |  |  |  | 2,460,692.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-14 | 2023-01-19 | 2023-01-21 | 2023-01-23 | 9 | 4 |  |  |  | PAC Done
| null null. 256787441429. Rubaga:Mengo.0.321932,32.562543 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 3,580,272 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-19 | 2023-01-21 | 2023-01-24 | 12 | 5 |  | Cable to be repositioned |  | PAC Done
| null null. 256772468653. Nakasero Hill:Buganda Road.0.317475,32.577042 . FTTH_20_M_O | Nakasero Hill |  | CoolWave |  |  |  | 2,265,989.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-20 | 2023-01-22 | 2023-01-22 | 10 | 2 |  |  |  | PAC Done
| null null. 256772423085. Kololo:Lugogo Bypass.0.327891,32.609569 . FTTH_20_M_O | Kololo |  | Chrif |  |  |  | 1,510,468.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-19 | 2023-01-23 | 2023-01-25 | 2023-01-26 | 7 | 3 |  |  |  | PAC Done
| null null. 256785257555. Ntinda (Kyambogo - Min Village):Kyambogo Road.0.353824,32.616053 . FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 2064773 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-20 | 2023-01-22 | 2023-01-24 | 6 | 4 |  |  |  | PAC Done
| SAHIL BARKATALI KOTADIA. 256788727544. Ntinda Bukoto:Kira Road.0.342971,32.591531 . FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 3,129,639.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-23 | 2023-01-25 | 2023-01-26 | 8 | 3 |  |  |  | PAC Done
| null null. 256778406753. Ggaba:Ggaba Road.0.280948,32.608785 . FTTH_20_M_O | Ggaba |  | ATX |  |  |  | 5, 005, 652.10 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-17 | 2023-01-20 | 2023-01-22 | 2023-01-26 | 9 | 6 |  |  |  | PAC Done
| null null. 256775337752. Ggaba:Ggaba Road.0.295348,32.605454 . FTTH_20_M_O | Ggaba |  | ATX |  |  |  | 3, 750, 646.10 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-16 | 2023-01-20 | 2023-01-22 | 2023-01-26 | 10 | 6 | We were requested by landlord to plant poles on 23/01/2023 in his presence |  |  | PAC Done
| DERRICK ASEDRI. 256784114200.Luzira:Port Bell road.0.312327,32.636447.FTTH_20_M_O | Luzira |  | Enetworks |  |  |  | 3,003,053.4 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-14 | 2023-01-24 | 2023-01-26 | 2023-01-25 | 11 | 1 |  |  |  | PAC Done
| SYLVIA ACEN. 256773533115. Kampala Upper CBD:Kampala Road.0.314058,32.588746 . FTTH_40_M_O | Kampala Upper CBD |  | CoolWave |  |  |  | 2318422 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-14 | 2023-01-23 | 2023-01-25 | 2023-01-25 | 11 | 2 |  |  |  | PAC Done
| null null. 256774661505. Ntinda (Kyambogo - Min Village):Martyrs Road.0.351928,32.619791 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 8041257.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-11 | 2023-01-25 | 2023-01-27 | 2023-01-26 | 15 | 1 |  |  |  | PAC Done
| null null. 256772502949. Ntinda (Kyambogo - Min Village):Martyrs Road.0.351896,32.619769 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 4020628.55 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-11 | 2023-01-25 | 2023-01-27 | 2023-01-26 | 15 | 1 |  |  |  | PAC Done
| null null. 256784340770. Nsambya:Nsambya Estate Road.0.299329,32.591531 . FTTH_20_M_O | Nsambya |  | Chrif |  |  |  | 3,482,660.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-11 | 2023-01-16 | 2023-01-18 | 2023-01-24 | 13 | 8 | Requested to be commissioned on Sunday 22nd when the revelands office is open ,Pole erection and cable hauling done, to be commissioned on 24.1.2023 |  |  | PAC Done
| null null. 256785538779. Ntinda (Kyambogo - Min Village):Martyrs Road.0.342538,32.618264 . FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 2,469,503.80 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-18 | 2023-01-20 | 2023-01-24 | 12 | 6 |  |  |  | PAC Done
| null null. 256772544610. Kampala Upper CBD:.0.295369,32.572048 . FTTH_20_M_O | Ndeeba |  | CoolWave |  |  |  | 3796775 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-17 | 2023-01-23 | 2023-01-25 | 2023-01-27 | 10 | 4 |  |  |  | PAC Done
| null null. 256778891442. Muyenga:Kansanga Kiwafu Road.0.287562,32.620918 . FTTH_40_M_O | Muyenga |  | Chrif |  |  |  | 2,831,240.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-11 | 2023-01-18 | 2023-01-20 | 2023-01-28 | 17 | 10 | Reassiggment | No pole saver Sagging cable
| SUSAN NALUBWAMA. 256781289955. Makerere:Sir Apollo Kaggwa Road.0.359091,32.532501 . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 2142441 | Office Internet | 0 | Done | Office internet (on air) | 2022-10-13 | 2023-01-20 | 2023-01-22 | 2023-01-31 | 110 | 11 | Reassiggment |  |  | PAC Done
| null null. 256779703720. Entebbe:Hill Lane.0.266709,32.615463 . FTTH_20_M_O | Entebbe |  | Chrif |  |  |  | 4,988,321.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-25 | 2023-01-27 | 2023-01-30 | 20 | 5 |  |  |  | PAC Done
| null null. 256783012719. Bugolobi:Luthuli Road.0.321364,32.612439 . FTTH_40_M_O | Bugolobi |  | Chrif |  |  |  | 3861126.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-24 | 2023-01-26 | 2023-01-30 | 20 | 6 |  |  |  | PAC Done
| null null. 256778145842. Muyenga:Muyenga Road.0.299162,32.602148 . FTTH_20_M_O | Muyenga |  | Chrif |  |  |  | 3129995.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-20 | 2023-01-22 | 2023-02-02 | 15 | 13 | Mobilizing to start Civil works ,Pole erection and cable hauling done, to be commissioned in the morning as requested by the client | Too much cable slack on one pole opposite Telex bar site; should be distributed and reorganised |  | PAC Done
| null null. 256770726476. Makindye:Luwafu Road.0.270587,32.590308 . FTTH_20_M_O | Makindye |  | Chrif |  |  |  | 2483620.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-17 | 2023-01-21 | 2023-01-23 | 2023-01-31 | 14 | 10 | Traffic Routing |  |  | PAC Done
| null null. 256776472799. Mbarara:Kabale - Mbarara Road.-0.603693,30.66286 . FTTH_20_M_O | Mbarara |  | Chrif |  |  |  | 10271304.2 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-21 | 2023-01-23 | 2023-01-31 | 13 | 10 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256776610690. Buwate:Seeta Kasangati.0.415646,32.614145 . FTTH_40_M_O | Buwate |  | Seagate |  |  |  | 18134278 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-02 | 2022-12-25 | 2022-12-27 | 2023-01-31 | 60 | 37 | Consolidated as null null. 256776610690. Buwate:Seeta Kasangati.0.415646,32.614145 . FTTH_40_M_O null null. 256784964814. Buwate:Seeta Kasangati.0.417627,32.615911 . FTTH_20_M null null. 256778078045. Buwate:Seeta Kasangati.0.414345,32.626862 . FTTH_20_M null null. 256775888785. Buwate:Seeta Kasangati.0.328652,32.619949 . FTTH_20_M_O |  |  | PAC Done
| null null. 256778078045.Buwate:Seeta Kasangati.0.330231,32.619174.FTTH_20_M_O | Buwate |  | Seagate |  |  |  | 18134278 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-16 | 2023-01-20 | 2023-01-22 | 2023-01-31 | 15 | 11 | Consolidated as null null. 256776610690. Buwate:Seeta Kasangati.0.415646,32.614145 . FTTH_40_M_O null null. 256784964814. Buwate:Seeta Kasangati.0.417627,32.615911 . FTTH_20_M null null. 256778078045. Buwate:Seeta Kasangati.0.414345,32.626862 . FTTH_20_M null null. 256775888785. Buwate:Seeta Kasangati.0.328652,32.619949 . FTTH_20_M_O |  |  | PAC Done
| null null. 256775888785. Buwate:Seeta Kasangati.0.328652,32.619949 . FTTH_20_M_O | Buwate |  | Seagate |  |  |  | 18134278 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-25 | 2023-01-28 | 2023-01-30 | 2023-01-31 | 6 | 3 |  |  |  | PAC Done
February | null null. 256781088363. Bugolobi:Luthuli Avenue.0.353988,32.607839 . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 1722345 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-24 | 2023-01-30 | 2023-02-01 | 2023-01-31 | 7 | 1 |  |  |  | PAC Done
| null null. 256776890891. Luzira:Port Bell road.0.306803,32.633325 . FTTH_40_M_O | Luzira |  | Enetworks |  |  |  | 4847702.8 | Office Internet | 2 | Done | Office internet (on air) | 2023-01-25 | 2023-01-28 | 2023-01-30 | 2023-02-01 | 7 | 2 |  |  |  | PAC Done
| null null. 256760969380. Ntinda (Kiwatule - Naalya):Naalya Namugongo Road.0.400042,32.665774 . FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Seagate |  |  |  | 4593968.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-23 | 2023-01-29 | 2023-01-31 | 2023-02-01 | 9 | 3 |  |  |  | PAC DONE
| null null. 256773438364. Ntinda (Kiwatule - Naalya):Naalya Namugongo Road.0.360668,32.572801 . FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Seagate |  |  |  | 4593968.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-26 | 2023-01-31 | 2023-02-02 | 2023-02-02 | 7 | 2 |  |  |  | PAC DONE
| null null. 256773040776. Makerere:Bombo Road.0.348119,32.564702 . FTTH_20_M_O | Makerere |  | Chrif |  |  |  | 2,683,767.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-20 | 2023-01-24 | 2023-01-26 | 2023-02-01 | 12 | 8 |  |  |  | PAC Done
| null null. 256777680580 Ntinda (Kyambogo - Min Village):Martyrs Way.0.355209, 32.61611.FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 3,344,724.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-30 | 2023-01-31 | 2023-02-02 | 2023-02-02 | 3 | 2 |  |  |  | PAC Done
| null null. 256789500722. Mbarara:Boma Road.-0.607096,30.669088 . FTTH_20_M_O | Mbarara |  | Chrif |  |  |  | 10271304.2 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-17 | 2023-01-31 | 2023-02-02 | 2023-02-01 | 15 | 1 |  |  |  | PAC Done
| null null. 256783570970. Makerere:Sir Apollo Kaggwa Road.0.353988,32.60785 . FTTH_20_M_O | Makerere |  | Chrif |  |  |  | 2,741,967.00 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-20 | 2023-01-24 | 2023-01-26 | 2023-02-01 | 12 | 8 | On Hold due to PO |  |  | PAC Done
| ATC Uganda - JUANITA KARAMAGI. 256787370808. Ggaba:Kalungu.0.272501,32.616971 . FTTH_20 | Ggaba |  | Chrif |  |  |  | 1387672.3 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-01-21 | 2023-02-06 | 2023-02-08 | 2023-02-06 | 16 | 0 | Pending VLAN |  |  | PAC Done
| null null. 256774699135. Rubaga:Kabusu Road.0.301788,32.556475 . FTTH_40_M_O | Rubaga |  | Chrif |  |  |  | 1,637,468.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-19 | 2023-01-21 | 2023-01-23 | 2023-02-04 | 16 | 14 | On Hold due to PO |  |  | PAC Done
| null null. 256782863490. Mbale:Masaba Road.1.07712,34.177356 . FTTH_40_M_O | Mbale |  | Chrif |  |  |  | 4393972 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-27 | 2023-01-29 | 2023-02-03 | 16 | 7 | On Hold due to PO |  |  | PAC Done
| Henry Mugerwa. 256788323540. Rubaga:Rubaga Road.0.304459,32.557983 . FTTH_20_M_O | Rubaga |  | Chrif |  |  |  | 2,802,496.90 | Office Internet | 0 | Done | Office internet (on air) | 2022-08-08 | 2023-01-22 | 2023-01-24 | 2023-02-06 | 182 | 15 | On Hold due to PO |  |  | PAC Done
| null null. 256783564019. Ntinda Bukoto:Bukoti Ntunda Road.0.343526,32.61568 . FTTH_40_M_O | Ntinda (Bukoto) |  | Seagate |  |  |  | 2,808,747.0 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-27 | 2023-01-30 | 2023-02-01 | 2023-02-04 | 8 | 5 | On Hold due to PO |  |  | PAC Done
| null null. 256773411542. Makindye:Lukuli Road.0.27029,32.611318 . FTTH_20_M_O | Makindye |  | Chrif |  |  |  | 1,787,280.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-28 | 2023-01-31 | 2023-02-02 | 2023-02-04 | 7 | 4 | On Hold due to PO |  |  | PAC Done
| null null. 256786301521. Ntinda (Kyambogo - Min Village):Charles Lwanga Road.0.35107,32.614498 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 2,032,173.4 | Office Internet | 2 | Done | Office internet (on air) | 2023-01-27 | 2023-01-31 | 2023-02-02 | 2023-02-05 | 9 | 3 | Client is near bank of Africa Ntinda works on hold we shall need guides from the property management technician and he is not available. |  |  | PAC Done
| ATC Uganda Ltd. 256774483950. Bulabira Road.0.379306,32.622278 . FTTH_20 | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 4612258 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-01-27 | 2023-02-03 | 2023-02-05 | 2023-02-03 | 7 | 0 | On Hold due to PO | Poor slack mgt on Pole 3 |  | PAC DONE
| null null. 256786993999. Namuwongo:Namuwongo Road.0.306027,32.612582 . FTTH_20_M_O | Namuwongo |  | Chrif |  |  |  | 3,128,656.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-25 | 2023-02-02 | 2023-02-04 | 2023-02-05 | 11 | 3 |  |  |  | PAC Done
| null null. 256786242486. Rubaga:Mengo.0.385556,32.487142 . FTTH_20_M_O | Rubaga |  | Chrif |  |  |  | 2282006 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-30 | 2023-02-01 | 2023-02-04 | 17 | 5 |  |  |  | PAC Done
| Akullo Judith. 256777108453. Ntinda Bukoto:Bukoto Kisaasi Road.0.355366,32.594517 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 5,584,721 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-02 | 2023-02-04 | 2023-02-04 | 4 | 2 | On Hold due to PO |  |  | PAC Done
| null null. 256780476925. Bweyogerere:Jinja Road.0.350172,32.654769 . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 2437224.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-27 | 2023-02-01 | 2023-02-03 | 2023-02-06 | 10 | 5 |  |  |  | PAC Done
| Kemigabo Teddy. 256781585769. Seeta:Bukerere Road.0.394095,32.703068 . FTTH_20_M_O | Seeta |  | Enetworks |  |  |  | 12,072,753.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-23 | 2023-02-02 | 2023-02-04 | 2023-02-06 | 14 | 4 |  |  |  | PAC Done
| null null. 256778099176. Ntinda Bukoto:Bukoto Kisaasi Road.0.355384,32.594488 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 5,584,721 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-02 | 2023-02-04 | 2023-02-04 | 4 | 2 |  | Plumb Pole & Compact back fill. |  | PAC DONE
| null null. 256771670696. Ntinda Bukoto:Naguru Drive. FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 4718890 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-03 | 2023-02-03 | 2023-02-05 | 2023-02-05 | 2 | 2 |  |  |  | PAC Done
| JESCA MUHEBWA. 256788809554. Makerere:Sir Apollo Kaggwa Road.0.33839,32.548664 . FTTH_20_M_O | Makerere |  | CoolWave |  |  |  | 4,901,028 | Office Internet | 10 | Done | Office internet (on air) | 2022-10-07 | 2023-01-05 | 2023-01-07 | 2023-01-20 | 105 | 5 | Customer re arrangement since they they were uanvailable for survey |  |  | PAC Done
| null null. 256784847773. Seeta:Bukerere Road.0.37974,32.708415 . FTTH_20_M_O | Seeta |  | Enetworks |  |  |  | 12072753.8 | Office Internet | 4 | Done | Office internet (on air) | 2023-01-19 | 2023-01-26 | 2023-01-28 | 2023-02-07 | 19 | 8 | Waiting for payments by 256781585769 |  |  | PAC Done
| null null. 256773563820. Entebbe:Nakiwogo Road.0.056582,32.457909 . FTTH_20_M_O | Entebbe |  | Chrif |  |  |  | 2906574.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-01 | 2023-02-03 | 2023-02-06 | 6 | 5 | On Hold due to PO |  |  | PAC Done
| null null. 256781056122. Muyenga:Kansanga Kiwafu Road.0.280184,32.614145 . FTTH_20_M_O | Muyenga |  | Chrif |  |  |  | 3096720.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-25 | 2023-01-31 | 2023-02-02 | 2023-02-07 | 13 | 7 | On Hold due to PO |  |  | PAC Done
| null null. 256789800700. Ntinda (Kyambogo - Min Village):Charles Lwanga Road.0.349314,32.619444 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 4521270 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-02 | 2023-02-04 | 2023-02-07 | 7 | 5 | On Hold due to PO |  |  | PAC Done
| null null. 256779044605. Rubaga:Kabusu Road.0.298484,32.536061 . FTTH_20_M_O | Rubaga |  | Chrif |  |  |  | 4999680.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-01 | 2023-02-03 | 2023-02-08 | 8 | 7 | On Hold due to PO |  |  | PAC Done
| Namaganda Patricia , 256775021474 Kira:Namugongo Road 0.365877, 32.655111 FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 1485336.2 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-05 | 2022-12-23 | 2022-12-25 | 2023-02-07 | 64 | 46 | On Hold due to PO |  |  | PAC Done
| null null. 256784693787. Najjanankumbi:Kampala Entebbe Road.0.285279,32.569266 . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 3,101,015 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-31 | 2023-02-02 | 2023-02-10 | 23 | 10 | Contact is not answered |  |  | PAC Done
| STEVEN OKITOI. 256778907937. Bugolobi:Mbuya Road.0.309353,32.624837 . FTTH_20_M_O | Bugolobi |  | CoolWave |  |  |  | 4,480,527 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-06 | 2023-01-27 | 2023-01-29 | 2023-02-07 | 63 | 11 | On Hold due to PO |  |  | PAC Done
| null null. 256762578291. Kololo:Acacia Avenue.0.338325,32.59669 . FTTH_20_M_O | Kololo |  | CoolWave |  |  |  | 1,739,518 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-23 | 2023-02-03 | 2023-02-05 | 2023-02-04 | 12 | 1 |  |  |  | PAC Done
| null null. 256785873695. Bugolobi:Younger Avenue.0.319884,32.617465 . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 1707242.2 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-06 | 2023-02-08 | 2023-02-09 | 9 | 3 |  |  |  | PAC Done
| null null. 256760905149. Kisaasi:Kisaasi Kira Road.0.3064,32.644021 . FTTH_40_M_O | Kisaasi (Kyanja - Kulambiro) |  | Enetworks |  |  |  | 1,286,080.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-02 | 2023-02-07 | 2023-02-09 | 2023-02-08 | 6 | 1 |  |  |  | PAC Done
| null null. 256783152627. Ntinda Bukoto:Saddler Way.0.341104,32.59937 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2828060.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-02-07 | 2023-02-09 | 2023-02-09 | 38 | 2 |  |  |  | PAC Done
| RONALD NYAKAHUMA. 256772722190. Rubaga:Mutundwe Road.0.294483,32.552784 . FTTH_40_M_O | Rubaga |  | Chrif |  |  |  | 3982172 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-19 | 2023-01-30 | 2023-02-01 | 2023-02-09 | 21 | 10 |  |  |  | PAC Done
| null null. 256781594859. Bugolobi:Port Bell road.0.313928,32.634958 . FTTH_40_M_O | Bugolobi |  | Enetworks |  |  |  | 2,121,738.90 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-03 | 2023-02-09 | 2023-02-11 | 2023-02-09 | 6 | 0 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256780257568. Kampala Upper CBD:Kampala Road.0.328572,32.573974 . FTTH_20_M_O | Nakasero Hill |  | Selmer |  |  |  | 1320699.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-23 | 2023-02-04 | 2023-02-06 | 2023-02-10 | 18 | 6 |  |  |  | PAC Done
| null null. 256785198588. Kira:Namugongo Road.0.365877,32.655111 . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 2316293.4 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-05 | 2023-01-23 | 2023-01-25 | 2023-02-08 | 65 | 16 | On Hold due to PO/MTNFTTO38781065 |  |  | PAC Done
| null null. 256777898050. Ntinda (Kyambogo - Min Village):Ntinda Avenue.0.352692,32.614486 . FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 2,433,977 68.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-28 | 2023-02-06 | 2023-02-08 | 2023-02-10 | 13 | 4 | On Hold due to PO |  |  | PAC Done
| null null. 256786917512. Kisaasi:Bahai Road.32.61611,32.598017 . FTTH_40_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 4174622 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-30 | 2023-02-07 | 2023-02-09 | 2023-02-10 | 11 | 3 |  |  |  | PAC Done
| Kaitale Dennis. 256779919850. Ntinda (Kiwatule - Naalya):Majwala Road.0.361695,32.620729 . FTTH_40_M_O | Ntinda (Kiwatule - Naalya ) |  | Seagate |  |  |  | 1781282 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-07 | 2023-02-09 | 2023-02-10 | 10 | 3 |  |  |  | PAC Done
| null null. 256777147337. Rubaga:Stensera Road.0.302882,32.560654 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2,889,032 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-06 | 2023-02-08 | 2023-02-10 | 2023-02-10 | 4 | 2 |  |  |  | PAC Done
| null null. 256775858551. Makerere:Sir Apollo Kaggwa Road.0.32678,32.565037 . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 2268208 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-01 | 2023-02-08 | 2023-02-10 | 2023-02-11 | 10 | 3 |  |  |  | PAC Done
| null null. 256785171304. Ntinda (Kyambogo - Min Village):Martyrs Crescent.0.355016,32.615091 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 2828481 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-02 | 2023-02-08 | 2023-02-10 | 2023-02-10 | 8 | 2 |  |  |  | PAC Done
| Twesigye Dorothy. 256782900523. Kira:Namugongo Road.0.394758,32.666469 . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 2358778 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-30 | 2023-02-06 | 2023-02-08 | 2023-02-13 | 14 | 7 | On Hold due to PO | Drop Cable run over the Poles |  | PAC DONE
| null null. 256782786099. Kololo:Acacia Avenue.0.339505,32.587832 . FTTH_20_M_O | Kololo |  | Enetworks |  |  |  | 1,577,109.4 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-03 | 2023-02-09 | 2023-02-11 | 2023-02-11 | 8 | 2 |  |  |  | PAC Done
| null null. 256778403190. Rubaga:Nateete.EBU Sales Agent,Justin Nakimuli 7372831. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2654215 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-07 | 2023-02-08 | 2023-02-10 | 2023-02-11 | 4 | 3 |  |  |  | PAC Done
| null null. 256772486307. Ntinda Bukoto:Upper Naguru East Road.0.340233,32.609942 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 3090859.4 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-06 | 2023-02-08 | 2023-02-10 | 2023-02-12 | 6 | 4 |  |  |  | PAC Done
| null null. 256763014545. Rubaga:Rubaga Road.0.307611,32.570357 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2,026,124 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-09 | 2023-02-09 | 2023-02-11 | 2023-02-11 | 2 | 2 | Mobilizing to start Civil works |  |  | PAC Done
| null null, 256778794114 Rubaga:Kabusu Road 0.302675, 32.560959 FTTH_40_M | Rubaga |  | Chrif |  |  |  | 3342207.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-25 | 2023-01-27 | 2023-02-12 | 25 | 18 | Due to LPO issues |  |  | PAC Done
| null null. 256775193838. Najjanankumbi:Kampala Entebbe Road.0.353994,32.607845 . FTTH_40_M_O | Najjanankumbi (Lubowa - Lweza) |  | Chrif |  |  |  | 2436296.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-28 | 2023-02-02 | 2023-02-04 | 2023-02-11 | 14 | 9 | Due to LPO issues |  |  | PAC Done
| Robert Mugga. 256772517141. Kisaasi:Bahai Road.0.371402,32.596808 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 1764500 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-04 | 2023-01-23 | 2023-01-25 | 2023-01-24 | 20 | 1 |  |  |  | PAC Done
| null null. 256763033839. Rubaga:Mengo.0.307508,32.570386 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2,181,517 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-09 | 2023-02-10 | 2023-02-12 | 2023-02-11 | 2 | 1 |  |  |  | PAC Done
| null null. 256772402955. Rubaga:Lubiri Ring Road.32.47781,32.570288 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2,264,732 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-09 | 2023-02-10 | 2023-02-12 | 2023-02-11 | 2 | 1 |  |  |  | PAC Done
| null null. 256392558204. Kololo:KAR Road.0.324196,32.598788 . FTTH_40_M_O | Kololo |  | Selmer |  |  |  | 1827908 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-28 | 2023-02-10 | 2023-02-12 | 2023-02-13 | 16 | 3 |  |  |  | PAC Done
| null null. 256775234342. Kisaasi:Kulambiro.0.323084,32.47454 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 1909380 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-02-09 | 2023-02-11 | 2023-02-11 | 24 | 2 |  |  |  | PAC Done
| ARTHUR BUKENYA. 256776552590. Rubaga:Albert Cook Road.0.312593,32.554774 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2939268 | Office Internet | 0 | Done | Office internet (on air) | 2022-07-04 | 2023-02-08 | 2023-02-10 | 2023-02-10 | 221 | 2 |  |  |  | PAC Done
| null null. 256775888502. Kololo:Tufnell Drive.0.338423,32.584446 . FTTH_20_M_O | Kololo |  | Chrif |  |  |  | 2557240.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-20 | 2023-02-01 | 2023-02-03 | 2023-02-13 | 24 | 12 |  |  |  | PAC Done
| null null.256762317894.Muyenga:Muyenga Road.0.299056,32.60228.FTTH_20_M_O | Muyenga |  | Chrif |  |  |  | 4,780,708.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-01-30 | 2023-02-01 | 2023-02-03 | 16 | 4 | On Hold due to PO/Contact is off |  |  | PAC Done
| null null. 256772924106. Ntinda Bukoto:Ntinda Road.0.351944,32.615267 . FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2,212,145.80 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-06 | 2023-02-08 | 2023-02-10 | 2023-02-14 | 8 | 6 | Mobilizing to start Civil works, civil works done, to be commissioned on Monday/ROW |  |  | PAC Done
| null null. 256786450770. Bweyogerere:Kireka Road.0.3469,32.648908 . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 4336662 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-03 | 2023-02-06 | 2023-02-08 | 2023-02-14 | 11 | 8 | ROW |  |  | PAC Done
| null null. 256772694769. Nsambya:Nsambya Estate Road.0.30089,32.593472 . FTTH_40_M_O | Nsambya |  | Chrif |  |  |  | 1469070.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-04 | 2023-01-24 | 2023-01-26 | 2023-02-15 | 42 | 22 | On Hold due to PO |  |  | PAC Done
| FERDINAND TUKEI. 256781181500. Najjanankumbi:Kampala Entebbe Road.0.264078,32.566412 . FTTH_40_M_O | Najjanankumbi (Lubowa - Lweza) |  | Chrif |  |  |  | 3,934,102.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-27 | 2023-01-31 | 2023-02-02 | 2023-02-17 | 21 | 17 | On Hold due to PO ,hysical Installations done, to be on 13.2.2023 commissioned after the splitter installation at Kenjoy/ZTE upgrade |  |  | PAC Done
| null null. 256774500466. Bugolobi:Port Bell road. FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 3702645.8 | Office Internet | 5 | Done | Office internet (on air) | 2023-02-07 | 2023-02-07 | 2023-02-09 | 2023-02-16 | 9 | 4 | Access to Mbuya Switch |  |  | PAC Done
| JACKLINE ASIIMWE. 256770748959. Nsambya:Gogonya Road.0.302374,32.581387 . FTTH_20_M_O | Nsambya |  | ATX |  |  |  | 3767044 | Office Internet | 0 | Done | Office internet (on air) | 2022-12-06 | 2023-01-31 | 2023-02-02 | 2023-02-18 | 74 | 18 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256787021216. Nakasero Hill:Lumumba Avenue.0.324977,32.576469 . FTTH_40_M_O | Nakasero Hill |  | Chrif |  |  |  | 1,658,812.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-11 | 2023-02-08 | 2023-02-10 | 2023-02-14 | 34 | 6 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256775983083. Entebbe:Bugonga Road.0.053692,32.459346 . FTTH_40_M_O | Entebbe |  | ATX |  |  |  | 3,305,989 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-07 | 2023-02-10 | 2023-02-12 | 2023-02-15 | 8 | 5 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256786868420. Kololo:Mabua Road.0.373031,32.649567 . FTTH_20_M_O | Kololo |  | Selmer |  |  |  | 2109408 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-10 | 2023-02-12 | 2023-02-16 | 8 | 6 |  |  |  | PAC Done
| null null. 256779147142. Rubaga:Albert Cook Road.0.312593,32.554774 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2,159,318 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-09 | 2023-02-13 | 2023-02-15 | 2023-02-15 | 6 | 2 |  |  |  | PAC Done
| null null. 256763051615. Rubaga:Stensera Road.0.307356,32.570561 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2,070,522 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-09 | 2023-02-13 | 2023-02-15 | 2023-02-15 | 6 | 2 |  |  |  | PAC Done
| ERASMUS KAMUSIIME. 256772525978. Muyenga:Tank Hill Road.0.293286,32.617041 . FTTH_40_M_O | Muyenga |  | Rontech |  |  |  | 3057849 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-01 | 2023-02-10 | 2023-02-12 | 2023-02-14 | 13 | 4 | Civil works ongoing |  |  | PAC Done
| DINA TUMWESIGYE. 256774940218. Ntinda (Kyambogo - Min Village):Kigobe Road.0.350906,32.61559 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Seagate |  |  |  | 3190744 | Office Internet | 0 | Done | Office internet (on air) | 2022-08-09 | 2023-02-09 | 2023-02-11 | 2023-02-16 | 191 | 7 |  |  |  | PAC Done
| null null. 256788297220. Ggaba:Ggaba Road.0.284654,32.608438 . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 1816649 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-09 | 2023-02-13 | 2023-02-15 | 2023-02-15 | 6 | 2 |  |  |  | PAC Done
| null null. 256776796191. Bweyogerere:Kireka Kamuli.0.346613,32.648586 . FTTH_40_M_O | Bweyogerere |  | Enetworks |  |  |  | 1320080.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-14 | 2023-02-16 | 2023-02-15 | 7 | 1 |  |  |  | PAC Done
| null null. 256763012154. Nsambya:Nsambya Estate Road.0.296248,32.600592 . FTTH_20_M_O | Nsambya |  | ATX |  |  |  | 2,123,377 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-13 | 2023-02-15 | 2023-02-17 | 9 | 4 |  |  |  | PAC Done
| Null Null.256789200996. Rubaga:Mutundwe Road 0.299412, 32.537718. FTTH_40_M_O | Rubaga |  | Rontech |  |  |  | 2372272 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2023-02-17 | 2 | 2 |  |  |  | PAC Done
| null null. 256786867914. Luzira:Port Bell road.0.322716,32.645233 . FTTH_20_M_O | Luzira |  | Enetworks |  |  |  | 4627695.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-15 | 2023-02-17 | 2023-02-16 | 8 | 1 | Civil works ongoing |  |  | PAC Done
| null null. 256783558578. Kira:Namugongo Road.0.354044,32.607805 . FTTH_40_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 2849380 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-13 | 2023-02-15 | 2023-02-17 | 2023-02-16 | 3 | 1 |  |  |  | PAC Done
| null null. 256788702074. Rubaga:Lungujja.0.306391,32.533615 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4391357 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-15 | 2023-02-17 | 2023-02-16 | 8 | 1 |  | Joint box to be reinstated to its position |  | PAC Done
| null null. 256781035302. Rubaga:Rubaga Road.0.308333,32.569181 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 1,388,889 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-03 | 2023-02-15 | 2023-02-17 | 2023-02-16 | 13 | 1 |  |  |  | PAC Done
| null null. 256772896954. Kigo:Kigo Road.0.236272,32.564671 . FTTH_20_M_O | Kigo |  | Chrif |  |  |  | 2717611.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-04 | 2023-02-06 | 2023-02-16 | 16 | 12 |  |  |  | PAC Done
| Paul Mutebe/MTNFTTO73024060. 256772932223. Ggaba:Ggaba Road.0.284726,32.608438 . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2233904 | Office Internet | 0 | Done | Office internet (on air) | 2022-06-21 | 2023-01-30 | 2023-02-01 | 2023-02-15 | 239 | 16 |  |  |  | PAC Done
| null null. 256782935105. Entebbe:Church Road.0.092579,32.500026 . FTTH_40_M_O | Entebbe |  | ATX |  |  |  | 1,983,827 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-15 | 2023-02-17 | 2023-02-15 | 7 | 0 |  |  |  | PAC Done
| null null. 256775963938. Bwebajja:Arkright City.0.326518,32.56463 . FTTH_20_M_O | Bwebajja |  | Chrif |  |  |  | 2451668.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-02 | 2023-02-11 | 2023-02-13 | 2023-02-15 | 13 | 4 |  |  |  | PAC Done
| null null. 256774500466. Bugolobi:Port Bell road.0.317659,32.629087 . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 3,702,645.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-02 | 2023-02-09 | 2023-02-11 | 2023-02-16 | 14 | 7 |  |  |  | PAC Done
| SHALLON AINEMUKAMA. 256789290911. Bugolobi:Spring Road.0.319477,32.614403 . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 4986490.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-19 | 2023-02-08 | 2023-02-10 | 2023-02-17 | 29 | 9 | To be commissioned on 17th February |  |  | PAC Done
| null null. 256775572915. Luzira:Port Bell road.0.296646,32.655033 . FTTH_40_M_O | Luzira |  | Enetworks |  |  |  | 4,687,855.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-23 | 2023-02-10 | 2023-02-12 | 2023-02-17 | 25 | 7 | pole erection and cable hauling done, terminations and traffic routing scheduled for tomorrow 12-feb/To be commissioned on 17th February/Access to Mbuya | Slack not provided |  | PAC Done
| null null. 256779327888. Ntinda Bukoto:Bukoto Kisaasi Road.0.35091,32.59742 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 1638546.2 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-13 | 2023-02-13 | 2023-02-15 | 2023-02-17 | 4 | 4 |  |  |  | PAC Done
| null null,256780319933 Kololo:Lugogo Bypass 0.322074,32.608492 FTTH_20_M_O | Kololo |  | Selmer |  |  |  | 4653920.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-27 | 2023-02-08 | 2023-02-10 | 2023-02-17 | 21 | 9 |  | Need a stay on first pole, put a pole after Road Crossing to reduce sagging and span. Add reserve on the last pole
| null null. 256781641075. Kololo:Kira Road.0.337351,32.583223 . FTTH_40_M | Kololo |  | Selmer |  |  |  | 2,980,928.00 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-02 | 2023-02-08 | 2023-02-10 | 2023-02-18 | 16 | 10 | Phone not available |  |  | PAC Done
| null null. 256780110929. Ntinda (Kyambogo - Min Village):Martyrs Way.0.220018,32.551593 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 3748386 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-13 | 2023-02-15 | 2023-02-17 | 2023-02-18 | 5 | 3 | Cable Hauling ongoing |  |  | PAC Done
| null null. 256762854834. Nsambya:Nsambya Estate Road.0.299477,32.596658 . FTTH_20_M_O | Nsambya |  | ATX |  |  |  | 2272414 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-13 | 2023-02-15 | 2023-02-17 | 2023-02-17 | 4 | 2 |  |  |  | PAC Done
| null null. 256762196675. Luzira:Port Bell road.0.30412,32.635376 . FTTH_40_M_O | Luzira |  | Enetworks |  |  |  | 2,309,961.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-14 | 2023-02-14 | 2023-02-16 | 2023-02-18 | 4 | 4 |  |  |  | PAC Done
| null null. 256784440976. luzira Uganda. FTTH_20_M_O | Luzira |  | Enetworks |  |  |  | 4,734,055.0 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2023-02-17 | 2 | 2 | Cable hauling ongoing |  |  | PAC Done
| null null. 256761651368. ntinda. FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 3748386 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2023-02-18 | 3 | 3 | HIGH BOQ |  |  | PAC Done
| null null. 256775238397. dashin heights nsambya. FTTH_20_M_O | Nsambya |  | ATX |  |  |  | 2094822 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-16 | 2023-02-16 | 2023-02-18 | 2023-02-18 | 2 | 2 |  |  |  | PAC Done
| null null. 256783432444. Bugolobi:Spring Road.0.35399,32.607847 . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 3578053.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-05 | 2023-02-13 | 2023-02-15 | 2023-02-20 | 15 | 7 | Cable hauling ongoing |  |  | PAC Done
| null null. 256772602328. Ntinda (Kyambogo - Min Village):Charles Lwanga Road.0.348076,32.618737 . FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 3142500 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-13 | 2023-02-17 | 2023-02-19 | 2023-02-20 | 7 | 3 | Commissioning ongoing |  |  | PAC Done
| null null. 256775083636. Bweyogerere:Bweyogerere.0.353518,32.661228 . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 3421836.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-13 | 2023-02-13 | 2023-02-15 | 2023-02-20 | 7 | 7 | Pole erection ongoing |  |  | PAC Done
| null null. 256770609016. Bugolobi:Luthuli Avenue.0.305675,32.627175 . FTTH_40_M_O | Bugolobi |  | Chrif |  |  |  | 2230785.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-14 | 2023-02-17 | 2023-02-19 | 2023-02-21 | 7 | 4 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256787902737. Ntinda (Kyambogo - Min Village):Kigobe Road.0.345366,32.619184 . FTTH_40_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 1753419.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-14 | 2023-02-17 | 2023-02-19 | 2023-02-20 | 6 | 3 | Commissioning ongoing |  |  | PAC Done
| null null. 256772386230. Kololo:Lugogo Bypass.0.338977,32.598527 . FTTH_40_M_O | Kololo |  | Enetworks |  |  |  | 1693856.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-14 | 2023-02-17 | 2023-02-19 | 2023-02-18 | 4 | 1 | Mobilizing to start Civil works |  |  | PAC Done
| Balemesa Abel.256772484944.Lubowa ISU. 0.236645,32.564903.FTTH_40_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 2,781,650 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2023-02-19 | 4 | 4 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256761651368. Ntinda (Kyambogo - Min Village):Muwafu Road.0.353993,32.607838 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 5927140 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-15 | 2023-02-15 | 2023-02-17 | 2023-02-18 | 3 | 3 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256772572501. lugogo bypass. FTTH_40_M_O | Kololo |  | Enetworks |  |  |  | 1499954.2 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-18 | 1 | 1 | Mobilizing to start Civil works |  |  | PAC Done
| Mark Philip Draper. 256777072261. Ntinda Bukoto:Kira Road.0.340235,32.588791 . FTTH_40_M_O | Ntinda (Bukoto) |  | Chrif |  |  |  | 1593070.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-30 | 2023-02-06 | 2023-02-08 | 2023-02-19 | 20 | 13 |  |  |  | PAC Done
| HOSEA LUWHANO. 256779639590. Kisaasi:Bahai Road.0.376551,32.596737 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 1828380 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-17 | 2023-02-19 | 2023-02-18 | 18 | 1 |  |  |  | PAC Done
| null null. 256778677672. Rubaga:Wakaliga Road.0.304038,32.546226 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2117620.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-18 | 2023-02-16 | 2023-02-18 | 2023-02-20 | 33 | 4 | Customer asked to be commissioned on 2oth Feb |  |  | PAC Done
| null null. 256771090439. Ggaba:Ggaba ByPass Road.0.264685,32.63085 . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2889032.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-10 | 2023-01-14 | 2023-01-16 | 2023-02-20 | 41 | 37 |  |  |  | PAC Done
| null null. 256772425049/MTNFTTO70256664. Kisaasi:Kulambiro.0.376427,32.605312 . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 2889032.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-01-31 | 2023-02-18 | 2023-02-20 | 2023-02-20 | 20 | 2 |  |  |  | PAC Done
| null null. 256782750727. Bweyogerere:Kirinya Bukasa Road.0.327529,32.675953 . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 3022293.4 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-08 | 2023-02-17 | 2023-02-19 | 2023-02-20 | 12 | 3 |  |  |  | PAC Done
| null null. 256786135354. Ggaba:Ggaba Road.0.241567,32.619797 . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2,264,732 | Office Internet | 0 | Done | Office internet (on air) | 2023-02-06 | 2023-02-17 | 2023-02-19 | 2023-02-21 | 15 | 4 |  |  |  | PAC Done
| null null.256771346500.natete.0.297202,32.52667.FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2,228,016.10 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-21 | 1 | 1 |  |  |  | PAC Done
| IBRAHIM MOHAMED FARAH. 256776501681. Kololo:Mawanda Road.0.34028,32.573756 . FTTH_20_M_O | Kololo |  | Selmer |  |  |  | 1321349.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-23 | 2023-02-09 | 2023-02-11 | 2023-02-20 | 28 | 11 | Commissioning scheduled tomorrow at 2pm |  |  | PAC Done
| null null. 256770815869. Muyenga:Tank Hill Road.0.350122,32.60839 . FTTH_40_M_O | Muyenga |  | Rontech |  |  |  | 4176341 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-09 | 2023-02-13 | 2023-02-15 | 2023-02-21 | 12 | 8 | Customer to communicate when ready for commissioning | Compact Backfill on Pole 4 |  | PAC Done
| null null. 256782270353. Lubowa. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 2257804 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-21 | 4 | 4 |  |  |  | PAC Done
| null null. 256787068413. ggaba road kansanga. FTTH_40_M_O | Ggaba |  | Rontech |  |  |  | 3227602 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-18 | 2023-02-18 | 2023-02-20 | 2023-02-22 | 4 | 4 |  |  |  | PAC Done
| null null. 256782830470. Ntinda Rise. FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2181827.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-16 | 2023-02-16 | 2023-02-18 | 2023-02-22 | 6 | 6 |  |  |  | PAC Done
| null null. 256786353360. Lubowa. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 1685004 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-20 | 3 | 3 |  |  |  | PAC Done
| null null. 256778411934. rubaga. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2117021.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-22 | 5 | 5 |  |  |  | PAC Done
| null null. 256771346500. natete. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2228016 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-21 | 1 | 1 |  |  |  | PAC Done
| null null. 256774077569. kisenyi. FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 3916429 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-22 | 5 | 5 |  |  |  | PAC Done
| null null. 256770353685. Bulabila Road,Najjera 1, Kira. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 4905916 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-18 | 2023-02-18 | 2023-02-20 | 2023-02-22 | 4 | 4 |  |  |  | PAC Done
| null null. 256780857806. church of uganda kisugu. FTTH_40_M_O | Namuwongo |  | Rontech |  |  |  | 3948802 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2 | 2 |  |  |  | PAC Done
| null null. 256777018666. namugongo Road. FTTH_40_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 3489885.4 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2 | 2 |  |  |  | PAC Done
| null null. 256774334970. nabisunsa close. FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 4003704.3 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2 | 2 |  |  |  | PAC Done
| null null. 256782576710. Bugolobi:Mbuya Road. FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 4250569.4 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2 | 2 |  |  |  | PAC Done
| null null. 256779145548. Nabisunsa Close. FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 4003704.3 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-22 | 2 | 2 |  |  |  | PAC Done
| null null. 256789745319. lungujja. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4682697 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-21 | 1 | 1 |  |  |  | PAC Done
| null null.256789745319.Lungujja.0.309657,32.540489.FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4682697.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-21 | 1 | 1 |  |  |  | PAC Done
| null null. 256771135914. Rubaga:Lungujja.0.306122,32.5476 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2120320.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-11 | 2023-02-21 | 2023-02-23 | 2023-02-21 | 41 | 0 |  |  |  | PAC Done
| Shamir Hussein. 256772200101. Naguru drive. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2314972.55 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-18 | 2023-02-22 | 2023-02-24 | 2023-02-24 | 6 | 2 |  | Poor slag mgt |  | PAC Done
| null null. 256776150104. Kampala Uganda. . FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 2373567 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-21 | 2023-02-21 | 2023-02-23 | 2023-02-22 | 1 | 1 |  |  |  | PAC Done
| null null. 256783357571. Ntinda Bukoto:Kira Road.0.341986,0.341986 . FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2309961.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-31 | 2023-02-16 | 2023-02-18 | 2023-02-22 | 22 | 6 |  |  |  | PAC Done
| HADADI DUMBA. 256773204694. Ggaba:Salaama Road.0.251705,32.607439 . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 3549634 | Office Internet | 0 | Done | Office Internet (on air) | 2022-09-14 | 2023-02-20 | 2023-02-22 | 2023-02-23 | 162 | 3 |  | Open Manhole |  | PAC Done
| null null. 256789976919. Mbarara:Boma Road.0.612846,30.659405 . FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 2259957 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-13 | 2023-02-23 | 2023-02-25 | 2023-02-23 | 10 | 0 |  |  |  | PAC Done
| null null. 256785145399. Kololo. . FTTH_40_M_O | Kololo |  | Selmer |  |  |  | 2141608 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-22 | 2023-02-22 | 2023-02-24 | 2023-02-24 | 2 | 2 |  |  |  | PAC Done
| null null. 256762917689. Makindye:Lukuli Road.0.257653,32.61776 . FTTH_20_M_O | Makindye |  | Rontech |  |  |  | 2514904 | Office Internet | 5 | Done | Office Internet (on air) | 2023-01-25 | 2023-01-26 | 2023-01-28 | 2023-02-25 | 31 | 25 | On Hold due to PO/Contact is off |  |  | PAC Done
| null null. 256784444189. Kigo:Kigo Road.0.353996,32.607838 . FTTH_20_M_O | Kigo |  | Chrif |  |  |  | 4,472,139.60 | Office Internet | 10 | Done | Office Internet (on air) | 2023-02-05 | 2023-02-09 | 2023-02-11 | 2023-02-22 | 17 | 3 | Physical installations done, traffic routing ongoing |  |  | PAC Done
| null null. 256763039997. Ntinda Bukoto:Kira Road.0.343117,32.592262 . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 1989463.9 | Office Internet |  | Done | Office Internet (on air) | 2023-02-08 | 2023-02-14 | 2023-02-16 | 2023-02-25 | 17 | 11 | Requested to be commissioned on Wednesday 22 |  |  | PAC Done
| null null. 256786755352. William street. FTTH_20_M_O | Old park |  | Chrif |  |  |  | 4905916 | Office Internet | 3 | Done | Office Internet (on air) | 2023-02-16 | 2023-02-16 | 2023-02-18 | 2023-02-24 | 8 | 5 | Traffic routing ongoing |  |  | PAC Done
| null null. 256779082166. Nakasero Hill:Mackinnon Road.0.321513,32.585279 . FTTH_40_M_O | Nakasero Hill |  | Chrif |  |  |  | 2176080.6 | Office Internet | 3 | Done | Office Internet (on air) | 2023-01-23 | 2023-02-17 | 2023-02-19 | 2023-02-26 | 34 | 6 |  |  |  | PAC Done
| + |  |  | ATX |  |  |  | 3874102.1 | Office Internet |  | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-27 | 10 | 10 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256771294084. mabirizi complex. FTTH_20_M_O | Old park |  | Chrif |  |  |  | 1577080.6 | Office Internet | 2 | Done | Office Internet (on air) | 2023-02-21 | 2023-02-21 | 2023-02-23 | 2023-02-24 | 3 | 1 |  |  |  | PAC Done
| null null. 256786325070. Johnson street. FTTH_40_M_O | Kampala downtown |  | Chrif |  |  |  | 2751284.9 | Office Internet | 1 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-26 | 9 | 8 |  |  |  | PAC Done
| null null. 256776323501. Entebbe, church road. FTTH_40_M_O | Entebbe |  | ATX |  |  |  | 1388889 | Office Internet | 5 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-17 | 2023-02-19 | 2023-02-24 | 7 | 2 | client requested we finalize her installation tomorrow - as they were under Audit |  |  | PAC Done
| null null. 256782311048. Gulu, uganda. FTTH_40_M_O | Gulu |  | ATX |  |  |  | 3874102.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-27 | 7 | 7 |  |  |  | PAC Done
| null null. 256773036999. lira. FTTH_20_M_O | Lira |  | ATX |  |  |  | 3387786.2667 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-24 | 4 | 4 | MTN FTTO Installation -NULL NULL-0789008372 & NULL NULL-0773036999 & NULL NULL-0763299266 |  |  | PAC Done
| null null. 256763215218. kololo. . FTTH_20_M_O | Kololo |  | Selmer |  |  |  | 2,126,368.00 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-18 | 2023-02-22 | 2023-02-24 | 2023-02-27 | 9 | 5 |  |  |  | PAC Done
| null null. 256763139822. plot 23A Akii Bua Road Nakasero. . FTTH_40_M_O | Nakasero Hill |  | Chrif |  |  |  | 2374065.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-02-25 | 5 | 3 |  |  |  | PAC Done
| null null. 256786099932. rubaga rd. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2538802.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-21 | 2023-02-22 | 2023-02-24 | 2023-02-27 | 6 | 5 |  |  |  | PAC Done
| null null. 256774679190. green lounge muyenga. . FTTH_40_M_O | Muyenga |  | Rontech |  |  |  | 2771604 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-21 | 2023-02-21 | 2023-02-23 | 2023-02-27 | 6 | 6 |  |  |  | PAC Done
| null null. 256788503503. bugolobi. . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 3311011.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-22 | 2023-02-22 | 2023-02-24 | 2023-02-25 | 3 | 3 |  |  |  | PAC Done
| null null. 256785887793. Bukoto. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 1773106.2 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-25 | 2023-02-27 | 2023-02-25 | 5 | 0 |  |  |  | PAC Done
| null null. 256771485276. kiwatule. . FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Seagate |  |  |  | 5004512 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-25 | 2023-02-27 | 2023-02-25 | 5 | 0 |  |  |  | PAC Done
| null null. 256776114108. Ggaba bye pass. . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 3077652 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-23 | 2023-02-25 | 2023-02-28 | 8 | 5 |  |  |  | PAC Done
| SHANON RWOTHONGEYO. 256775571594. kireka. . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 2464856.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-23 | 2023-02-25 | 2023-02-27 | 7 | 4 |  |  |  | PAC Done
| ull null. 256775195865. Kampala Uganda. 0.322147,32.621784. FTTH_20_M | Bugolobi |  | Chrif |  |  |  | 1936780.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-11 | 2023-02-21 | 2023-02-23 | 2023-02-24 | 13 | 3 |  |  |  | PAC Done
| null null. 256775882687. superlife wandegeye Annex s.a. . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 1,736,368.00 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-24 | 2023-02-26 | 2023-02-28 | 11 | 4 |  |  |  | PAC Done
| null null. 256781575470. mutundwe. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4080503.35 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-02-25 | 5 | 3 |  |  |  | PAC Done
| null null. 256762450143. namugongo. . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 1821606.2 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-22 | 2023-02-23 | 2023-02-25 | 2023-02-25 | 3 | 2 |  |  |  | PAC Done
| null null. 256784590580. naguru drive. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 4844973.9 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-23 | 2023-02-22 | 2023-02-24 | 2023-02-24 | 1 | 2 |  |  |  | PAC Done
| null null. 256781506471. Namugongo. . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 5031536 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-23 | 2023-02-23 | 2023-02-25 | 2023-02-25 | 2 | 2 |  |  |  | PAC DONE
| null null. 256789708720. Kampala Uganda. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2117021.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-24 | 2023-02-22 | 2023-02-24 | 2023-02-25 | 1 | 3 |  |  |  | PAC Done
| Dennis Mujambere. 256782373780. Makerere:Sir Apollo Kaggwa Road.0.359885,32.531302 . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 1877448 | Office Internet | 0 | Done | Office Internet (on air) | 2022-11-04 | 2023-02-07 | 2023-02-09 | 2023-02-27 | 115 | 20 | High BOQ |  |  | PAC Done
| null null. 256783819004. lungujja. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4,502,332.10 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-24 | 2023-02-23 | 2023-02-25 | 2023-02-28 | 4 | 5 |  |  |  | PAC Done
| null null. 256777814226. -0.60716,30.654502.FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 4093961 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-24 | 2023-02-24 | 2023-02-26 | 2023-02-25 | 1 | 1 |  |  |  | PAC Done
| null null. 256774228077. Kololo:Lugogo Bypass.0.326149,32.604008 . FTTH_40_M_O | Kololo |  | Selmer |  |  |  | 1912448 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-03 | 2023-02-24 | 2023-02-26 | 2023-02-25 | 22 | 1 |  |  |  | PAC Done
| CONRAD WANDERA. 256774002847. Entebbe:Berkeley Road.0.068788,32.47556 . FTTH_20_M_O | Entebbe |  | Enetworks |  |  |  | 1628691.8 | Office Internet | 0 | Done | Office Internet (on air) | 2022-09-23 | 2022-09-23 | 2022-09-25 | 2023-02-27 | 157 | 157 | Tric-padlock on Mutungo Site |  |  | PAC Done
| null null. 256772418778. Kampala Upper CBD:.0.353931,32.607794 . FTTH_40_M_O | Ntinda (Bukoto) |  | Chrif |  |  |  | 3802028.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-27 | 2023-02-06 | 2023-02-08 | 2023-02-28 | 32 | 22 | All physical installations & Traffic Routing Done, promised to call when ready for commissioning. |  |  | PAC Done
| null null. 256782937993. kikoni. FTTH_20_M_O | Makerere |  | ATX |  |  |  | 2161419 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-02-28 | 1 | 1 |  |  |  | PAC Done
| VIVIAN NAKIWU. 256782079086. Makerere:Bombo Road.0.360588,32.530733 . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 1879985.44 | Office Internet | 0 | Done | Office Internet (on air) | 2022-10-25 | 2022-11-01 | 2022-11-03 | 2023-02-27 | 125 | 118 | High BOQ |  |  | PAC Done
March | Abdullahi Muhammed. 256786839268. Rubaga:Musajja Alumbwa Road.0.30461,32.568913 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 3,523,204.60 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-02 | 2023-02-24 | 2023-02-26 | 2023-03-01 | 27 | 5 |  |  |  | PAC DONE
| null null. 256770480442.7th Street industrial area. 0.318811,32.595311. FTTH_20_M_O | Kololo |  | Chrif |  |  |  | 4396920 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-02 | 3 | 3 | Survey done, pole erection and cable hauling commencing 28/02/23
| HONG XU. 256782407178. Media plaza. FTTH_40_M_O | Kololo |  | Enetworks |  |  |  | 1624109.4 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-27 | 2023-02-20 | 2023-02-22 | 2023-03-01 | 2 | 9
| null null. 256762340959. 7 uringi cres road entebbe. FTTH_20_M_O | Entebbe |  | ATX |  |  |  | 3183124 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-27 | 2023-02-27 | 2023-03-01 | 2023-03-01 | 2 | 2 |  |  |  | PAC DONE
| null null. 256762398870. bweyogerere. . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 1670187 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-28 | 2023-03-02 | 2023-03-04 | 2023-03-02 | 2 | 0
| null null. 256773061636. mbarara. . FTTH_40_M_O | Mbarara |  | Rontech |  |  |  | 4205244 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-01 | 2023-03-02 | 2023-03-04 | 2023-03-02 | 1 | 0
| null null. 256784140177. seeta. . FTTH_20_M_O | Seeta |  | Enetworks |  |  |  | 3967465.9 | Office Internet | 3 | Done | Office Internet (on air) | 2023-02-22 | 2023-02-22 | 2023-02-24 | 2023-03-02 | 8 | 5
| null null. 256776752279. lubaga Red cross, Kampala. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2781602 | Office Internet | 7 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-23 | 2023-02-25 | 2023-03-02 | 13 | 0 |  |  |  | PAC DONE
| null null. 256784345865. kira road. . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Seagate |  |  |  | 5154096.5 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-17 | 2023-02-23 | 2023-02-25 | 2023-03-02 | 13 | 7 |  |  |  | PAC DONE
| null null. 256781789194. rubaga. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 3001760 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-25 | 2023-02-27 | 2023-03-01 | 2023-03-02 | 5 | 3 |  |  |  | PAC DONE
| null null. 256789387325. kenrock hotel muyenga. FTTH_40_M_O | Muyenga |  | Rontech |  |  |  | 3463525 | Office Internet | 5 | Done | Office Internet (on air) | 2023-02-28 | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2 | -3
| null null. 256789594886. lungujja. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2139220 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-25 | 2023-03-01 | 2023-03-03 | 2023-03-02 | 5 | 1 |  |  |  | PAC Done
| null null. 256778284814. Wandegeya. . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 1337348 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-28 | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2 | 2 |  |  |  | PAC Done
| null null. 256783099654. Africourts buganda road. . FTTH_20_M_O | Nakasero Hill |  | Enetworks |  |  |  | 1,716,264.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-28 | 2023-02-28 | 2023-03-02 | 2023-03-02 | 2 | 2 |  |  |  | PAC Done
| null null. 256776997696. Wandegaya. . FTTH_20_M_O | Makerere |  | ATX |  |  |  | 2604563 | Office Internet | 2 | Done | Office Internet (on air) | 2023-03-01 | 2023-03-01 | 2023-03-03 | 2023-03-02 | 1 | -1 | WAS PENDING ACCESS WE SUBMITTED THE LETTER WAITING FOR THEIR RESPONSE(BUILDING MANAGEMENT) |  |  | PAC DONE
| null null. 256770700618. lubaga. . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 4497084 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-25 | 2023-03-01 | 2023-03-03 | 2023-03-02 | 5 | 1 |  |  |  | PAC DONE
| null null. 256760713742. weraga road. . FTTH_20_M_O | Rubaga |  | Rontech |  |  |  | 2454379 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-01 | 2023-03-01 | 2023-03-03 | 2023-03-02 | 1 | 1 |  |  |  | PAC Done
| null null. 256772647989. bugolobi. . FTTH_40_M_O | Bugolobi |  | Chrif |  |  |  | 1676800.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-01 | 2023-03-01 | 2023-03-03 | 2023-03-02 | 1 | 1
| MAHAT ABDI WARSAME. 256787866977. kitakule road Namirembe. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 3519746 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-01 | 2023-03-02 | 2023-03-04 | 2023-03-02 | 1 | 0 |  |  |  | PAC DONE
| null null. 256782158249. mbuya. . FTTH_40_M_O | Bugolobi |  | Enetworks |  |  |  | 2694293.4 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-01 | 2023-03-02 | 2023-03-04 | 2023-03-02 | 1 | 0
| null null. 256775601512. Naguru. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2674195.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-02 | 0 | 0
| null null. 256777084306. Luwum Street. . FTTH_20_M_O | Old park |  | Enetworks |  |  |  | 1960477.4 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-03 | 1 | 1
| null null. 256775446466. ntinda. . FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 4442627 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-03 | 2023-03-02 | 2023-03-04 | 2023-03-04 | 1 | 2
| null null. 256778050136. Ntinda (Kyambogo - Min Village):Kayodo Road.0.353914,32.607809 . FTTH_20_M_O | Ntinda (Kyambogo - Min Village) |  | Enetworks |  |  |  | 3924301 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-08 | 2023-02-15 | 2023-02-17 | 2023-02-20 | 12 | 5 |  |  |  | PAC Done
| null null. 256776744128. Kololo:Kololo Hill Drive.0.337856,32.588183 . FTTH_20_M_O | Kololo |  | Selmer |  |  |  | 1 ,748,208.00 | Office Internet | 5 | Done | Office Internet (on air) | 2023-02-14 | 2023-02-17 | 2023-02-19 | 2023-02-24 | 10 | 2 | Done- Commissioning ongoing, *Service Activation scheduled on 27/2/2023 |  |  | PAC Done
| null null. 256776700696. ntinda. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2813856.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-21 | 2023-02-23 | 2023-02-24 | 4 | 3 | High BOQ |  |  | PAC Done
| null null. 256785474782. Buganda road. . FTTH_20_M_O | Nakasero Hill |  | Chrif |  |  |  | 2429039.1 | Office Internet | 10 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-22 | 2023-02-24 | 2023-03-04 | 12 | 0 | After confirming the appointment to haul the cable, on reaching the client's promises, he decided that instead of installing at Nankeera building, we install at Prime complex building and that should be monday after consulting from his partner. handed over to Seagate
| AMUZA DONGO. 256788346788. Ntinda (Kiwatule - Naalya):Clovis Road.0.353987,32.607847 . FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Seagate |  |  |  | 2214590 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-26 | 2023-02-20 | 2023-02-22 | 2023-03-01 | 34 | 9 | Done - requested to be commissioned after 10 days |  |  | PAC Done
| null null. 256772567273. down town. . FTTH_20_M_O | Kampala downtown |  | Enetworks |  |  |  | 3634787.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-21 | 2023-02-21 | 2023-02-23 | 2023-03-01 | 8 | 8
| null null. 256773694160. nyanama. . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 2705386 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-20 | 2023-02-25 | 2023-02-27 | 2023-02-28 | 8 | 3 |  |  |  | PAC Done
| null null. 256785319797. bukerere road. . FTTH_20_M_O | Seeta |  | Enetworks |  |  |  | 4947195.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-02 | 0 | 0
| null null. 256772309375. mbarara. . FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 4842729 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-02 | 2023-03-01 | 2023-03-03 | 2023-03-02 | 0 | 1
| null null. 256783456348. Nalukolongo. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4197788.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-03 | 2023-03-03 | 2023-03-05 | 2023-03-03 | 0 | 0 |  |  |  | PAC DONE
| DFCU - MATHIAS KATAMBA. 256786312998. BUWAATE.0,0 . FTTH_40 | Buwate |  | Seagate |  |  |  | 0 | Office Internet ( Postpaid) | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-07 | 2023-03-09 | 2023-03-07 | 0 | 0 |  |  |  | PAC DONE
| null null 256772489720. mbarara. -0.60716, 30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 2796637 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-03 | 2023-03-04 | 2023-03-06 | 2023-03-04 | 1 | 0
| Megalo Africa ltd 256761248557. Ggaba:Ggaba Road. 0.288009,32.607271. FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2095046 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-24 | 2023-03-04 | 2023-03-06 | 2023-03-04 | 8 | 0
| Null 256776581995. Rubaga, Kampala.0.308372,32.562824. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4072134 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-03 | 2023-03-04 | 2023-03-06 | 2023-03-04 | 1 | 0 |  | Replace Cassette with Joint box |  | PAC Done
| Null null .256774541065. wandegeya Uganda. 0.326309,32.573924. FTTH_40_M_O | Makerere |  | ATX |  |  |  | 2139220.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-23 | 2023-03-08 | 2023-03-10 | 2023-03-08 | 13 | 0 | ROW |  |  | PAC Done
| null.nyll. 256392548491. mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 2644169 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-06 | 2023-03-06 | 2023-03-08 | 2023-03-06 | 0 | 0
| null null. 256776574064. Soroti:Soroti - Moroto Road.1.721037,33.615654 . FTTH_20_M_O | Soroti |  | ATX |  |  |  | 5,035,539.80 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-21 | 2023-02-27 | 2023-03-01 | 2023-03-07 | 14 | 8 |  |  |  | PAC Done
| null null. 256772720630. Bugolobi:Luthuli Rise.0.319053,32.62233 . FTTH_20_M_O | Bugolobi |  | Chrif |  |  |  | 1996882.2 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-02 | 2023-03-06 | 2023-03-08 | 2023-03-07 | 33 | 1
| null null. 256786445704. nakulabye Kampala. . FTTH_20_M_O | Makerere |  | ATX |  |  |  | 2728479.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-09 | 2023-03-11 | 2023-03-09 | 2 | 0 |  |  |  | PAC DONE
| JUKAS CONSTRUCTION LIMITED. 256773099231. KOLOLO. . FTTH_20 | Kololo |  | Seagate |  |  |  | 1882804.6667 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-10 | 1 | 1 |  |  |  | PAC Done
| JUKAS CONSTRUSTION LIMITED. 256781054833. Kololo. . FTTH_20 | Kololo |  | Seagate |  |  |  | 1882804.6667 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-10 | 1 | 1 |  |  |  | PAC Done
| JUKAS CONSTRUCTION LIMITED. 256786684731. KOLOLO. . FTTH_20 | Kololo |  | Seagate |  |  |  | 1882804.6667 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-10 | 1 | 1 |  |  |  | PAC Done
| null null. 256777779712. industrial area 5th street. . FTTH_20_M_O | Namuwongo |  | Chrif |  |  |  | 4054378.4 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-06 | 2023-03-06 | 2023-03-08 | 2023-03-09 | 3 | 3
| null null. 256778927302. industrial are. . FTTH_20_M_O | Namuwongo |  | Chrif |  |  |  | 4992880.6 | Office Internet | 5 | Done | Office Internet (on air) | 2023-03-02 | 2023-03-02 | 2023-03-04 | 2023-03-11 | 9 | 4 | Blocked Ducts and manholes - To introduce aerial
| null null. 256788214595. Munyonyo. . FTTH_40_M_O | Ggaba |  | Rontech |  |  |  | 3601437 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-03 | 2023-03-03 | 2023-03-05 | 2023-03-11 | 8 | 8
| null null. 256781955989. Mbale,Uganda. . FTTH_20_M_O | Mbale |  | Rontech |  |  |  | 3068275 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-03 | 2023-02-05 | 2023-02-07 | 2023-03-12 | 9 | 35
| FINCA UGANDA – JAMES ONYUTTA MD. 256780139300. BUWAATE.0,0 . FTTH_20 | Buwate |  | Seagate |  |  |  | 0 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-03-23 | 0 | 0 |  |  |  | PAC DONE
| null null. 256777237118. spring road. . FTTH_40_M_O | Bugolobi |  | Chrif |  |  |  | 2614704.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-06 | 2023-03-07 | 2023-03-09 | 2023-03-11 | 5 | 4
| null null. 256771437717. luwum street. . FTTH_20_M_O | Old park |  | Enetworks |  |  |  | 4197739.5 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-14 | 5 | 5
| null null. 256763342724. Lweza. . FTTH_20_M_O | Kajjansi |  | Chrif |  |  |  | 4993174.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-08 | 2023-03-08 | 2023-03-10 | 2023-03-14 | 6 | 6
| YASIN SSESOLO. 256786988505. kabalagala. . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 3040203 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-08 | 2023-03-10 | 2023-03-16 | 9 | 8
| null null. 256763424469. muyenga bukasa police. . FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 4082344 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-08 | 2023-03-10 | 2023-03-14 | 7 | 6
| null null. 256786004709. muyenga. . FTTH_20_M_O | Muyenga |  | ROntech |  |  |  | 4082344 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-06 | 2023-03-06 | 2023-03-08 | 2023-03-14 | 8 | 8
| null null. 256772699808. bugolobi. . FTTH_20_M_O | Bugolobi |  | Chrif |  |  |  | 2256654.6 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-15 | 6 | 6 | On hold, client's premises/Office under construction
| ATC Marketing U Ltd. 256773110044. Luzira, Turcker Crescent. . FTTH_20 | Luzira |  | Enetworks |  |  |  | 3,423,759.0 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-15 | 6 | 6
| null null. 256776502175. Nsambya. . FTTH_20_M_O | Nsambya |  | ATX |  |  |  | 2,070,522.10 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-11 | 1 | 1 |  |  |  | PAC Done
| null null. 256786853057. KSK green campus. . FTTH_20_M_O | Nakasero Hill |  | Enetworks |  |  |  | 2805419.8 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-16 | 6 | 6
| null null. 256786409770. wonder world amusement park. . FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2,370,904 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-16 | 6 | 6
| LYDIA APIO. 256775085520. bwebajja. . FTTH_20_M_O | Bwebajja |  | Chrif |  |  |  | 2783665.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-15 | 5 | 5
| ERIC MUGADDE. 256788282082. bugolobi. . FTTH_20_M_O | Bugolobi |  | Chrif |  |  |  | 2246654.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-11 | 1 | 1
| JOEL MUWONGE. 256780466377. Kireka. . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 2,986,512.1 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-13 | 3 | 3
| DANIEL SENKUNGU. 256786667431. mawanda road. . FTTH_20_M_O | Makerere |  | Enetworks |  |  |  | 3,850,118.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-13 | 3 | 3
| SALIM KATSIGAZI. 256772835859. ntinda industrial area. . FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 3,730,447.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-11 | 1 | 1
| Rosette Tyba. 256787054858. Kireka opp police. . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 2517759 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-13 | 4 | 4
| MAKUMBI NASASIRA. 256786619175. Wandegeya. . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 1712968 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-13 | 2023-03-13 | 2023-03-15 | 2023-03-15 | 2 | 2
| null null. 256788768106. Najjanankumbi:Kampala Entebbe Road.0.286989,32.569797 . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 2099173 | Office Internet | 0 | Done | Office Internet (on air) | 2023-01-19 | 2023-03-06 | 2023-03-08 | 2023-03-13 | 53 | 7
| null null. 256781649813. Fort Portal:Bwamba Road.0.657755, 30.268439. FTTH_20_M_O | Fort portal |  | Rontech |  |  |  | 2874271 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-08 | 2023-03-08 | 2023-03-10 | 2023-03-10 | 2 | 2
| null null. 256763566758. Mugwanya Rd, Lubaga Division. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2722165 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-13 | 2023-03-13 | 2023-03-15 | 2023-03-15 | 2 | 2 |  |  |  | PAC DONE
| null null. 256772558032. fortpotal. . FTTH_40_M_O | Fort portal |  | Rontech |  |  |  | 3750393 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-13 | 2023-03-13 | 2023-03-15 | 2023-03-16 | 3 | 3
| null null. 256785160292. Ambassador House. . FTTH_20_M_O | Kampala downtown |  | Enetworks |  |  |  | 2097167 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-14 | 2023-03-14 | 2023-03-16 | 2023-03-15 | 1 | 1
| null null. 256777502639. rumee towers lumumba avenue. . FTTH_20_M_O | Nakasero Hill |  | Enetworks |  |  |  | 1606264.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-14 | 2023-03-14 | 2023-03-16 | 2023-03-16 | 2 | 2
| null null. 256772387031. mbarara. . FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 3047040 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-14 | 2023-03-14 | 2023-03-16 | 2023-03-14 | 0 | 0
| null null. 256763580406. Nsambya, kampala. . FTTH_20_M_O | Nsambya |  | ATX |  |  |  | 2181517 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-14 | 2023-03-14 | 2023-03-16 | 2023-03-16 | 2 | 2 |  |  |  | PAC DONE
| Kawenja Livingstone. 256772402519. Makindye kizungu road. . FTTH_20_M_O | Makindye |  | ATX |  |  |  | 2070522 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-16 | 1 | 1 |  |  |  | PAC DONE
| Null Null 256786619175 |  |  | Selmer |  |  |  | 1712968 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-13 | 2023-03-15 | 2023-03-15 | 8 | 2
| ATC Marketing U Ltd. 256788552755. Mugalu road, Kyanja. 0.317192,32.57996.FTTH_10_M | Kisaasi (Kyanja - Kulambiro) |  | ATX |  |  |  | 1858374.6 | Office Internet ( Postpaid) | 0 | Done | Office Internet (on air) | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-09 | 0 | 0 |  |  |  | PAC Done
| null null. 256774239024. kazo. . FTTH_20_M_O | Kawempe |  | Chrif |  |  |  | 2448464 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-16 | 7 | 7 | Mobilizing to start Civil works
| PAULINE NAMPEBWA. 256770902110. bombo road. . FTTH_40_M_O | Makerere |  | Selmer |  |  |  | 1667608 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-07 | 2023-03-09 | 2023-03-17 | 10 | 10 | Mobilizing to start Civil works |  |  | PAC Done
| null null. 256776299662. rubaga rd. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 4241915 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-16 | 2023-03-16 | 2023-03-18 | 2023-03-17 | 1 | 1 |  |  |  | PAC Done
| null null 256781242153 Mbarara -0.60716, 30.654502 FTTH_40_M_O | Mbarara |  | Rontech |  |  |  | 4828884 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-13 | 2023-03-13 | 2023-03-15 | 2023-03-14 | 1 | 1
| null null. 256772358509. lubugumu. . FTTH_20_M_O | Kigo |  | Rontech |  |  |  | 4046909 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-18 | 9 | 9
| null null. 256763492131. kabalagala. . FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 3104598 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-09 | 2023-03-09 | 2023-03-11 | 2023-03-20 | 11 | 11 | Router attachment with HLS team.
| CHRISTINE NUWASIIME. 256778394524. computer training and printing s. . FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 3536738 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-18 | 8 | 8 | Contact not available |  |  | PAC DONE
| null null. 256788982854. bunga. . FTTH_40_M_O | Ggaba |  | Rontech |  |  |  | 4746599 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-20 | 10 | 10
| null null. 256772441631. communication house. . FTTH_40_M_O | Nakasero Hill |  | Enetworks |  |  |  | 1,762,480.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-16 | 2023-03-16 | 2023-03-18 | 2023-03-20 | 4 | 4
| FIONA AKITE. 256783466000. Lira, Uganda. . FTTH_20_M_O | Lira |  | ATX |  |  |  | 4109343 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-19 | 4 | 4 |  |  |  | PAC Done
| null null. 256763231326. muyenga. . FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 2717267 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-18 | 3 | 3
| null null. 256777213952. Kirinya Bukasa. . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  |  | 4277472.3 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-18 | 3 | 3
| ABDIFATAH FARAH. 256783649174. Kisenyi. 0.306657,32.572935.FTTH_20_M_O | Ndeeba |  | ATX |  |  |  | 2052487.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-07 | 2023-03-14 | 2023-03-16 | 2023-03-15 | 8 | 1 |  |  |  | PAC Done
| null null. 256394507862. nkumba university. . FTTH_20_M_O | Entebbe |  | Chrif |  |  |  | 1726879.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-17 | 2023-03-17 | 2023-03-19 | 2023-03-19 | 2 | 2
| ALOYSIOUS MUGISHA ,256772362071 mbarara -0.60716, 30.654502 FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 3415191 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-18 | 2023-03-18 | 2023-03-20 | 2023-03-19 | 1 | 1
| null null. 256776442257. beijing clinic kisugu. . FTTH_20_M_O | Namuwongo |  | Rontech |  |  |  | 2641258 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-17 | 2023-03-17 | 2023-03-19 | 2023-03-21 | 4 | 4
| null null.256784970836 Entebbe. . FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 5306416 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-10 | 2023-03-11 | 2023-03-13 | 2023-03-20 | 10 | 9
| null null .256772816126 muarik FTTH_20_M_O | Gayaza |  | Seagate |  |  |  | 3928034.0667 | Office Internet | 0 | Done | Office Internet (on air) | 2023-02-25 | 2023-03-13 | 2023-03-15 | 2023-03-21 | 24 | 8 |  |  |  | PAC DONE
| null null 256788602150 FTTH_40_M_O |  |  | ATX |  |  |  | 1635669.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-21 | 1 | 1 |  |  |  | PAC Done
| null null. 256776273456. world food programme nalukulongo. . FTTH_40_M_O | Rubaga |  | Rontech |  |  |  | 3651672 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-17 | 2023-03-17 | 2023-03-19 | 2023-03-21 | 4 | 4
| null null. 256787472442. Lira, Uganda. . FTTH_40_M_O | Lira |  | ATX |  |  |  | 1635669.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-17 | 2023-03-18 | 2023-03-20 | 2023-03-21 | 4 | 3 |  |  |  | PAC Done
| RAJESH BABU KRISHNAN KUTTY KAPPIL RAJESH. 256763649073. naguru. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 3274296.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-21 | 1 | 1
| null null 256763700242 null null |  |  | ATX |  |  |  | 1635669.6 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-21 | 1 | 1 |  |  |  | PAC Done
| null null.256774442413 Kitetika 0.386821,32.57797 FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Seagate |  |  |  | 2289683 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-21 | 1 | 1 |  |  |  | PAC Done
| CONNIE LUWANGWA. 256775627382. Bunamwaya Lubowa. . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 3696392 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-13 | 2023-03-13 | 2023-03-15 | 2023-03-22 | 9 | 9
| JUSTINE NAKIMULI. 256763643623. sunrise Nursery school. . FTTH_20_M_O | Makerere |  | ATX |  |  |  | 2265858 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-17 | 2023-03-17 | 2023-03-19 | 2023-03-22 | 5 | 5 |  |  |  | PAC Done
| null null. 256781173131. sseguku. . FTTH_40_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 4856938 | Office Internet | 0 | Done | Office Internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-22 | 7 | 7
| null null. 256783294738. kasubi tombs. . FTTH_40_M_O | Makerere |  | ATX |  |  |  | 4,641,526.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-11 | 2023-03-11 | 2023-03-13 | 2023-03-18 | 7 | 7 | 5 poles , Not Fesiable |  |  | PAC DONE
| KAFEERO ISAAC. 256772432314. Kitante close. . FTTH_40_M_O | Kololo |  | ROntech |  |  |  | 2393448.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-23 | 8 | 8
| null null. 772779041. Entebbe:Bugonga Road. 0.095128,32.506873.FTTH_20_M_O | Entebbe |  | Chrif |  |  |  | 2515599.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-07 | 2023-03-13 | 2023-03-15 | 2023-03-15 | 8 | 2
| ALOYSIUS MUBANGIZI. 256772786997. muarik. . FTTH_20_M_O | Gayaza |  | Seagate |  |  |  | 3928034.0667 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-19 | 2023-03-19 | 2023-03-21 | 2023-03-21 | 2 | 2 |  |  |  | PAC DONE
| null null. 256763358838. Lubowa. . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | ROntech |  |  |  | 3,530,574 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-18 | 2023-03-18 | 2023-03-20 | 2023-03-26 | 8 | 8
| MUHAMMAD MUGOYA. 256776537459. old kamapla. . FTTH_20_M_O |  |  | ATX |  |  |  | 2,030,044 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-18 | 2023-03-18 | 2023-03-20 | 2023-03-20 | 2 | 2 |  |  |  | PAC Done
| null null. 256772402891. Entebbe. . FTTH_20_M_O | Entebbe |  | Chrif |  |  |  | 724070.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-18 | 2023-03-18 | 2023-03-20 | 2023-03-25 | 7 | 7
| Catherine Namutebi. 256772519251. Kenjoy supermarket. . FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 2,827,122 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-17 | 2023-03-17 | 2023-03-19 | 2023-03-23 | 6 | 6
| SHARON NAMUSISI. 256779706862. shell busega. . FTTH_20_M_O | Rubaga |  | Chrif |  |  |  | 4539218.1 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-10 | 2023-03-10 | 2023-03-12 | 2023-03-22 | 12 | 12
| null null. 256787037642. kabalagala. . FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 2,523,097 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-21 | 2023-03-21 | 2023-03-23 | 2023-03-27 | 6 | 6
| null null. 256784387630. namugongo. . FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 4192081.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-24 | 4 | 4
| WILKEN PROPERTY SERVICES LIMITED. 256785316540. Najjanankumbi. . FTTH_40_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 3,380,574 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 | 2023-03-23 | 3 | 3
| null null. 256772087588. ntinda.0.350605,32.615769. FTTH_20_M_O | Ntinda (Bukoto) |  | Selmer |  |  |  | 0 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-27 | 5 | 5 |  |  |  | PAC Done
| null null. 256772828443. parliamentary avenue.0.318811,32.595311. FTTH_20_M_O | Kampala Upper CBD |  | Chrif |  |  |  | 2830025.3 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-25 | 3 | 3
| null null. 256772345564. lungujja.0.309657,32.540489. FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 2826265 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-23 | 1 | 1 |  |  |  | PAC Done
| ABUDALAZAKE KYAGURANYI. 256772298828. buziga konge catholic church.0.318811,32.595311. FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2,401,404 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-22 | 2023-03-23 | 2023-03-25 | 2023-03-25 | 3 | 2
| null null. 256779712829. lubowa.0.229468,32.564324. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 2,832,496 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-21 | 2023-03-21 | 2023-03-23 | 2023-03-27 | 6 | 6
| null null. 256772049111. Furniture city Bugolobi.0.321198,32.6127. FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 2,853,540.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-03-27 | 4 | 4
| null null. 256763355916. bugolobi.0.309722,32.625765. FTTH_40_M_O | Bugolobi |  | Chrif |  |  |  | 1780015.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-24 | 2023-03-24 | 2023-03-26 | 2023-03-25 | 1 | 1
| null null. 256762815089. 7th Street industrial area.0.318811,32.595311. FTTH_20_M_O | Namuwongo |  | Chrif |  |  |  | 1,548,672.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-03-26 | 3 | 3
| null null. 256771004706. mbarara uganda. -0.60716,30.654502.FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 3,781,247 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-19 | 2023-03-26 | 2023-03-28 | 2023-03-27 | 8 | 1
| null null. 785612173. kabalagala. 0.305899,32.591001. FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 3311501.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-03-27 | 4 | 4
| null null. 789911062. Nalukolongo. 0.291146,32.555658. FTTH_20_M_O | Rubaga |  | Chrif |  |  |  | 4,432,605.60 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-03-27 | 4 | 4
| null null. 788427771. Makindye. 0.272835,32.617492. FTTH_20_M_O | Makindye |  | Chrif |  |  |  | 3333615 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-24 | 2023-03-27 | 2023-03-29 | 2023-03-27 | 3 | 0
| Echotel at Amref office, opposite Lohana Academy.256788689797 | Rubaga |  | Enetworks |  |  |  | 4154945.8 | Office Internet ( Postpaid) | 0 | Done | Office Internet (Postpaid) on air | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-27 | 0 | 0
| null null. 785721916. Kyanja Ring Road. 0.388722,32.596013. FTTH_10_M | Kisaasi (Kyanja - Kulambiro) |  | Enetworks |  |  |  | 2,224,909.40 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-25 | 2023-03-25 | 2023-03-27 | 2023-03-27 | 2 | 2
| AYOREKIRWE AYO BITANGAAZA. 256394824613. Jinja road. . FTTH_20_M_O | Bugolobi |  | Enetworks |  |  |  | 4,488,507.2 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-03-31 | 16 | 16
| null null. 256775163846. muyenga Road.0.296898,32.615028. FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 3,097,695 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-03-28 | 5 | 5
| null null. 256763789098. busabala rd.0.29887,32.610041. FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2,111,033 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-03-28 | 6 | 6
| null null. 256782642882. namugongo.0.385062,32.647526. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 3713773.3333 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-25 | 2023-03-25 | 2023-03-27 | 2023-03-30 | 5 | 5
| null null. 256763693392. busabala Rd.0.29887,32.610041. FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2,438,969 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-22 | 2023-03-28 | 2023-03-30 | 2023-03-29 | 7 | 1
| null null. 256788427771. Makindye. 0.272835,32.617492. FTTH_20_M_O | Makindye |  | Chrif |  |  |  | 3333615 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-24 | 2023-03-27 | 2023-03-29 | 2023-03-27 | 3 | 0
| P P SHABBIR. 256778746153. tight Security ltd.0.318811,32.595311. FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2620211 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2 | 2
| Babirye Annet. 256785480402. bukoto street.0.350525,32.595242. FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2620211 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2 | 2
| Ssebbowa Sam Mwebe. 256772959925. kabusu.0.318811,32.595311. FTTH_20_M_O | Rubaga |  | Chrif |  |  |  | 976705.6 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-30 | 3 | 3
| null null. 256788640131. mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 2918947 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-28 | 1 | 1
| null null. 256787942086. Bunamwaya.0.264913,32.546466. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 4,938,096 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-31 | 4 | 4
| WYCLIFE ASIIMWE. 256781072978. 30 naguru drive, kampala, uganda.0.339087,32.606465. FTTH_40_M_O | Ntinda (Bukoto) |  | Enetworks |  |  |  | 2,043,546.20 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-29 | 2 | 2
| null null. 256775620086. da track.0.369426,32.651243. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks |  |  |  | 2,113,821.4 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-03-30 | 3 | 3
| ASHOK MURU KESHWALA. 256763891075. mbarara uganda.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 4374712 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-03-30 | 2 | 2
| null null. 256776067733. mbarara uganda.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 3,827,154 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-03-29 | 1 | 1
| null null. 256773256262. Kiwatule.0.365298,32.624919. FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Enetworks |  |  |  | 4315278.5 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-03-31 | 2 | 2
| YOSIA AHIMBISIBWE. 256772999718. mbarara uganda.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 2,739,571 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-03-31 | 3 | 3
| null null. 256772406508. king fahad plaza.0.318811,32.595311. FTTH_20_M_O | Kololo |  | Chrif |  |  |  | 1668447.4 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-25 | 2023-03-25 | 2023-03-27 | 2023-03-30 | 5 | 5
| null null. 256774014672. mbarara, Uganda.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  | 1742043 | 1960498 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-03-31 | 1 | 1
| null null. 256781201448. Kampala Uganda.0.309417, 32.54733. FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Enetworks | 3485105 | 517231 | 2970220 | 4002335.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-08 | 2023-03-10 | 2023-03-12 | 2023-04-03 | 26 | 24 | [5 empty] | 31
| null null. 256772896289. mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  | 2710863 | 2936371 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-03-31 | 2 | 2
| Kutegeka Wilson. 256772609113. Bukoto Street. . FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks |  |  | 2396000 | 2894783 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-21 | 2023-03-21 | 2023-03-23 | 2023-04-03 | 13 | 13 | [5 empty] | 10
| null null. 256787235702. Kampala Casino kimathu avenue.0.314549,32.583769. FTTH_40_M_O | Kampala Upper CBD |  | Chrif |  |  | 2223000 | 2524630.8 | Office Internet | 0 | Done | Office internet (on air) | 2023-03-20 | 2023-03-23 | 2023-03-25 | 2023-04-04 | 15 | 12 | [5 empty] | 8
| null null. 256772269809. Bunamwaya.0.264913,32.546466. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 3,611,623 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-21 | 2023-03-25 | 2023-03-27 | 2023-04-02 | 12 | 8 | [5 empty] | 7
| null null. 256393225735. Arua.3.022703,30.909956. FTTH_20_M_O | Arua |  | Chrif |  |  |  | 2,326,232.78 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-23 | 2023-03-23 | 2023-03-25 | 2023-04-04 | 12 | 12 | Customer will be available on Saturday for surveying |  |  |  |  | 4
| null null. 256763350187. makindye.0.272835,32.617492. FTTH_40_M_O | Makindye |  | Rontech |  |  |  | 4,811,077 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-04-04 | 8 | 8 | [5 empty] | 12
| null null. 256776191339. kololo.0.327297,32.59492. FTTH_20_M_O | Kololo |  | Chrif |  |  |  | 3,532,385.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-04-01 | 4 | 4 | [5 empty] | 10
| null null. 256771627213. Masaka road.0.318811,32.595311. FTTH_20_M_O | Ndeeba |  | Rontech |  |  |  | 1,353,291 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-04-03 | 5 | 5 | [5 empty] | 5
| EMMANUEL KIDULA. 256788105861. LifeWay church of Christ lugala.0.318811,32.595311. FTTH_40_M_O | Rubaga |  | Rontech |  |  |  | 3,158,717 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-26 | 2023-03-26 | 2023-03-28 | 2023-04-02 | 7 | 7 | [5 empty] | 8
| WALTER EGWEL OTIM. 256775949520. post bank Kampala road. 0.311918,32.587171. FTTH_20_M_O | Kampala Upper CBD |  | Chrif |  |  |  | 1,075,411.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-02-24 | 2023-03-18 | 2023-03-20 | 2023-04-01 | 36 | 14 | [5 empty] | 5
| null null. 256786708143. namuwongo.0.310792,32.609375. FTTH_40_M_O | Namuwongo |  | Rontech |  |  |  | 3,677,093 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-04-04 | 6 | 6 | [5 empty] | 3
| Ivan Kirum. 256782871347. mukono town.0.354866,32.752014. FTTH_20_M_O | Mukono |  | Enetworks | 662303 | 414131 | 462335 | 1076433.2 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-04-04 | 5 | 5 | [5 empty] | 2
| OLIVIA NAMBUYA. 256779867150. kiru apartments.0.318811,32.595311. FTTH_20_M_O | Luzira |  | Enetworks |  |  | 473120 | 730772.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-04-03 | 4 | 4 | [5 empty] | 0
| null null. 256779792544. mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 1,962,538 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-04-02 | 3 | 3 | [5 empty] | 5
| null null. 256786801096. mpererwe.0.381891,32.576158. FTTH_20_M_O | Gayaza |  | Enetworks |  |  | 1653089.5 | 2297167.3 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-04-04 | 5 | 5 | [5 empty] | 5
| ABDULKARIM ASIIMWE. 256772268997. mbarara uganda.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech |  |  |  | 1,646,792 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-31 | 2023-03-30 | 2023-04-01 | 2023-04-02 | 2 | 3 | [5 empty] | 6
| null null. 256788498589. Muyenga:Bukasa Road. 0.298796,32.622587. FTTH_20_M_O | Muyenga |  | Rontech |  |  |  | 4837804 | Office Internet | 0 | Done | Office Internet (On air) | 2023-02-01 | 2023-03-15 | 2023-03-17 | 2023-04-02 | 60 | 18 | [5 empty] | 10
| JOHN KASIMBAZI. nkumba university. 0.095128,32.506873. FTTH_20_M_O | Entebbe |  | Chrif |  |  |  | 954521.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-15 | 2023-03-30 | 2023-04-01 | 2023-04-02 | 18 | 3 | [5 empty] | 8
| null null. 256774340273. Kawaala Kasubi.0.332752,32.554645. FTTH_20_M_O | Rubaga |  | Rontech |  |  |  | 3,699,813 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-09 | 2023-03-27 | 2023-03-29 | 2023-04-04 | 26 | 8 | [5 empty] | 9 | Done | On air | 2023-04-04
| null null. 256777864915. Gulu:Gulu CBD.2.763301,32.299987 . FTTH_20_M_O | Gulu |  | Rontech |  |  |  | 6916827.8 | Office Internet | 18 | Done | Office Internet (On air) | 2023-01-27 | 2023-02-08 | 2023-02-10 | 2023-04-06 | 69 | 39 | HIGH BOQ 6,916,827.80 |  |  |  |  | 8
| null null. 256763020752. Rubaga:Nateete.0.301704,32.528136 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 2430464 | Office Internet | 5 | Done | Office Internet (On air) | 2023-02-08 | 2023-02-13 | 2023-02-15 | 2023-03-28 | 48 | 38 | ROW |  |  | PAC DONE
| null null. 256761025897. kitebi star. FTTH_20_M_O | Rubaga |  | Rontech |  |  |  | 3091016 | Office Internet | 3 | Done | Office Internet (On air) | 2023-02-18 | 2023-02-18 | 2023-02-20 | 2023-03-23 | 33 | 30 | ZTE Upgrade
| null null. 256778616155. lugogo bypass. FTTH_40_M_O | Kololo |  | Selmer |  |  |  | 1600108 | Office Internet | 0 | Done | Office Internet (On air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-02-23 | 3 | 3 | Done- Commissioning ongoing |  |  | PAC Done
| null null. 256770832749. 3F9G V5P Plot 55 Entebbe market. FTTH_20_M_O | Entebbe |  | ATX |  |  |  | 4,601,444.60 | Office Internet | 1 | Done | Office Internet (On air) | 2023-02-20 | 2023-02-20 | 2023-02-22 | 2023-03-01 | 9 | 8 | Customer traveled |  |  | PAC DONE
| null null. 256761078592. rubaga. . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 3,644,405 | Office Internet | 5 | Done | Office Internet (On air) | 2023-02-22 | 2023-02-27 | 2023-03-01 | 2023-03-09 | 15 | 5 | ROW issue |  |  | PAC DONE
| null null. 256763661614. Bugolobi. . FTTH_40_M_O | Bugolobi |  | chrif |  |  |  | 3558874.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-11 | 2023-03-11 | 2023-03-13 | 2023-03-22 | 11 | 11 | (Travelspot) -On Hold, R.O.W with landlords
| CLIFFORD OCHAN. 256782674810. Gulu city.( 0.318811,32.595311). FTTH_20_M_O | Gulu |  | Rontech |  |  |  | 4,852,863 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-22 | 2023-03-22 | 2023-03-24 | 2023-04-06 | 15 | 15 | High BOQ |  |  |  |  | 7
| null null. 256780411269. Mtn arena, lugogo by pass.0.326668,32.606548. FTTH_20_M_O | Kololo |  | Enetworks |  |  | 2963000 | 3416322.2 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-24 | 2023-03-24 | 2023-03-26 | 2023-04-04 | 11 | 11 | [5 empty] | 14
| null null. 256772487551. seguku.0.237516,32.541173. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech |  |  |  | 4472130 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-04-05 | 8 | 8 | [5 empty] | 10
| null null. 256762957457. kyanja.0.395861,32.593671. FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Enetworks | 563291.2 | 516431 | 696254 | 1079721.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-02 | 2023-04-02 | 2023-04-04 | 2023-04-06 | 4 | 4 | [5 empty] | 2
| BRUNO FILLINGER. 256788080995. communication house.0.318811,32.595311. FTTH_20_M_O | Kololo |  | Chrif | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-03 | 2023-04-03 | 2023-04-05 | 2023-04-06 | 34 | 3 | [5 empty] | 6
| null null. 256772422450. bunga.0.318811,32.595311. FTTH_20_M_O | Ggaba |  | Rontech | 2140544 | 655012 | 2562353 | 2795556 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-03 | 2023-04-03 | 2023-04-05 | 2023-04-07 | 35 | 4 | [5 empty] | 4
| null null. 256788619437. bwebajja. 0.164019,32.54788. FTTH_20_M_O | Bwebajja |  | Chrif |  |  |  | 594070.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-05 | 2023-04-07 | 2023-04-05 | 1 | 0 | [5 empty] | 4
| null null. 256775384460.Mbarara. -0.60716,30.65450. FTTH_20_M_O | Mbarara |  | Rontech | 1281506 | 753331 | 1769470 | 2034837 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-05 | 2023-04-07 | 2023-04-05 | 1 | 0 | [5 empty] | 6
| null null. 256392840284. Kampala Uganda.0.312566,2.579458. FTTH_20_M | Old park |  | Chrif |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-02-17 | 2023-03-21 | 2023-03-23 | 2023-04-07 | 49 | 17 | Delayed by COntractor |  |  |  |  | 3
| Nkalubo Vianney. 256789284585. Makindye:Luwafu Road. 0.23489,32.62015. FTTH_20_M_O | Makindye |  | Rontech |  |  |  | 4137865 | Office Internet | 0 | Done | Office Internet (On air) | 2022-11-21 | 2023-03-28 | 2023-03-30 | 2023-04-06 | 136 | 9 | [5 empty] | 11
| KYARIKUNDA ANNAH. 256773708399. esami building bombo road.0.326852,32.573766. FTTH_20_M_O | Nakasero Hill |  | Chrif |  |  |  | 847943 | Office Internet | 14 | Done | Office Internet (On air) | 2023-03-23 | 2023-03-24 | 2023-03-26 | 2023-04-10 | 18 | 3 | Customer to communicate when ready |  |  |  |  | 10
| null null. 256777153675. bombo road.0.318811,32.595311. FTTH_20_M_O | Kololo |  | Chrif |  |  |  | 2317719.6 | Office Internet | 7 | Done | Office Internet (On air) | 2023-03-27 | 2023-03-27 | 2023-03-29 | 2023-04-10 | 14 | 7 | ROW/BW issue on Rwenzori |  |  |  |  | 10
| Jovia. 256782129261. kikuubo.0.338005,32.621123. FTTH_20_M_O | Kampala downtown |  | Chrif |  |  |  | 1585372.35 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-04-08 | 11 | 11 | Pending customer for commissioning |  |  |  |  | 2
| FUDRIBO YORAM. 256780958210. bunga.0.318811,32.595311. FTTH_20_M_O | Ggaba |  | Rontech |  |  |  | 2777958 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-04-08 | 9 | 9 | [5 empty] | 4
| Sultan Nasser Asab. 256772445032. Kisugu mutajjazi.0.304864,32.603722. FTTH_20_M_O | Rubaga |  | Rontech | 1695313 | 741005 | 2206135 | 2436319 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-02 | 2023-04-02 | 2023-04-04 | 2023-04-08 | 6 | 6 | Delayed by Customer. Change of Office Location |  |  |  |  | 5
| null null. 256774511074. lungujja.0.309657,32.540489. FTTH_20_M_O | Rubaga |  | Rontech | 3009929 | 693763 | 3365096 | 3703692 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-04 | 2023-04-06 | 2023-04-11 | 7 | 7 | Row with Landlord |  |  |  |  | 9
| null null. 256763259574. Namugongo.0.385062,32.647526. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks | 1678068 | 517231 | 1710930 | 2195298.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-04 | 2023-04-06 | 2023-04-08 | 4 | 4 | [5 empty] | 14
| null null. 256782819096. lungujja.0.309657,32.540489. FTTH_20_M_O | Rubaga |  | Chrif | 0 | 0 | 0 | 1402471.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-04 | 2023-04-06 | 2023-04-09 | 5 | 5 | [5 empty] | 4
| null null. 256787376519. Mutundwe.0.280748,32.540416. FTTH_20_M_O | Rubaga |  | Rontech | 2109951 | 726317 | 2572734 | 2836268 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-04 | 2023-04-06 | 2023-04-10 | 6 | 6 | Delayed access to Mutundwe Switch |  |  |  |  | 6
| FLAVIA ATUMANYA. 256772402147. mukono.0.354866,32.752014. FTTH_20_M_O | Mukono |  | Enetworks | 1810021.4 | 517230.6 | 1828469 | 2327252 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-04 | 2023-04-06 | 2023-04-08 | 4 | 4 | [5 empty] | 16
| null null. 256763958591. entebbe.0.051184,32.463708. FTTH_20_M_O | Entebbe |  | Chrif | 0 | 0 | 0 | 724070.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-10 | 5 | 5 | [5 empty] | 4
| REBECCA NTIMARWA. 256777194006. Bugolobi, Kampala.0.312704,32.624147. FTTH_40_M_O | Bugolobi |  | Enetworks | 1470968.8 | 537931 | 1423630 | 2008899.4 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-11 | 6 | 6 | System issue |  |  |  |  | 12
| Charles Ntembo. 256773832586. kigo road.0.318811,32.595311. FTTH_20_M_O | Kigo |  | Chrif | 0 | 0 | 0 | 1345636.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-02 | 2023-04-02 | 2023-04-04 | 2023-04-08 | 6 | 6 | Delayed by customer unavailability - Available on Sundays |  |  |  |  | 5
| JAMES PETER EMORUT. 256785257655. kira.0.318811,32.595311. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks | 0 | 745828.6 | 534355 | 745828.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-06 | 2023-04-06 | 2023-04-08 | 2023-04-08 | 2 | 2 | [5 empty] | 1
| ALLEN AMPUMUZA. 256787783484. Enttebbe.0.051184,32.463708. FTTH_40_M_O | Entebbe |  | Chrif | 0 | 0 | 0 | 1891910.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-08 | 2023-04-08 | 2023-04-10 | 2023-04-10 | 2 | 2 | [5 empty] | 5
| denis. 256763905917. Lumumba avenue.0.318811,32.595311. FTTH_40_M_O | Kololo |  | Chrif |  |  | 454,000.00 | 738,039.10 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-04-13 | 15 | 15 | Appointment for 1st Saturday April |  |  |  |  | 5
| IVAN OJOK. 256777297960. gulu.2.78471,32.297938. FTTH_40_M_O | Gulu |  | ROntech | 1790333 | 807243 | 2359331 | 2597577 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-13 | 8 | 8 | ROW |  |  |  |  | 3
| Mutebi Humphrey. 256772923431. oasis mall.0.318811,32.595311. FTTH_40_M_O | Kololo |  | Chrif | 0 | 0 | 478,730.00 | 745,177.40 | Office Internet | 4 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-09 | 4 | 0 | [5 empty] | 10
| ANNET NAKANWAGI. 256781511240. industrial area.0.318811,32.595311. FTTH_20_M_O | Kololo |  | Enetworks | 1133217 | 517230.6 | 1166079 | 1650447.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-12 | 7 | 7 | ROW |  |  |  |  | 6
| GERALD RAYMOND BUKENYA. 256776520341. Bunamwaya.0.264913,32.546466. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech | 2474864 | 761299 | 2708390.5 | 3236163 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-13 | 8 | 8 | Delayed Consolidation |  |  |  |  | 21
| null null. 256775674220. Kampala Downtown:Nakivubo Road. 0.310007,32.57684. FTTH_20_M_O | Kampala downtown |  | Chrif |  |  |  |  | Office Internet | 5 | Done | Office Internet (On air) | 2023-04-08 | 2023-04-08 | 2023-04-10 | 2023-04-14 | 6 | 1 | [5 empty] | 10
| PETER BYAMUKAMA. 256780106558. kireka.0.337484,32.646896. FTTH_20_M_O | Bweyogerere |  | Enetworks | 528940 | 429231 | 619155 | 958170.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-09 | 2023-04-09 | 2023-04-11 | 2023-04-13 | 4 | 4 | [5 empty] | 8
| MUBARAK MUKWAYA. 256783012719. Bugolobi.0.309722,32.625765. FTTH_20_M_O | Bugolobi |  | Enetworks | 1050945 | 443031 | 1081679 | 1493975.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-14 | 4 | 4 | [5 empty] | 6
| Wampawu Rogers.256789750384.kumbuzi.0.404679,32.588007. FTTH_20_M_O | Gayaza |  | Enetworks |  |  |  | 45030 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-10 | 2023-03-15 | 2023-03-17 | 2023-04-14 | 35 | 30 | High BOQ - Consolidated with 256789750384 CEDRICK MUTEKANGA |  |  |  |  | 8
| JULIET AWEKO. 256782867582. Kirinya namataba.0.333756,32.667831. FTTH_20_M_O | Bweyogerere |  | Enetworks | 1506704 | 531031 | 1603429 | 2037734.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-06 | 2023-04-11 | 2023-04-13 | 2023-04-13 | 7 | 2 | [5 empty] | 4
| BHARAT GOVIND VAGHJIYANI. 256789907224. mbarara _uganda.-0.60716,30.654502. FTTH_20_M_O | Mbarara |  | Rontech | 1977609 | 871503 | 2583745 | 2849112 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-13 | 1 | 1 | [5 empty] | 5
| ALEX SENYONJO 256779024214 Entebbe 0.045565, 32.464364 FTTH_20_M_O | Entebbe |  | Chrif |  |  | 386200 | 615265.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-23 | 2023-04-04 | 2023-04-06 | 2023-04-13 | 21 | 9 | Delayed by customer - Had another service |  |  |  |  | 5
| GILBERT TURYAHEBWA. 256782016059. ntinda.0.350605,32.615769. FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) |  | Enetworks | 2313077.5 | 427324.5 | 2127524.5 | 2740402 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-04-14 | 2 | 2 | [5 empty] | 22
| null null. 256772956758. kapera kyaliwajjala. 0.380597,32.646819. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks | 1438060 | 465030.6 | 1346650 | 1903090.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-04 | 2023-04-11 | 2023-04-13 | 2023-04-12 | 8 | 1 | [5 empty] | 2
| null null. 256781106390. kirinya bukasa. . FTTH_20_M_O | Bweyogerere |  | Enetworks |  |  | 3747000 | 4277472.3 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-15 | 2023-03-15 | 2023-03-17 | 2023-04-17 | 33 | 33 | Done - Pending customer to communicate when ready for commissioning |  |  |  |  | 3
| null null. 256777907205. Christian freedom church.0.318811,32.595311. FTTH_20_M_O | Gayaza |  | Enetworks | 1536899.6 | 638480.6 | 1633354 | 2175380.2 | Office Internet | 10 | Done | Office Internet (On air) | 2023-04-12 | 2023-03-29 | 2023-03-31 | 2023-04-17 | 5 | 9 | Mobilizing to start Civil works< waiting for4 Access at Akamwesi |  |  |  |  | 10
| null null. 256775851382. Bukoto,Kampala.0.350525,32.595242. FTTH_20_M_O | Ntinda (Bukoto) |  | Chrif |  |  | 617,756.00 | 1,473,431.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-30 | 2023-03-30 | 2023-04-01 | 2023-04-18 | 19 | 19 | Customer to confirm commissioning date |  |  |  |  | 8
| Joyce Olany Nyaga. 256773471316. gulu.2.782216,32.300292. FTTH_40_M_O | Gulu |  | Rontech |  |  |  | 1995607 | Office Internet | 13 | Done | Office Internet (On air) | 2023-03-31 | 2023-03-30 | 2023-04-01 | 2023-04-15 | 15 | 3 | BW at UNICAF |  |  |  |  | 0
| null null. 256770702478. lake crescent.0.318811,32.595311. FTTH_20_M_O | Ggaba |  | Rontech |  |  | 2206898 | 2416733 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-03 | 2023-03-03 | 2023-03-05 | 2023-04-15 | 43 | 43 | Mobilizing to start Civil works |  |  |  |  | 11
| MARK NOWAMANI. 256776174016. kololo.0.327297,32.59492. FTTH_20_M_O | Kololo |  | Chrif |  |  | 2330026 | 3131466.6 | Office Internet | 5 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-17 | 12 | 7 | ROW with Centenary Park. needs to engage his landlord for r.o.w and revert possibly on Tuesday 11.4.2023. The scope involves erection of 4 poles within centenary park which requires the landlord to be aware. |  |  |  |  | 10
| AMINA HUSSEIN. 256785341694. ndeeba.0.292993,32.564796. FTTH_20_M_O | Ndeeba |  | Rontech |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-05 | 2023-04-05 | 2023-04-07 | 2023-04-18 | 13 | 13 | Delayed by customer unavailability |  |  |  |  | 0
| ABDINASIR MOHAMED. 256777043178. gulu.0.318811,32.595311. FTTH_20_M_O | Gulu |  | Rontech | 1561548 | 696481 | 1939132 | 2258029 | Office Internet | 7 | Done | Office Internet (On air) | 2023-04-06 | 2023-04-06 | 2023-04-08 | 2023-04-15 | 9 | 2 | BW Issue |  |  |  |  | 4
| JUMA MULYANTI. 256788081466. Masaka rd.0.318811,32.595311. FTTH_40_M_O | Kololo |  | Chrif |  |  | 1,904,376.00 | 2,705,816.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-17 | 6 | 6 | System downtime |  |  |  |  | 10
| FAO UNITED NATIONS. 256776008083. Akright- Sseguku Entebbe Road.0.174251,32.538818. FTTH_20 | Bwebajja |  | Chrif |  |  | 1762000 | 2606680.6 | Office Internet ( Postpaid) | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-17 | 6 | 6 | System downtime |  |  |  |  | 3
| HELEN AKUI. 256786220550. ntinda.0.350605,32.615769. FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) |  | Enetworks | 1064883.4 | 290950 | 986780 | 1355833.4 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-18 | 7 | 7 | Delayed by customer unavailability |  |  |  |  | 0
| MUJIIB MINALLAH. 256774657926. Makerere.0.332635,32.568586. FTTH_20_M_O | Makerere |  | Chrif |  |  | 454,000.00 | 672,070.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-18 | 7 | 7 | BW issue - Rwenzori Port 0 |  |  |  |  | 6
| AJIT HIRJI HARIA. 256786367803. bukoto.0.350525,32.595242. FTTH_20_M_O | Ntinda (Bukoto) |  | Chrif |  |  | 354,520.00 | 576,988.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-13 | 2 | 2 | [5 empty] | 10
| HANNAH NSUMBA. 256772418936. Entebbe.0.051184,32.463708. FTTH_20_M_O | Entebbe |  | Chrif |  |  | 1,535,806.00 | 2,272,386.60 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-13 | 2023-04-13 | 2023-04-15 | 2023-04-18 | 5 | 5 | [5 empty] | 6
| PHILLIP ATWINE. 256774188920. mbalwa kyambogo.0.365182,32.653176. FTTH_10_M_O | Bweyogerere |  | Enetworks | 1431694 | 603231 | 1614659 | 1953674.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-15 | 1 | 1 | [5 empty] | 0
| LYDIA BASEMERA. 256777093189. Kyanja.0.395861,32.593671. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) |  | Enetworks | 0 | 827017.6 | 564234 | 827017.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-18 | 4 | 4 | [5 empty] | 4
| MERVEILLE BALUME. 256761206384. salama.0.318811,32.595311. FTTH_10_M_O | Ggaba |  | Rontech | 0 | 809224 | 561449 | 809224 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-15 | 2023-04-17 | 2023-04-18 | 3 | 3 | [5 empty] | 6
| ARNOLD CEASER ATUSIMIRWE. 256770718295. ntinda.0.350605,32.615769. FTTH_10_M_O | Ntinda (Bukoto) |  | Rak | 208750 | 277174 | 485924 | 714566.6 | Office Internet | = | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-18 | 0 | #VALUE! | [5 empty] | 0
| null null.256775961273.bugolobi.0.309722.32.625765. FTTH_10_M_O | Bugolobi |  | Enetworks | 0 | 869523.6 | 649254 | 869523.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-13 | 2023-04-14 | 2023-04-16 | 2023-04-16 | 3 | 2 | [5 empty] | 0
| EDWIN MAKOHA. 256788210235. wabigalo.0.315394,32.607851. FTTH_40_M_O | Namuwongo |  | Chrif |  |  | 1470969 | 1819513.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-19 | 8 | 8 | Delayed by Customer - Office closed over the weekend |  |  |  |  | 9
| . 256772935992. ntinda.0.350605,32.615769. FTTH_20_M_O | Ntinda (Bukoto) |  | Enetworks | 390915.5 | 319612 | 547616.5 | 710527 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-19 | 5 | 5 | Mobilizing to start Civil works |  |  |  |  | 2
| TONNY KUNIHIRA. 256787966787. kazo.0.318811,32.595311. FTTH_10_M_O | kawempe |  | Chrif |  |  | 1284600 | 1671260.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-23 | 9 | 9 | Reassignment |  |  |  |  | 12
| Jihee Ahn. 256783802030. Mabua road kololo.0.332698,32.588012. FTTH_10_M_O | Kololo |  | Chrif |  |  | 354520 | 576988.6 | Office Internet | 5 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-21 | 7 | 2 | Both installations physical and configuration in green top residency are done but the management requires the client to buy an access point in his apartment because the building already has LAN. Therefore activation has been put to hold. |  |  |  |  | 12
| CHRISTOPHER MWESIGE. 256779590866. Makindye.0.272835,32.617492. FTTH_10_M_O | Makindye |  | Rontech | 2143635 | 680359 | 2573933 | 2823994 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-21 | 7 | 7 | ROW by Landlord |  |  |  |  | 5
| LORDINE ARTHUR OKUMU. 256777730629. bukoto.0.350525,32.595242. FTTH_10_M_O | Ntinda (Bukoto) |  | Enetworks | 1212654 | 258615.5 | 1070549.5 | 1471269.5 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-15 | 2023-04-17 | 2023-04-21 | 6 | 6 | ROW by Landlord |  |  |  |  | 8
| . 256789318836. Ntinda.0.350605,32.615769. FTTH_10_M_O | Ntinda (Kiwatule - Naalya ) |  | Enetworks | 2060778 | 539731 | 1928788 | 2600508.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-15 | 2023-04-17 | 2023-04-20 | 5 | 5 | [5 empty] | 9
| CAROLYN NAMWANGA. 256761312525. lungujja.0.309657,32.540489. FTTH_10_M_O | Rubaga |  | Chrif |  |  | 322245 | 799385.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-15 | 2023-04-17 | 2023-04-20 | 5 | 5 | [5 empty] | 14
| Simon. 256773339951. nakasero.0.321785,32.581011. FTTH_10_M_O | Nakasero Hill |  | Chrif |  |  | 454000 | 683065.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-15 | 2023-04-17 | 2023-04-20 | 5 | 5 | [5 empty] | 8
| INNOCENT KARAMAGI. 256772920901. Makerere kavule.0.346514,32.567689. FTTH_10_M_O | Makerere |  | Chrif |  |  | 436730 | 659198.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-21 | 4 | 4 | [5 empty] | 6
| TWEBAZE EMMANUEL. 256782769906. Kibuli.0.305427,32.605169. FTTH_20_M_O | Nsambya |  | Rontech | 789529 | 668253 | 1192415 | 1457782 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-25 | 8 | 8 | Delayed by Contractor |  |  |  |  | 10
| IVAN SSALI. 256787962214. 1st street Industrial Area.0.320648,32.599331. FTTH_10_M_O | Kololo |  | Enetworks | 659017.4 | 730031 | 1061031 | 1389048 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-19 | 2 | 2 | [5 empty] | 3
| SIMON PETER NDAWULA. 256789070300. Entebbe road.0.051184,32.463708. FTTH_10_M_O | Entebbe |  | Chrif |  |  | 454000 | 683065.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-22 | 5 | 5 | [5 empty] | 8
| Isa Kibirige Mayanja. 256782455079. bwebajja.0.164019,32.54788. FTTH_20_M_O | Bwebajja |  | Chrif |  |  | 1937356 | 2782036.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-21 | 4 | 4 | [5 empty] | 14
| DERIE MOHAMUD. 256776449604. main street, Jinja.0.439964,33.218451. FTTH_10_M_O | Jinja |  | Enetworks | 2612939 | 473231 | 2146769 | 3013069.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-17 | 2023-04-19 | 2023-04-21 | 10 | 4 |  |  |  | PAC Done |  | 28
| FORTUNE MWIZA. 256760595850. Mbuya Citadel place.0.325589,32.630572. FTTH_10_M_O | Bugolobi |  | Enetworks | 0 | 777343.6 | 554875 | 777343.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-18 | 2023-04-20 | 2023-04-24 | 10 | 6 | Delayed by customer unavailability |  |  |  |  | 18
| Sadiq Amako. 256772506570. entebbe.0.051184,32.463708. FTTH_10_M_O | Entebbe |  | Chrif |  |  | 367840 | 577114.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-19 | 2 | 2 | [5 empty] | 9
| DINAH OPOLA. 256775058238. Ndeeba.0.294379,32.558749. FTTH_40_M_O | Ndeeba |  | Rontech | 789529 | 674015 | 1198177 | 1463544 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-24 | 2023-04-26 | 2023-04-24 | 7 | 0 | [5 empty] | 22
| MABLE KABAGABU MULENGA. 256772666472. kireka SK HOUSE.0.337484,32.646896. FTTH_10_M_O | Bweyogerere |  | Enetworks | 0 | 858397.6 | 490795 | 858397.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-19 | 2 | 2 | [5 empty] | 4
| PAUL KITAKULE. 256772225159. Gabula, Jinja.0.426312,33.207149. FTTH_20_M_O | Jinja |  | Enetworks | 2164939 | 473231 | 2096169 | 2638169.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-21 | 4 | 4 |  |  |  | PAC Done |  | 22
| Selina Olumbe. 256781410266. Maya inn entebbe.0.075102,32.456843. FTTH_40_M_O | Entebbe |  | Chrif |  |  | 333600 | 562665.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-25 | 7 | 7 | BW issue - Entebbe OLT |  |  |  |  | 0
| MARVIN KIGOZI. 256778566062. Jinja Road.0.312229,32.585889. FTTH_10_M_O | Kampala Upper CBD |  | Rak | 208750 | 220850 | 429600 | 675834.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-24 | 6 | 6 | ROW |  |  |  |  | 5
| SARAH BIRUNGI. 256773015967. Old portbell rd.0.318811,32.595311. FTTH_20_M_O | Kololo |  | Rak | 208750 | 207250 | 416000 | 662234.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-21 | 3 | 3 | [5 empty] | 0
| . 256775991852. kololo princecharles apartments.0.327297,32.59492. FTTH_20_M_O | Kololo |  | Rak | 208750 | 332026 | 540776 | 771617.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-20 | 2 | 2 | [5 empty] | 10
| EUNICE BAKOBYE. 256763898440. lubas road jinja.0.427854,33.210989. FTTH_10_M_O | Jinja |  | Enetworks | 970496 | 768230.6 | 1440029 | 1738726.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-22 | 4 | 4 |  |  |  | PAC Done |  | 4
| BERNARD WILLIAM BOSSA. 256772402261. Balintuma Road plot 430.0.318811,32.595311. FTTH_20_M_O | RUBAGA |  | Pavicon | 1400376 | 155,970 | 1,556,346 | 2,158,396 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-21 | 3 | 3 | High BOQ |  |  |  |  | 2
| Nehemiah Mukiibi. 256776702591. Kikoni.0.342714,32.561313. FTTH_10_M_O | Makerere |  | Rak | 208750 | 208750 | 417500 | 673583.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-19 | 1 | 1 | [5 empty] | 5
| ANNAH AKANKUNDA. 256760143248. Mbarara.0.318811,32.595311. FTTH_40_M_O | Mbarara |  | Rontech | 0 | 1197194 | 1197194 | 1398058 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-19 | 1 | 1 | [5 empty] | 2
| PAUL OUMA. 256776847828. Bugolobi.0.309722,32.625765. FTTH_20_M_O | Bugolobi |  | Enetworks | 0 | 816929.6 | 609854 | 816929.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-24 | 6 | 6 | ROW |  |  |  |  | 4
| ANN NAKABUYE. 256773027713. Rubaga.0.308739,32.547918. FTTH_10_M_O | RUBAGA |  | Pavicon | 852,826 | 153,070 | 1,005,896 | 1553896 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-19 | 1 | 1 | [5 empty] | 4
| PATRICIA KAUTE ANGELA KILAVI. 256777186559. Ntinda Kigowa Road.0.350605,32.615769. FTTH_10_M_O | Ntinda (Kiwatule - Naalya ) |  | Soliton | 1906820 | 398978 | 1658408 | 2305798 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-18 | 0 | 0 | [5 empty] | 6
| RAMADHAN KISAMBIRA. 256773092206. wankulukuku.0.282238,32.551415. FTTH_10_M_O | RUBAGA |  | Pavicon | 852,826 | 164290 | 1,017,116 | 1684026 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-19 | 1 | 1 | [5 empty] | 3
| TONY MWESIGWA. 256787122041. ntinda.0.350605,32.615769. FTTH_10_M_O | Ntinda (Bukoto) |  | Rak | 978386 | 166690 | 1145076 | 2138463.2 | Office Internet |  | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-23 | 5 | 5 | [5 empty] | 10
| JACKIE TURYAGYENDA.256777398442.buwaate.0.406834,32.619739.FTTH_20_M_O | Bugolobi |  | Enetworks | 1074073.2 | 524131 | 998520 | 1598203.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-06 | 2023-04-17 | 2023-04-19 | 2023-04-18 | 43 | 1 | [5 empty] | 10
| ashar cheptoris.256776045352.Kololo:Acacia Avenue.0.338684,32.588202.FTTH_20_M_O | Kololo |  | Chrif |  |  | 358600 | 581068.6 | Office Internet | 0 | Done | Office Internet (On air) | 2022-06-03 | 2023-04-11 | 2023-04-13 | 2023-04-22 | 323 | 11 | Reassignment - Cluster Reallocation |  |  |  |  | 12
| null null.256784818718.kirinya,kampala.0.340979.32.662211. FTTH_20_M_O | Bweyogerere |  | Enetworks | 1088049 | 473231 | 1105759 | 1561279.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-28 | 2023-04-17 | 2023-04-19 | 2023-04-20 | 23 | 3 | [5 empty] | 4
| null null.256762702719.kisaasi.0.361441,32.596655.FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) |  | Soliton | 2686059 | 388628 | 2101334 | 3074687 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-03 | 2023-04-19 | 2023-04-21 | 2023-04-19 | 47 | 0 | [5 empty] | 11
| MABLE KABAGABU MULENGA.256772666472.kireka SK HOUSE.0.337484,32.646896.FTTH_10_M_O | Bweyogerere |  | Enetworks | 0 | 858397.6 | 490795 | 858397.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-19 | 2 | 2 | [5 empty] | 4
| DAVID BWAMBALE. 256771581002. Nasser Road.0.318811,32.595311. FTTH_20_M_O | Kampala Upper CBD | MTNFTTO84338248 | Rak | 208750 | 196880 | 405630 | 640869.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-24 | 4 | 4 | [5 empty] | 10
| ASHIRAPH KULE. 256774239575. mutunya road.0.318811,32.595311. FTTH_20_M_O | Rubaga | MTNFTTO22220312 | Rak | 553,016 | 129610 | 682626 | 1,250,232 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-21 | 1 | 1 | [5 empty] | 2
| DANISON KAMUGISHA. 256775500935. nakasero.0.321785,32.581011. FTTH_10_M_O | Kampala Upper CBD | MTNFTTO42124888 | Rak | 208750 | 313826 | 522576 | 753417.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-24 | 4 | 4 | [5 empty] | 8
| FRANCIS MUSOKE SSEKAMATTE. 256775099230. Greenfield Gardens Kanyanya.0.379739,32.572501. FTTH_20_M_O | Gayaza | MTNFTTO37314120 | Soliton | 901619 | 400280 | 1075644 | 1301899 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-21 | 2 | 2 | [5 empty] | 0
| PAUL AKEPA. 256774587419. kisasi.0.361441,32.596655. FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO11211728 | Soliton | 2061110 | 381128 | 1859268 | 2442238 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-22 | 3 | 3 | [5 empty] | 3
| WENDY EJANG. 256771853013. kisaasi.0.361441,32.596655. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO85133320 | Soliton | 2759910 | 383558 | 2321068 | 3143468 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-22 | 3 | 3 | [5 empty] | 4
| ALEXANDER ATUHEIRE. 256773695156. Fortportal, Uganda.0.653495,30.275075. FTTH_10_M_O | Fort portal | MTNFTTO32128065 | Chrif |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-22 | 3 | 3 | [5 empty] | 4
| MARTIN LUKABYA. 256782522829. Portbell.0.297762,32.653176. FTTH_20_M_O | Luzira | MTNFTTO71574563 | Enetworks | 0 | 972518.6 | 741254 | 972518.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-25 | 6 | 6 | [5 empty] | 4
| DERRICK KIRYA. 256393240676. Kireka, Kampala.0.318916,32.632824. FTTH_20_M_O | Luzira | MTNFTTO07001342 | Enetworks | 725485 | 509030.6 | 649275 | 1234515.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-24 | 5 | 5 | [5 empty] | 0
| . 256761064293. ENTEBBE, bugonga.0.043731,32.466342. FTTH_40_M_O | Entebbe | MTNFTTO55846811 | Chrif |  |  | 549356 | 778421.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-24 | 5 | 5 | [5 empty] | 3
| SILVER HAKIZA. 256773003214. kitintale market.0.310706,32.634802. FTTH_10_M_O | Luzira | MTNFTTO20385817 | Enetworks | 454060 | 483750.6 | 598795 | 937810.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-22 | 3 | 3 | [5 empty] | 5
| . 256760359342. ENTEBBE BUGONGO.0.051184,32.463708. FTTH_40_M_O | Entebbe | MTNFTTO73228233 | Chrif | 0 | 0 | 933320 | 1561800.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-24 | 5 | 5 | [5 empty] | 14
| null null.256782787471.mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara | MTNFTTO41683452 | Rontech | 0 | 0 | 1225754 | 1414311 | Office Internet | 0 | Done | Office Internet (On air) | 2023-02-21 | 2023-03-22 | 2023-03-24 | 2023-04-22 | 60 | 31 | [5 empty] | 3
| Musaazi Bruno.256776686157.rubaga.0.308739.32.547918.FTTH_20_M_O | RUBAGA | MTNFTTO37261383 | Pavicon | - | 549026 | 549026 | 794901 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-20 | 2023-04-14 | 2023-04-16 | 2023-04-21 | 32 | 7 | Re-assigned to Pavicon on 19-April- Work was closed on 20-April |  |  |  |  | 0
| DAVIDS STANLY AHABUMUGISHA.256783149389.muyenga.0.296898,32.615028. FTTH_10_M_O | Muyenga | MTNFTTO26776221 | Rontech | 208750 | 760501 | 686293 | 969251 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-20 | 1 | 1 | [5 empty] | 0
| null null.256781211269.gadafi road.0.318811,32.595311.FTTH_20_M_O | Makerere | MTNFTTO28123752 | Rak | 208750 | 173650 | 382400 | 628634.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-21 | 2023-04-14 | 2023-04-16 | 2023-04-21 | 0 | 7 | [5 empty] | 10
| null null.256772791557.Bwebajja.0.164019,32.54788.FTTH_20_M_O | Bwebajja | MTNFTTO37223734 | Chrif |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-24 | 2023-03-24 | 2023-03-26 | 2023-04-18 | 25 | 25 | [5 empty] | 7
| DEO MAFABI. 256760359759. Kyanja supermarket.0.396535,32.593528. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO80702376 | Soliton | 0 | 768422.6 | 528923 | 768422.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-22 | 2023-04-22 | 2023-04-24 | 2023-04-24 | 2 | 2 | [5 empty] | 0
| MAUREEN NABWETEME. 256779376672. port bell.0.318811,32.595311. FTTH_10_M_O | Luzira | MTNFTTO05411564 | Enetworks | 1217188 | 465724 | 1298478 | 1682911.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-23 | 2023-04-23 | 2023-04-25 | 2023-04-25 | 2 | 2 | [5 empty] | 14
| DOMINAH MASOLO. 256772587603. sparkles Saloon Bugolobi.0.309722,32.625765. FTTH_20_M_O | Bugolobi |  | Enetworks | 943705 | 565031 | 1122075 | 1508735.6 | Office Internet | 5 | Done | Office Internet (On air) | 2023-04-07 | 2023-04-07 | 2023-04-09 | 2023-04-27 | 20 | 15 | waiting for management Approval |  |  |  |  | 5
| STEPHEN KABUYE. 256772485887. Entebbe.0.051184,32.463708. FTTH_40_M_O | Entebbe |  | Chrif |  |  |  | 0 | Office Internet | 10 | Done | Office Internet (On air) | 2023-04-10 | 2023-04-10 | 2023-04-12 | 2023-04-25 | 15 | 5 | Waiting for Management to Poles Location |  |  |  |  | 5
| CEDRICK MUTEKANGA. 256781507974. Kitetika-Gayaza.0.386821,32.57797. FTTH_20_M_O | Gayaza |  | Enetworks | 943705 | 565031 | 1122075 | 1508735.6 | Office Internet | 5 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-26 | 15 | 10 | Customer to communicate when ready for commissioning |  |  |  |  | 3
| IVAN SSERUBIRI. 256787686486. Abayita Ababiri.0.093547,32.499856. FTTH_20_M_O | Entebbe |  | Chrif | 1112256 | 1740736.6 | 1189006 | 551730.6 | Office Internet | 15 | Done | Office Internet (On air) | 2023-04-11 | 2023-04-11 | 2023-04-13 | 2023-04-27 | 16 | 1 | ROW with Landlord |  |  |  |  | 2
| ANGELLA BABIRYE. 256781863192. Entebbe.0.051184,32.463708. FTTH_10_M_O | Entebbe |  | Chrif | 2276238 | 3147470.5 | 5843356 | 451585.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-26 | 12 | 12 | Client is 450m away from service, looking for a neighbor to consolidate |  |  |  |  | 10
| FRANCIS MBUGA KIZITO. 256786652302. lungujja, kitunzi.0.309657,32.540489. FTTH_40_M_O | RUBAGA |  | Pavicon | 3848232 | 700391 | 3294502 | 4548623 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-04-28 | 14 | 14 | Re-assigned to Pavicon on 26-April- Customer Paid Before we Started MTN works, We closed the work on 28-April |  |  |  |  | 30
| CEDRICK MUTEKANGA. 256782441558. Ssekajja Road.0.318811,32.595311. FTTH_10_M_O | Kira (Buwate - Busibante Najjera) |  | Enetworks | 1088049 | 524131 | 1156659 | 1612179.6 | Office Internet | 7 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-15 | 2023-04-17 | 2023-04-26 | 11 | 4 | Client not picking standard sms |  |  |  |  | 0
| SAID WAMBI. 256772581852. Entebbe road.0.051184,32.463708. FTTH_10_M_O | Kampala Upper CBD |  | Pavicon | 233750 | 365274 | 350950 | 599024 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-27 | 10 | 10 | Re-assigned to Pavicon on 24-April- Delays to Access Ganesh Plaza by building management |  |  |  |  | 0
| NAKAZIBWE SIANA. 256772501605. bugembe.0.318811,32.595311. FTTH_20_M_O | Jinja |  | Enetworks | 1789339.6667 | 392061 | 1583089.6667 | 2181400.6667 | Office Internet | 4 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-26 | 9 | 5 | On hold, High BOQ |  |  |  |  | 10
| FIDEL AMANYA. 256392001736. entebbe road.0.051184,32.463708. FTTH_10_M_O | Kampala Upper CBD |  | Pavicon | 233750 | 339840 | 338710 | 573590 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-27 | 10 | 10 | Re-assigned to Pavicon on 24-April- Delays to Access Ganesh Plaza by building management- installation completed on 27-April |  |  |  |  | 0
| REHEMA NAMAKULA. 256787694353. Salaama road.0.318811,32.595311. FTTH_10_M_O | Ggaba |  | Rontech | 1719388 | 756733 | 2188765 | 2476121 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-26 | 9 | 9 | Delayed due to customer unavailability |  |  |  |  | 12
| . 256778580226. Hill Road.0.318811,32.595311. FTTH_40_M_O | Kololo |  | Chrif |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-25 | 7 | 7 | ROW issues |  |  |  |  | 0
| BHARAT LADKANI. 256774249649. airport stage.0.318811,32.595311. FTTH_10_M_O | Entebbe |  | Chrif | 877520 | 1245122.6 | 720200 | 381987.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-26 | 8 | 8 | Delayed due to customer unavailability |  |  |  |  | 6
| FRANCIS ABIYO. 256775127708. Entebbe.0.051184,32.463708. FTTH_10_M_O | Entebbe |  | Chrif |  |  | 6876800 | 1348992.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-25 | 7 | 7 | Delayed by Consolidation |  |  |  |  | 13
| VIOLAH GUMOSHABE. 256763293374. Kira road.0.318811,32.595311. FTTH_10_M_O | Ntinda (Bukoto) |  | Rak | 208750 | 186550 | 395300 | 643734 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-27 | 9 | 9 | System issue |  |  |  |  | 4
| NIWAMANYA RUTH. 256789166688. bombo road kalule zone.0.318811,32.595311. FTTH_20_M_O | Makerere |  | Rak | 1854500 | 140450 | 1994950 | 2821604.2 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-26 | 7 | 7 | Customer had civil works and we had ROW issues with Landloads |  |  |  |  | 4
| LUGOGO EVENTS AND ENTERTAINMENT LIMITED. 256775643513. lugogo.0.326668,32.606548. FTTH_40_M_O | Kololo | MTNFTTO15733751 | Rak | 1326246 | 157570 | 1483816 | 2038957.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-25 | 7 | 7 | ZTE Upgrade/Core issues |  |  |  |  | 4
| PETER NETUWA. 256782220622. king fahad.0.31577,32.576158. FTTH_20_M_O | Kampala Upper CBD | MTNFTTO44573623 | Rak | 208750 | 177610 | 386360 | 621599.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-26 | 6 | 6 | We had core challenges between Karobwa and Charm Towers and ROW issues between the building management |  |  |  |  | 5
| VIKAS KARAMWANI. 256763435778. Nakasero.0.321785,32.581011. FTTH_20_M_O | Nakasero Hill | MTNFTTO35860546 | Rak | 208750 | 219850 | 428600 | 663839.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-26 | 6 | 6 | Delayed due to Access to Workers House and system delay (Band Width) |  |  |  |  | 6
| SIAD HUSSEIN. 256788285900. kampala kabalagala.0.305899,32.591001. FTTH_10_M_O | Muyenga | MTNFTTO05721253 | Rontech | 789529 | 749552 | 1279578 | 1539081 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-28 | 8 | 8 | [5 empty] | 5
| RASHID ALI. 256774120578. salaam raod.0.318811,32.595311. FTTH_10_M_O | Ggaba | MTNFTTO30247152 | Rontech | 1721370 | 657133 | 2117725 | 2378503 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-04-26 | 6 | 6 | ROW issues |  |  |  |  | 6
| JULIUS TURIKYAROKI. 256770617727. bunamwaya.0.264913,32.546466. FTTH_10_M_O | Najjanankumbi (Lubowa - Lweza) | MTNFTTO85415812 | Rontech | 1987457 | 704433 | 2408844 | 2691890 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-26 | 7 | 7 | ROW issues |  |  |  |  | 20
| ROBERT LWANGA. 256772243476. masanafu senior school.0.318811,32.595311. FTTH_20_M_O | RUBAGA | MTNFTTO48886185 | Pavicon | 695982 | 368252 | 816160 | 1064234 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-27 | 3 | 3 | [5 empty] | 4
| ALI ABUBAKAR. 256761566150. mainstreet jinja.0.428828,33.209498. FTTH_10_M_O | Jinja | MTNFTTO33756114 | Enetworks | 1789339.6667 | 392061 | 1583089.6667 | 2181400.6667 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2 | 2 | [5 empty] | 10
| KENNETH WAAKO. 256760303622. Ntinda, Ministers Village.0.350605,32.615769. FTTH_10_M_O | Ntinda (Kyambogo - Min Village) | MTNFTTO77674832 | Soliton | 0 | 567218 | 347031 | 567218 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-25 | 1 | 1 | [5 empty] | 0
| JOHNBOSCO MWANGA NTENGO. 256789273355. Victoria street,Masaka Uganda.-0.34441,31.736624. FTTH_10_M_O | Masaka | MTNFTTO78010574 | Rontech | 1417466 | 629783 | 1932004 | 2147249 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-28 | 4 | 4 | [5 empty] | 6
| SHAFIK MUGUDA. 256761636166. Jinja, Uganda.0.318811,32.595311. FTTH_10_M_O | Jinja | MTNFTTO85084233 | Enetworks | 1789339.6667 | 392061 | 1583089.6667 | 2181400.6667 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2 | 2 | [5 empty] | 10
| Emmanuel Ojambo. 256779343733. Ntinda ministers village.0.350605,32.615769. FTTH_20_M_O | Ntinda (Kyambogo - Min Village) | MTNFTTO11754017 | Soliton | 1167910 | 370520 | 1097112 | 1538430 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-25 | 1 | 1 | [5 empty] | 0
| MARTIN MUYINGO. 256782317785. Kabuusu.0.297588,32.556365. FTTH_10_M_O | RUBAGA | MTNFTTO77074030 | Pavicon | 794376 | 410642 | 628246 | 1205018 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2 | 2 | [5 empty] | 4
| KENNEDY TENYWA. 256774546884. mainstreet jinja.0.428828,33.209498. FTTH_10_M_O | Jinja | MTNFTTO01261620 | Enetworks | 0 | 1295515 | 1066449 | 1295514.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-26 | 2 | 2 | [5 empty] | 12
| SAMUEL KINTU. 256771945925. Jinja, Uganda.0.432153,33.211919. FTTH_10_M_O | Jinja | MTNFTTO65266460 | Enetworks | 0 | 1200124 | 1007649 | 1221321.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-25 | 1 | 1 | [5 empty] | 4
| SYLIVIA NAMEGEMBE. 256786560936. bakuli.0.312933,32.564141. FTTH_20_M_O | RUBAGA | MTNFTTO86343250 | Pavicon | 424506 | 373752 | 545786 | 798258 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-25 | 0 | 0 | [5 empty] | 1
| MUGULA MUKALAZI GEORGE. 256772860695. Najjera1.0.38516,32.624919. FTTH_10_M_O | Ntinda (Kiwatule - Naalya ) | MTNFTTO58623054 | Soliton | 0 | 581304.2 | 341685 | 581304.2 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-26 | 1 | 1 | [5 empty] | 0
| DANIEL SENKUBUGE. 256779638084. najjanakumbi shell.0.285965,32.57045. FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) | MTNFTTO61771508 | Rontech | 861180 | 709394 | 1309796 | 1570574 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-26 | 1 | 1 | [5 empty] | 19
| BASHIR RUTASINGWA. 256760632395. nateete.0.297202,32.52667. FTTH_20_M_O | RUBAGA | MTNFTTO54680342 | Pavicon | 618266 | 376730 | 619586 | 994996 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-27 | 3 | 3 | [5 empty] | 8
| Faridah Ssebale. 256772196572. Nakasero.0.321785,32.581011. FTTH_20_M_O | Nakasero Hill | MTNFTTO68305424 | Rak | 208750 | 181470 | 390220 | 623261 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-27 | 3 | 3 | [5 empty] | 12
| ANGELLA BABIRYE. 256788787700. parliamentary avenue.0.318811,32.595311. FTTH_20_M_O | Kampala Upper CBD | MTNFTTO67112564 | Rak | 208750 | 162810 | 371560 | 606800 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-28 | 3 | 3 | [5 empty] | 5
| CONSOLATA KAREBA. 256772402341. Cafe javas.0.312605,32.585873. FTTH_10_M_O | Kampala Upper CBD | MTNFTTO11647362 | Rak | 208750 | 389572 | 367480 | 598322 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-28 | 3 | 3 | [5 empty] | 0
| YVONNE NAJJUMA. 256780527008. kulambiro.0.373612,32.606889. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO54527468 | Soliton | 0 | 543690.8 | 319623 | 543690.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-27 | 1 | 1 | [5 empty] | 0
| MARTIN KYANDA. 256778108054. Entebbe.0.051184,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO65320158 | Chrif |  |  | 909846 | 454625.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-28 | 2 | 2 | [5 empty] | 3
| Gerald Mijasi. 256779453165. bbina.0.318811,32.595311. FTTH_10_M_O | Luzira | MTNFTTO56361314 | Enetworks | 0 | 816140.6 | 587075 | 816140.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-27 | 1 | 1 | [5 empty] | 2
| EVA ALIGAWEESA.256788008143.Butikiro Road.0.310608,32.564316.FTTH_10_M_O | RUBAGA | MTNFTTO43157037 | Pavicon | 424506 | 369513 | 543746 | 794019 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-26 | 1 | 1 | [5 empty] | 0
| MARIA GORRET TUMUKUNDE.256763659457.mukono.0.354866,32.752014.FTTH_40_M_O | Mukono | MTNFTTO31408022 | Enetworks | 559502 | 639411 | 549510 | 1198912.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-19 | 2023-04-21 | 2023-04-28 | 14 | 9 | System error |  |  |  |  | 11
| DASCO.256786729192.kyanja.0.395861,32.593671.FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO28561280 | Soliton | 1815201 | 388610 | 1509936 | 2203811 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-26 | 1 | 1 | [5 empty] | 0
| null null.256781091526.bunamwaya.0.264913,32.546466.FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) | MTNFTTO80384261 | Rontech | 887819 | 649895 | 1251825 | 1537714 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-21 | 2023-04-15 | 2023-04-17 | 2023-04-26 | 36 | 11 | [5 empty] | 15
| Nakalembe Bridget.256770954080.entebbe.0.051184,32.463708.FTTH_40_M_O | Entebbe | MTNFTTO15143216 | Chrif | 867700 | 815326.6 | 1011306 | 1683026.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-04-25 | 7 | 7 | No Power |  |  |  |  | 2
| SHARON KANSIIME. 256786452147. bweyogerere.0.348194,32.661714. FTTH_10_M_O | Bweyogerere | MTNFTTO00028281 | Enetworks | 1524079 | 436870.5 | 1524079 | 1960949.5 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-28 | 2 | 2 | [5 empty] | 3
| ABDURAHMAN BEETONDA. 256772734460. Masaka.-0.326738,31.75374. FTTH_10_M_O | Masaka | MTNFTTO52566570 | Rontech | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-04-28 | 1 | 1 | [5 empty] | 10
| DENNIS KISAKYE KAMUGISHA. 256776031511. Namugongo bataka lane.0.385062,32.647526. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO05231703 | Soliton | 0 | 5651455.6 | 338891 | 5651455.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-04-28 | 1 | 1 | [5 empty] | 13
| DERRICK ASHABA. 256789245976. Bombo road Nankulabye. 0.325023,32.560569.FTTH_10_M_O | MAKERERE | MTNFTTO73380033 | Pavicon | 819376 | 385208 | 641006 | 1204584 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-27 | 2023-04-29 | 2023-04-27 | 7 | 0 | [5 empty] | 23
| SUSAN ARYAHEEBWA.256772326083.mbarara,uganda.-0.60716,30.654502. FTTH_10_M_O | Mbarara | MTNFTTO14486555 | Rontech | 1461076 | 563894 | 1805415 | 2024970 | Office Internet | 0 | Done | Office Internet (On air) | 2023-03-16 | 2023-04-26 | 2023-04-28 | 2023-04-27 | 42 | 1 | [5 empty] | 5
| ALVIN OTIM.256775793272.Kira:Namugongo Road.0.396151,32.659344.FTTH_10_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO60353475 | Enetworks | 2425309 | 524131 | 1819949 | 2949440 | Office Internet | 0 | Done | Office Internet (On air) | 2022-11-08 | 2023-04-17 | 2023-04-19 | 2023-04-27 | 170 | 10 | Initially client had a high BOQ so we had to put him on hold as we look for clients around. The high BOQ |  |  |  |  | 14
| SUSAN NAKISUYI.256772954676.naalya.0.370209,32.637636.FTTH_10_M_O | Ntinda (Kyambogo - Min Village) | MTNFTTO83601214 | Soliton | 0 | 568959.8 | 326910 | 568959.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-26 | 0 | 0 | [5 empty] | 2
| JENIFFER MUSIMENTA.256784172247.entebbe.0.051184,32.463708.FTTH_10_M_O | Entebbe | MTNFTTO71386304 | Chrif |  | 5843356 | 451585.6 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-15 | 2023-04-19 | 2023-04-21 | 2023-04-28 | 13 | 9 | Consolidation - Delayed due to high BOQ |  |  |  |  | 0
| YOHANA TESFAMARIAM.256783644303.Location.0.318811,32.595311.FTTH_20_M_O | Najjanankumbi (Lubowa - Lweza) | MTNFTTO66783060 | Rontech | 789529 | 781798 | 1323552 | 1571327 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-12 | 2023-04-25 | 2023-04-27 | 2023-04-28 | 16 | 3 | [5 empty] | 8
| FELISHINA MUTHONI WAWERU. 256784605329. nsabya.0.300136,32.59379. FTTH_20_M_O | Nsambya |  | Rontech |  |  |  | 0 | Office Internet |  | Done | Office Internet (On air) | 2023-03-29 | 2023-03-29 | 2023-03-31 | 2023-04-29 | 31 | 31 | Mobilizing to start Civil works |  |  |  |  | 7
| DINESH BHIMJI PINDORIYA. 256761605279. makerere.0.332635,32.568586. FTTH_20_M_O | Makerere |  | Chrif | 1341300 | 902479 | 2243779 | 2582794.6 | Office Internet | 14 | Done | Office Internet (On air) | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-05-02 | 20 | 6 | W.I.P, Pysical installations Done, requested comissioning for 25/04/23 |  |  |  |  | 6
| ABDU GANNIYU BAKULUMPAGI. 256788544937. lyamutundwe.0.104767,32.512901. FTTH_10_M_O | Kitala |  | Chrif | 2292266.6667 | 449664 | 2163527 | 2741930.6667 | Office Internet | 8 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-28 | 11 | 3 | Consolidation in Mpala, waiting for the 3rd person to pay |  |  |  |  | 32
| DICKSON NIWAMPEIRE. 256779825230. zana stage.0.318811,32.595311. FTTH_10_M_O | Najjanankumbi (Lubowa - Lweza) |  | Rontech | 1637479 | 814061 | 2186173 | 2451540 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-04-29 | 12 | 12 | Customer doesn't pick calls |  |  |  |  | 6
| WILFRED TUKAMUSHABA. 256783141488. Bunga.0.318811,32.595311. FTTH_10_M_O | Ggaba |  | Rontech | 1906427 | 714760 | 2391370 | 2621186 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-04-18 | 2023-04-20 | 2023-05-01 | 13 | 13 | Customer had an existing service |  |  |  |  | 8
| STEPHEN MUGISHA. 256785597307. Julaina Complex.0.318811,32.595311. FTTH_10_M_O | Old parl | MTNFTTO55366126 | Soliton | 208750 | 177090 | 385840 | 636473 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-04-29 | 10 | 10 | System issue |  |  |  |  | 0
| SERAPHINO OGOLA. 256786925555. salaama road munyonyo.0.24661,32.614256. FTTH_10_M_O | Ggaba | MTNFTTO44120642 | Rontech | 1851370 | 767621 | 2358213 | 2618991 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-21 | 2023-04-21 | 2023-04-23 | 2023-04-29 | 8 | 8 | ROW with the Landlord |  |  |  |  | 8
| Ashiraf Musisi. 256778229190. ntinda hardware world.0.350605,32.615769. FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) | MTNFTTO28284362 | Soliton | 1190040 | 373922 | 1079742 | 1563962 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-22 | 2023-04-22 | 2023-04-24 | 2023-04-28 | 6 | 6 | ZTE upgrade |  |  |  |  | 1
| MOSES SERUMA. 256775062190. nkumba university.0.095128,32.506873. FTTH_10_M_O | ENTEBBE | MTNFTTO81178844 | Pavicon | 233750 | 416645 | 404520 | 650395 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-04-30 | 6 | 6 | Re-assigned to us from chrif group- Lack of cores from Entebbe plot 17 |  |  |  |  | 1
| . 256786457003. bugolobi.0.309722,32.625765. FTTH_20_M_O | Bugolobi | MTNFTTO38145583 | Enetworks | 1126371 | 414130.6 | 1064849 | 1540501.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-04-28 | 3 | 3 | [5 empty] | 14
| . 256785833696. muyenga.0.296898,32.615028. FTTH_20_M_O | Muyenga | MTNFTTO86721747 | ROntech | 789529 | 703001 | 1209572 | 1492530 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-05-01 | 6 | 6 | ROW issue |  |  |  |  | 10
| BONIFANCE ODUBURU. 256772648744. bakuli.0.312933,32.564141. FTTH_20_M_O | RUBAGA | MTNFTTO60548017 | Pavicon | 2527442 | 505558 | 2447802 | 3033000 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-05-01 | 6 | 6 | Survey Appointment was on 29-april, Quotation approved on 1-may, installation completed on 1-may |  |  |  |  | 3
| Annet Dianah Bwamiki. 256785854872. namugongo janda.0.385062,32.647526. FTTH_10_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO78687653 | Soliton | 1504259.6667 | 255960 | 1212601.3333 | 1760219.6667 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-29 | 3 | 3 | [5 empty] | 0
| DAUDI LUSWATA. 256787328614. namugongo janda.0.385062,32.647526. FTTH_10_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO56511634 | Soliton | 1504259.6667 | 255960 | 1212601.3333 | 1760219.6667 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-04-30 | 4 | 4 | [5 empty] | 8
| ESTHER AWORI. 256784868886. kisasi.0.361441,32.596655. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO68123236 | Soliton | 0 | 551283.8 | 322113 | 551283.8 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-04-28 | 1 | 1 | [5 empty] | 0
| MATAYO WAMOKA. 256783891377. bakuli.0.312933,32.564141. FTTH_20_M_O | RUBAGA | MTNFTTO01382816 | Pavicon | 2521326 | 355535 | 2004376 | 2876861 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-04-29 | 2 | 2 | [5 empty] | 9
| FERNANDO OPIFEERA. 256781792785. Namere.0.383356,32.57661. FTTH_20_M_O | Gayaza | MTNFTTO37503870 | Soliton | 1404819 | 402614 | 1558093 | 1807433 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-04-29 | 2 | 2 | [5 empty] | 2
| Taddeo Aliganyira. 256784099665. Kabuusu, Rubaga, Kampala.0.297588,32.556365. FTTH_20_M_O | RUBAGA | MTNFTTO87336302 | Pavicon | 233750 | 407285 | 395160 | 641035 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-28 | 2023-04-28 | 2023-04-30 | 2023-04-29 | 1 | 1 | [5 empty] | 13
| BRIAN NABONGHO. 256788333509. ndeeba.0.292993,32.564796. FTTH_20_M_O | RUBAGA | MTNFTTO32864524 | Pavicon | 662070 | 397925 | 814120 | 1212045 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-28 | 2023-04-28 | 2023-04-30 | 2023-04-29 | 1 | 1 | [5 empty] | 2
| HASSAN MUTAGUBYA.256787072745.entebbe.0.051184,32.463708.FTTH_10_M_O | Entebbe | MTNFTTO02338266 | Chrif |  |  | 399506 | 448220.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-04-30 | 1 | 1 | [5 empty] | 2
| Jim Matsiko.256774810012.Mutundwe.0.280748,32.540416.FTTH_20_M_O | RUBAGA | MTNFTTO27656765 | Pavicon | 233750 | 407285 | 395160 | 641035 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-27 | 2023-04-29 | 2023-04-29 | 10 | 2 | [5 empty] | 1
| FRANK KIBERU. 256775930087. Nakulabye Namirembe Parents Sch.0.321971,32.557093. FTTH_40_M_O | MAKERERE | MTNFTTO34411235 | Pavicon | 233750 | 360656 | 372720 | 594406 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-30 | 2023-04-30 | 2023-05-02 | 2023-05-01 | 1 | 1 | [5 empty] | 1
| PHIONA KUSINGURA. 256783276026. Kyanja.0.395861,32.593671. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO35055231 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-02 | 1 | 1 | [5 empty] | 0
| NISHIT JOSHI. 256773280251. mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara | MTNFTTO35861008 | ROntech | 0 | 1124537 | 1124537 | 1366448 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-02 | 1 | 1 | [5 empty] | 15
| TONNY TUMWESIGYE.56784979572.kamamboga.0.378287,32.586953.FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO73767481 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-28 | 2023-04-30 | 2023-05-02 | 8 | 4 | [5 empty] | 3
| Asasira Flavia.256772692231.kyanja.0.395861,32.593671.FTTH_20_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO71215244 | Soliton | 0 | 584266.9 | 359277 | 584266.9 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-01 | 0 | 0 | [5 empty] | 0
| CAROLINE NADUNGA. 256788121244. Mpererwe.0.381891,32.576158. FTTH_20_M_O | Gayaza |  | Enetworks |  |  |  | 2297167 | Office Internet | 25 | Done | Office Internet (On air) | 2023-03-28 | 2023-03-28 | 2023-03-30 | 2023-05-04 | 37 | 12 | To be commissioned in May |  |  |  |  | 4
| DOREEN ATUKUNDA. 256784444822. old taxi park.0.312572,32.576351. FTTH_20_M_O | Old Park |  | Rak | 208750 | 465025 | 427540 | 673774 | Office Internet | 13 | Done | Office Internet (On air) | 2023-04-12 | 2023-04-12 | 2023-04-14 | 2023-05-04 | 22 | 9 | Not picking standrad sms sent |  |  |  |  | 5
| ABDULSAID WALID. 256774081064. Total bwaise kikoni.0.342714,32.561313. FTTH_20_M_O | Makerere | MTNFTTO68303274 | Rak | 1190066 | 366734 | 1049296 | 1556799.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-05-04 | 14 | 14 | Commissioning ongoing |  |  |  |  | 3
| RITAH NABYATO. 256786573374. Nasser road.0.318811,32.595311. FTTH_10_M_O | Kampala Upper CBD | MTNFTTO02288285 | Rak | 208750 | 341195 | 325700 | 549944 | Office Internet | 8 | Done | Office Internet (On air) | 2023-04-20 | 2023-04-20 | 2023-04-22 | 2023-05-03 | 13 | 5 | Physicall connections done, affected by FAT installation to resolve Core Issues |  |  |  |  | 10
| ABDU MONDAY. 256772409982. buziga.0.318811,32.595311. FTTH_10_M_O | Ggaba | MTNFTTO73706071 | Rontech | 1281963 | 600245 | 1640855 | 1882209 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-22 | 2023-04-24 | 2023-04-26 | 2023-05-03 | 11 | 9 | [5 empty] | 15
| HENRY KASULE SSEKITTO. 256772429394. Katwe.0.298357,32.57515. FTTH_40_M_O | Old Park | MTNFTTO47166010 | Rak | 1825256 | 370812 | 1965226 | 2196067 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-05-04 | 10 | 10 | [5 empty] | 3
| SANDRA EDITH LUNKUSE. 256781384227. Muyenga Bukasa.0.296898,32.615028. FTTH_20_M_O | Muyenga | MTNFTTO00220378 | ROntech | 2131859 | 769302 | 2611884 | 2901161 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-05-02 | 13 | 13 | [5 empty] | 13
| SUNNIVA HAABERG. 256762980717. Muyenga.0.296898,32.615028. FTTH_20_M_O | Muyenga | MTNFTTO30573436 | ROntech | 1336924 | 666709 | 1701455 | 2003633 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-05-03 | 8 | 8 | [5 empty] | 10
| BETTY ACHOLA. 256772089342. bugolobi.0.309722,32.625765. FTTH_20_M_O | Bugolobi | MTNFTTO12682838 | Enetworks | 3546548 | 436120.6 | 915620 | 3982668.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-05-05 | 9 | 9 | [5 empty] | 4
| . 256786615150. Mukwano mall.0.318811,32.595311. FTTH_10_M_O | Old Park | MTNFTTO56210633 | Rak | 208750 | 402650 | 376160 | 611399 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-05-05 | 9 | 9 | [5 empty] | 5
| PAUL AKOL. 256783829154. bukasa.0.29886,32.62068. FTTH_10_M_O | Muyenga | MTNFTTO53013160 | Rontech | 1042441.5 | 340981 | 1269797 | 1383422.5 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-04-26 | 2023-04-28 | 2023-05-05 | 9 | 9 | [5 empty] | 13
| RITAH NABBANJA. 256786784988. naalya.0.370209,32.637636. FTTH_10_M_O | Ntinda (Kyambogo - Min Village) | MTNFTTO08516758 | Soliton |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-05-03 | 6 | 6 | [5 empty] | 4
| ANDREW KIRUNGI. 256789774072. fort portal, Uganda.0.652728,30.274694. FTTH_10_M_O | Fort portal | MTNFTTO12671035 | Chrif |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-27 | 2023-04-27 | 2023-04-29 | 2023-05-02 | 5 | 5 | [5 empty] | 8
| JANI BHAVESH KUMAR GORDHANBHAI. 256776077625. Bukoto.0.350525,32.595242. FTTH_10_M_O | Ntinda (Kiwatule - Naalya ) | MTNFTTO30574142 | Soliton |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-05-03 | 4 | 4 | [5 empty] | 15
| RHONIE SENYONJO. 256789274772. greatlakeshouse.0.318811,32.595311. FTTH_10_M_O | Makerere | MTNFTTO76338575 | Rak | 922046 | 690538 | 1435176 | 1612584 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-05-05 | 6 | 6 | [5 empty] | 2
| GRACE KORUTARO. 256781908009. nsyamba.0.318811,32.595311. FTTH_20_M_O | NSAMBYA | MTNFTTO83777202 | Pavicon | 233750 | 382733 | 388200 | 616483 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-05-03 | 4 | 4 | [5 empty] | 0
| Simon Sserugo. 256787718618. bugolobi.0.309722,32.625765. FTTH_10_M_O | Bugolobi | MTNFTTO23055801 | Enetworks | 0 | 436870.5 | 1524079 | 1960949.5 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-05-02 | 3 | 3 | [5 empty] | 4
| ISAAC KIWANUKA. 256778207531. Kawuku Entebbe road.0.064689,32.474436. FTTH_10_M_O | Entebbe | MTNFTTO06326607 | Chrif | 0 |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-30 | 2023-04-30 | 2023-05-02 | 2023-05-04 | 4 | 4 | [5 empty] | 2
| CECILA NAMONO. 256762184241. Salama road.0.318811,32.595311. FTTH_20_M_O | Ggaba | MTNFTTO53858288 | Rontech | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-04 | 3 | 3 | [5 empty] | 15
| PETER NETUWA. 256775649033. akright bwebajja.0.318811,32.595311. FTTH_10_M_O | Ntinda (Kyambogo - Min Village) | MTNFTTO45635365 | Soliton |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 4 | 4 | [5 empty] | 5
| najima ahmed. 256780450325. ssemundu lukuli road.0.318811,32.595311. FTTH_40_M_O | MAKERERE | MTNFTTO51541743 | Pavicon |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-04 | 3 | 3 | [5 empty] | 0
| CHARITY RAPHAEL KABUYE. 256760485634. Full gospel church Makerere.0.318811,32.595311. FTTH_10_M_O | MAKERERE | MTNFTTO80817551 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-03 | 1 | 1 | [5 empty] | 2
| JUDITH NABIMANYA. 256774529528. ntinda.0.350605,32.615769. FTTH_10_M_O | Gayaza | MTNFTTO58674888 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-03 | 1 | 1 | [5 empty] | 0
| Allan Kato. 256786789932. nsambya.0.29722,32.585224. FTTH_10_M_O | NSAMBYA | MTNFTTO70035572 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-03 | 1 | 1 | [5 empty] | 0
| Henry Kiryagana. 256779955985. bugembe stadium.0.318811,32.595311. FTTH_10_M_O | Jinja | MTNFTTO08238006 | Enetworks | 1199129 | 457523.6 | 1445179 | 1656652.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-04 | 2 | 2 | [5 empty] | 7
| MUBIRU WORSHIPPER. 256774426527. Mutundwe.0.280748,32.540416. FTTH_10_M_O | RUBAGA | MTNFTTO06120036 | Pavicon | 2495436 | 385874 | 2039056 | 2881310 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-05 | 3 | 3 | [5 empty] | 9
| BERNARD ONYANGO. 256786949463. Namataba kirinya.0.332705,32.674279. FTTH_10_M_O | Bweyogerere | MTNFTTO42083138 | Enetworks | 1385709 | 481722.6 | 1372699 | 1867431.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-05 | 3 | 3 | [5 empty] | 3
| JERRY KIPLANGAT. 256786019825. Full gospel church Makerere.0.318811,32.595311. FTTH_10_M_O | MAKERERE | MTNFTTO77184600 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-03 | 0 | 0 | [5 empty] | 2
| BRIAN LUTAAYA. 256789566944. Kasubi Market. . FTTH_10_M | MAKERERE | MTNFTTH25310421 | Pavicon | 1508366 | 322723.5 | 1334756 | 1831089.5 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-03 | 2023-05-04 | 2023-05-03 | 1 | 0 | [5 empty] | 17
| BRIAN IVAN LUTAAYA. 256787987255. Cheap General Hardware. . FTTH_10_M | MAKERERE | MTNFTTH02552172 | Pavicon | 1508366 | 322723.5 | 1334756 | 1831089.5 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-03 | 2023-05-04 | 2023-05-03 | 2 | 0 | [5 empty] | 17
| ABDUL-ABDU MUGABE. 256777239512. main street jinja.0.431225,33.210953. FTTH_10_M_O | Jinja | MTNFTTO34876115 | Enetworks | 1199129 | 457523.6 | 1445179 | 1656652.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-05 | 4 | 4 | [5 empty] | 22
| SENKUMBA SOPHIA. 256772420253. Lumumba avenue.0.318811,32.595311. FTTH_20_M_O | Nakasero Hill | MTNFTTO31601064 | Rak | 208750 | 425650 | 399160 | 634399 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-04 | 1 | 1 | [5 empty] | 2
| Mushega Amanya. 256760264464. katwe, makindye division.0.301667,32.576425. FTTH_40_M_O | MAKINDYE | MTNFTTO24848433 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-04 | 1 | 1 | [5 empty] | 18
| SAMUEL SSENDI. 256779265701. Kireka, Uganda.0.337484,32.646896. FTTH_10_M_O | Bweyogerere | MTNFTTO12438666 | Enetworks | 826943 | 574120.6 | 945173 | 1401063.6 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-04 | 1 | 1 | [5 empty] | 11
| ABBAS SEKYANZI MULUUBYA.256772262726.Luteete.0.318811,32.595311.FTTH_10_M_O | Gayaza | MTNFTTO62085620 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-05-04 | 10 | 10 | [5 empty] | 6
| Richard Rujumba.256782582377.fortpotal.0.652806,30.275517.FTTH_10_M_O | Fort portal | MTNFTTO70336230 | Rontech | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-02 | 0 | 0 | [5 empty] | 9
| IMMACULATE LENIA.256772271139.fort portal.0.318811.32.595311.FTTH_10_M_O | Fort portal | MTNFTTO85182213 | Rontech | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-02 | 0 | 0 | [5 empty] | 7
| WAISWA JOSHUA.256771806549.entebbe.0.051184,2.463708.FTTH_10_M_O | Entebbe | MTNFTTO36182230 | Chrif | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-02 | 2023-05-02 | 0 | 0 | [5 empty] | 0
| DENNIS BATABAIRE.256780198735.Jinja:Nile Avenue.0.434613,33.206651.FTTH_20_M_O | Jinja | MTNFTTO83508607 | Enetworks | 1827300 | 505921.6 | 1901150 | 2333221.6 | Office Internet | 0 | Done | Office Internet (On air) | 2022-05-17 | 2023-04-19 | 2023-04-21 | 2023-05-04 | 352 | 15 | [5 empty] | 16
| EDMOND TAMALE.256775468209.Ntinda Kigowa Road.0.350605,32.615769.FTTH_10_M_O | Ntinda (Kiwatule - Naalya ) | MTNFTTO23705182 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-18 | 2023-05-03 | 2023-05-05 | 2023-05-03 | 15 | 0 | [5 empty] | 2
| JIM MUHUMUZA. 256772061612. kiwatule.0.3652976,32.6249195. FTTH_20_M_O | Ntinda (Kiwatule - Naalya ) | MTNFTTO20013717 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-05 | 1 | 1 | [5 empty] | 0
| JOYCE TURYAGYENDA. 256763484425. lubaga.0.3087385,32.5479178. FTTH_10_M_O | RUBAGA | MTNFTTO87625485 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-05 | 1 | 1 | [5 empty] | 2
| EMMANUEL TUMUSIIME.256772458935.Jinja road.0.3188106.32.5953111.FTTH_10_M_O | Kampala Upper CBD | MTNFTTO70235873 | Rak | 208750 | 556284 | 565636 | 765034 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-04 | 0 | 0 | [5 empty] | 5
| null null. 256762429152. Bwebajja:Kitende.0.058778,32.473499 . FTTH_20_M_O |  |  | Chrif |  |  |  | 9124566.2/2 | Office Internet | 9 | Done | Office Internet (On air) | 2023-01-04 | 2023-01-07 | 2023-01-09 | 2023-05-05 | 121 | 109 | Pending Neighbors payment - Consolidated BOQ/Customer to communicate when ready for commissioning, Physical installations and traffic routing done, Client to communicate when ready to be commissioned
| null null. 256776291440. Bwebajja:Arkright City.0.353464,32.613416.FTTH_20_M_O |  |  | Chrif |  |  |  | 8117164.2 | Office Internet | 0 | Done | Office Internet (On air) | 2023-01-03 | 2023-01-05 | 2023-01-07 | 2023-05-05 | 122 | 120 | Customer to communicate when ready for commissioning
| SAMSOM BAGANDA. 256776455630. entebbe road.0.051184,32.463708. FTTH_10_M_O |  |  | Chrif |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-14 | 2023-04-14 | 2023-04-16 | 2023-05-08 | 24 | 24 | In Kampala, Client was not available. survey scheduled for Tuesday 25/04/23
| MICHAEL MEMBE. 256787629628. mulago hospital.0.340376,32.572711. FTTH_10_M_O | Makerere |  | Chrif | 229150 | 213700 | 442850 | 963230.6 | Office Internet | 7 | Done | Office Internet (On air) | 2023-04-17 | 2023-04-17 | 2023-04-19 | 2023-05-08 | 21 | 14 | says we hold on the commissioning until he occupied the premises. He's in the process of shifting to this new home.
| PATRICIA MADAYA. 256393256678. Mbalwa.0.365182,32.653176. FTTH_10_M_O |  | MTNFTTO16844671 | Enetworks | 2444129 | 425623 | 1976149 | 2869752 | Office Internet | 10 | Done | Office Internet (On air) | 2023-04-24 | 2023-04-24 | 2023-04-26 | 2023-05-06 | 12 | 2 | ROW |  |  |  |  | 12
| . 256789202281. kisasi.0.361441,32.596655. FTTH_10_M_O |  | MTNFTTO70522684 | Soliton |  |  |  | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-05-06 | 7 | 7 | [5 empty] | 0
| GRACE KORUTARO. 256773284046. communication house.0.318811,32.595311. FTTH_20_M_O | Muyenga | MTNFTTO85562441 | ROntech | 990779 | 519554 | 1262558 | 1510333 | Office Internet | 7 | Done | Office Internet (On air) | 2023-04-29 | 2023-04-29 | 2023-05-01 | 2023-05-06 | 7 | 0 | [5 empty] | 5
| Kakuba Anna.256784999312.entebbe.0.051184,32.463708. FTTH_20_M_O | Muyenga | MTNFTTO33614442 | Rontech | 789529 | 719867 | 1244029 | 1509396 | Office Internet | 8 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-09 | 8 | 0 | Client will communicate (Customer delay) |  |  |  |  | 10
| SURESH KARSAN VEKARIYA. 256777395575. Mbarara.-0.60716,30.654502. FTTH_20_M_O | Mbarara | MTNFTTO01633080 | Rontech | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-10 | 9 | 9 | Damaged Route
| . 256772713960. Buziga,.0.269005,32.616445. FTTH_20_M_O | Ggaba | MTNFTTO83422828 | Rontech | 1224129 | 746405 | 1687576 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-10 | 8 | 8 | Contractor delay |  |  |  |  | 18
| KARIMBHAI SALIMBHAI SAYANI. 256787787787. Lira Uganda.0.318811,32.595311. FTTH_10_M_O |  | MTNFTTO72466185 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-07 | 5 | 5 | [5 empty] | 0
| Atukunda Daphine. 256787888805. church rd.0.318811,32.595311. FTTH_40_M_O | Entebbe | MTNFTTO32565847 | Chrif | 2703453 | 377598.1 | 2327978 | 3081051.1 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-07 | 6 | 5 | Clients are 1.3km from the fiber, extra 2 clients are needed for consolidation. |  |  |  |  | 12
| Atukunda Daphine. 256775636093. church rd.0.318811,32.595311. FTTH_40_M_O | Entebbe | MTNFTTO12556776 | Chrif | 2703453 | 377598.1 | 2327978 | 3081051.1 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-01 | 2023-05-01 | 2023-05-03 | 2023-05-07 | 6 | 5 | Clients are 1.3km from the fiber, extra 2 clients are needed for consolidation. |  |  |  |  | 11
| DAUDI MWESIGWA ASIIMWE. 256784101593. Ntinda complex.0.352805,32.614586. FTTH_20_M_O | Ntinda (Bukoto) | MTNFTTO22825382 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-08 | 5 | 5 | Mobilizing to start Civil works
| SHAWALI BUGEMBE. 256782574733. enteebe.0.051184,32.463708. FTTH_40_M_O | Entebbe | MTNFTTO23463257 | Chrif | 2703453 | 377598.1 | 2327978 | 3081051.1 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 4 | 3 | Clients are 1.3km from the fiber, extra 2 clients are needed for consolidation. |  |  |  |  | 12
| WYCLIFF SSERUYANGE. 256776481318. Freedom city.0.318811,32.595311. FTTH_20_M_O | Najjanankumbi | MTNFTTO67030801 | Rontech | 1460121 | 561415 | 1775227 | 2021536 | Office Internet | 4 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-08 | 5 | 1 | ROW |  |  |  |  | 25
| Ahmed Sadak. 256774600556. Butikiro road, kisenyi.0.310608,32.564316. FTTH_20_M_O |  | MTNFTTO85105462 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-07 | 4 | 3 | Contact currently off |  |  |  |  | 2
| EMMANUELA KUNIHIRA. 256777013221. walusimbi's garage.0.318811,32.595311. FTTH_20_M_O | Kololo | MTNFTTO16641030 | Rak | 208750 | 423390 | 396900 | 632140 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-08 | 5 | 5
| AFUSWA KALUNGI. 256786450224. Kampala industrial area.0.350605,32.615769. FTTH_40_M_O | Bugolobi | MTNFTTO58652136 | Enetworks | 0 | 916292 | 588275 | 916292 | Office Internet | 5 | Done | Office Internet (On air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-09 | 7 | 2 | Done |  |  |  |  | 4
| RONNY OKECHA. 256786356986. Kisaasi, Kampala.0.356946,32.612645. FTTH_10_M_O | Kisaasi | MTNFTTO17136127 | Soliton | 0 | 775939.4 | 536320 | 775939.4 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-05 | 2 | 2 | [5 empty] | 0
| Nabukwasi Sarah. 256782051568. Kireka.0.3374838,32.6468956. FTTH_10_M_O | Bweyogerere | MTNFTTO44880328 | Enetworks | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-08 | 4 | 4
| SHAMIM BIRABWA. 256774051741. ndeba.0.292853,32.5652468. FTTH_20_M_O | Ndeeba | MTNFTTO61172018 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-07 | 3 | 3 | [5 empty] | 0
| MOREEN KYEYAMWA. 256774892197. Jinja mainstreet.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO23073882 | Enetworks | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-06 | 2 | 2 | [5 empty] | 7
| GLORIA ANENA. 256774059202. kireka.0.3374838,32.6468956. FTTH_20_M_O | Bweyogerere | MTNFTTO54502155 | 1698209 | 484130.6 | 1651149 | 2182339.6 | TBC | Office Internet | 5 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-09 | 5 | 0 | Core provisioning ongoing |  |  |  |  | 6
| BRIGHT MWEBESA. 256788104802. mbarara uganda.-0.6071596,30.6545022. FTTH_10_M_O | Mbarara | MTNFTTO88004417 | Rontech | 2090779 | 495166 | 2364558 | 2585945 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-07 | 3 | 3 | Contractor Delay |  |  |  |  | 4
| . 256773656414. kira road.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO22207017 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-09 | 5 | 5
| Monica Namuwonge. 256771326500. Entebbe road.0.0511839,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO63438301 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-09 | 5 | 5
| JUKAS CONSTRUCTION LIMITED. Kololo Green Top Villas. 0.331855,32.588869. FTTH_20 |  | MTNFTTP87606187 | Rak | 208750 | 133410 |  | TBC | Office Internet ( Postpaid) | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-05-06 | 2023-05-08 | 2023-05-08 | 14 | 2
| PANAGIOTIS KARAKITSOS. 256787212979. Entebbe.0.069238,32.465696. FTTH_10_M_O | Entebbe | MTNFTTO42083240 | Chrif | 1989639.5 | 430730.6 | 1737839.5 | 2420370.1 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-03 | 2023-05-03 | 2023-05-05 | 2023-05-08 | 5 | 5
| OMAR SEBUNYA. 256761678515. namanve.0.3552961,32.6924934. FTTH_10_M_O | Mukono | MTNFTTO32836220 | Enetworks | 2563429 | 475125.5 | 1966679 | 3038554.5 | Office Internet | 4 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-09 | 4 | 0 | [5 empty] | 10
| Agatha Verdin. 256763365725. kololo.0.327297,32.5949199. FTTH_20_M_O | Kololo | MTNFTTO33432642 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 3 | 3
| QASIM MOHAMED ABDI. 256775875895. kisasi.0.3614407,32.5966549. FTTH_10_M_O |  | MTNFTTO46026314 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 3 | 3
| AMBROSE ONGOM. 256773401026. kirinya.0.3422655,32.660715. FTTH_10_M_O | Bweyogerere | MTNFTTO48763760 | Enetworks | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 3 | 3
| FAITH MPIRIRWE. 256771266572. kisemeti.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO01220331 | Rak | 0 | 0 | 0 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-09 | 4 | 4
| DICKSON MWEBAZE. 256781250246. mbarara uganda.-0.6071596,30.6545022. FTTH_10_M_O | Mbarara | MTNFTTO67861066 | Rontech | 0 | 771233 | 564505 | 771233 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-06 | 1 | 1 | [5 empty] | 0
| CEDRICK MUTEKANGA. 256773973338. Majwala Road.0.3188106,32.5953111. FTTH_10_M_O | Kiwatule | MTNFTTO37735172 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 3 | 3 | Optical power issue.
| DAVIS AGABA. 256761601093. buwate.0.4050592,32.6192672. FTTH_10_M_O |  | MTNFTTO28485712 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-07 | 2 | 2 | [5 empty] | 0
| Odur Nathan Ivan. 256783610265. kulambiro.0.3736122,32.6068891. FTTH_10_M_O | Kisaasi (Kyanja - Kulambiro) | MTNFTTO63716402 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-06 | 1 | 1 | [5 empty] | 0
| SALAMAH NAMUTEBI. 256772946527. nateete.0.2972025,32.5266698. FTTH_10_M_O |  | MTNFTTO23350506 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-05 | 2023-05-07 | 2023-05-08 | 3 | 3
| MILDRED NAYIGA.256774360578.kirinya.0.342266,32.660715.FTTH_10_M_O | Bweyogerere | MTNFTTO06473468 | Enetworks | 2919094.5 | 445424.5 | 2495834.5 | 3364519 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-26 | 2023-05-04 | 2023-05-06 | 2023-05-08 | 12 | 4
| ROBERT HABYARIMANA.256784506009.mbarara uganda.-0.60716,30.654502.FTTH_20_M_O | Mbarara | MTNFTTO14381150 | Rontech | 1483785 | 650634 | 1914864 | 2134419 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-24 | 2023-05-02 | 2023-05-04 | 2023-05-05 | 11 | 3 | Contractor delay |  |  |  |  | 11
| EMMANUEL OKWAJA. 256782144814. Kireka.0.3374838,32.6468956. FTTH_10_M_O | Bweyogerere | MTNFTTO11065435 | Enetworks | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-06 | 2023-05-06 | 2023-05-08 | 2023-05-07 | 1 | 1 | [5 empty] | 0
| NANTONGO ZUBEDA. 256772383525. Nateete.0.2972025,32.5266698. FTTH_10_M_O |  | MTNFTTO30744614 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-06 | 2023-05-06 | 2023-05-08 | 2023-05-08 | 2 | 2
| ISMA SSENYONJO. 256787865520. kitebi.0.2733322,32.5471733. FTTH_10_M_O |  | MTNFTTO60708860 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-06 | 2023-05-06 | 2023-05-08 | 2023-05-09 | 3 | 3
| NUSIFA NABUKALU. 256771564107. kitebi.0.2733322,32.5471733. FTTH_10_M_O |  | MTNFTTO41731361 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-06 | 2023-05-06 | 2023-05-08 | 2023-05-09 | 3 | 3
| HADIJAH NANSUMBA. 256783218829. tervan woods kabusu rubaga.0.2969407,32.553134. FTTH_10_M_O | Rubaga | MTNFTTO83771234 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-06 | 2023-05-06 | 2023-05-08 | 2023-05-07 | 1 | 1 | [5 empty] | 0
| MASHOOD KABANDA. 256775616347. Jinja , Uganda.0.3188106,32.5953111. FTTH_10_M_O | Jinja | MTNFTTO71653247 | Enetworks | 0 | 2133302.6 | 1021829 | 2133302.6 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-05 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 4 | 0 | To be commissioned today |  |  |  |  | 14
| ALEX SSEMAMBO. 256772699342. Entebbe kitala.0.0511839,32.463708. FTTH_10_M_O | Entebbe | MTNFTTO63757247 | Chrif | 0 | 351300 | 351300 | 580365 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 1 | 1 | Delayed HLS |  |  |  |  | 0
| KELLY ATUNGOZA. 256761846933. ntinda.0.350605,32.6157688. FTTH_10_M_O | Ntinda | MTNFTTO65133644 | Rak | 0 | 0 | 0 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 1 | 1
| RAYMOND NAMISAANO. 256772462578. kwaliwajala.0.3805965,32.6468192. FTTH_10_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO85245350 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-10 | 2 | 2
| FREDRICK OTIENO. 256781055540. rubaga.0.3087385,32.5479178. FTTH_10_M_O |  | MTNFTTO80481038 | Pavicon | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 1 | 1
| RACHEL AINEMBABAZI. 256781083483. kiwatule.0.3652976,32.6249195. FTTH_20_M_O | Kiwatule | MTNFTTO61741674 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-10 | 2 | 2
| MARY NABUSHAWO. 256780342381. kiwatule.0.3652976,32.6249195. FTTH_10_M_O | Kiwatule | MTNFTTO25878080 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 1 | 1
| FRED WANYAMA. 256776464210. nakawa.0.3384602,32.625801. FTTH_40_M_O | Bugolobi | MTNFTTO31070561 | Enetworks | 1574960 | 448727.6 | 1323750 | 2023687.6 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-10 | 2 | 1 | To be commissioned today |  |  |  |  | 12
| LINDA BRENDA MUSIIME. 256781689667. bukuto.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO52848607 | Rak | 0 | 0 | 0 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-10 | 2 | 2
| Franco Katabarwa. 256785474782. jinja road.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO02734286 | Rak | 0 | 0 | 0 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 1 | 1
| JOSEPH KIKOYO. 256785281585. sir apollo.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO26331851 | Rak | 0 | 0 | 0 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-10 | 2 | 2
| AIDAH NAKIBUUKA. 256781125186. studio house, bugolobi, Kampala.0.3127044,32.6241475. FTTH_10_M_O | Bugolobi | MTNFTTO62666442 | Enetworks |  | 1133652.6 | 878933 | 1133652.6 | Office Internet | 1 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-10 | 2 | 1 | Delayed by Building Mgt |  |  |  |  | 3
| Kenneth Olupe. 256785595032. Ntinda.0.3608835,32.6182795. FTTH_20_M_O | Ntinda | MTNFTTO41508418 | Soliton | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-05-08 | 2023-05-08 | 2023-05-10 | 2023-05-09 | 1 | 1
| DAOUD ABDELRAZAG HUSSEIN.256772924414.Nsambya.0.295032,32.588944. FTTH_40_M_O | Makindye | MTNFTTO68826418 | ROntech | 1884308 | 684312 | 2352762 | 2568619 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-25 | 2023-04-25 | 2023-04-27 | 2023-05-09 | 14 | 14 | Right of way with neighbours which was later resolved |  |  |  |  | 7
| SARAH NAKACHWA.256773565876.makerere.0.327608,32.573686.FTTH_10_M_O | Old Kampala | MTNFTTO70583365 | Rak | 0 | 0 | 0 | TBC | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-28 | 2023-05-03 | 2023-05-05 | 2023-05-09 | 11 | 6
| NATHANI MATEEYENE.256760381584.Makindye.0.272835,32.617492. FTTH_20_M_O | Buziga | MTNFTTO15254426 | Rontech | 0 | 0 | 0 | 0 | Office Internet | 0 | Done | Office Internet (On air) | 2023-04-19 | 2023-04-19 | 2023-04-21 | 2023-05-10 | 21 | 21
| null null. 256776819896. Rubaga:Lubiri Ring Road.0.306698,32.565521 . FTTH_20_M_O | Rubaga |  | ATX |  |  |  | 1892930 | Office Internet | 0 | Done | Office internet (not on air) | 2023-02-04 | 2023-02-08 | 2023-02-10 |  | -44961 | -44965 | On Hold due to PO/ROW/Requested to be commissioned in March
| null null. 256783740055. Namuwongo:Kisugu Road.0.337853,32.543086 . FTTH_20_M_O | Namuwongo |  | ATX |  |  |  | 3344412.1 | Office Internet |  | On Hold | Office Internet (not on air) | 2022-12-28 | 2023-01-06 | 2023-01-08 |  |  |  | High BOQ, Get more Clients/We have ROW challenges with client below - the neighbours have cut our cable and want him to settle their differences first
| Ridgeway Apartments Kololo / Doreen ,+256 752 455014/ +256 772 515135 , 20Mbps package |  |  | Seagate |  |  |  | 0 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-01-24 | N/A | #VALUE! |  |  |  | Mobilizing to start Civil works
| null null. 256772120963. 69 Port Bell Road. FTTH_20_M_O |  |  | Enetworks |  |  |  | 0 | Office Internet |  | On hold | Office Internet (not on air) | 2023-02-08 | 2023-02-08 | 2023-02-10 |  |  |  | EBU test
| null null. 256782721247. Rubaga:Lubiri Ring Road.0.29857,32.535721 . FTTH_40_M_O | Rubaga |  | ATX |  |  |  | 1959527 | Office Internet |  | Done | Office Internet (not on air) | 2023-02-09 | 2023-02-11 | 2023-02-13 |  |  |  | To be commissioned on Friday 18th as requested by the customer
| null null. 256773481703. Kiwatule. FTTH_40_M_O |  |  | Seagate |  |  |  | 0 | Office Internet |  | test |  | 2023-02-16 | 2023-02-16 | 2023-02-18 |  |  |  | Mobilizing to start Civil works
| null null. 256776386665. ham road. . FTTH_20_M_O |  |  | Chrif |  |  |  | 0 | Office Internet | 2 | On Hold | Office Internet (not on air) | 2023-03-01 | 2023-03-01 | 2023-03-03 |  |  |  | High BOQ
| null null. 256784140325. mbarara. . FTTH_20_M_O |  |  | Rontech |  |  |  | 0 | Office Internet | 14 | On Hold | Office Internet (not on air) | 2023-03-06 | 2023-03-06 | 2023-03-08 |  |  |  | High BOQ - sales looking for addittional customers
| null null. 256773481703. Kiwatule. . FTTH_20_M_O |  |  | Seagate |  |  |  | 0 | Office Internet |  | Test | Office Internet (not on air) | 2023-03-14 | 2023-03-14 | 2023-03-16 |  |  |  | Mobilizing to start Civil works
| null null. 256771804928. Makerere. . FTTH_20_M_O | Makerere |  | Selmer |  |  |  | 0 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-03-16 | 2023-03-16 | 2023-03-18 |  |  |  | There is no Cable in Duct/Fiber Upgrade between LDC and Makerere Studio Site 750m. The existing route/ducts has no fiber
| DENIS OKWARE. 256774221277. Ben kiwanuka Street. . FTTH_20_M_O |  |  | Chrif |  |  |  | 0 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-03-16 | 2023-03-16 | 2023-03-18 |  |  |  | Contact off
| Infectious Diseases Institute. 256772543730. Bukasa - Muyenga.0,0. FTTH_40 |  |  | Rontech |  |  |  | 0 | Office Internet ( Postpaid) | 14 | Sent back to EBU | Office Internet (not on air) | 2023-03-20 | 2023-03-20 | 2023-03-22 |  |  |  | EBU handling
| null null. 256782359267. Bunamwaya-Lubowa.0.264913,32.546466. FTTH_20_M_O |  |  | Rontech |  |  |  | 0 | Office Internet | 14 | Done | Office Internet (not on air) | 2023-03-26 | 2023-03-26 | 2023-03-28 |  |  |  | Requested to be activated when he's available
| CHRIF ENTERPRISES LIMITED. 256778544804. Buwaate.0.395694,32.624194. FTTH_20 |  |  | Enetworks |  |  |  | 0 | Office Internet ( Postpaid) |  | On Hold | Office Internet (Postpaid) not on air | 2023-03-29 | 2023-03-29 | 2023-03-31 |  |  |  | Customer to communicate when ready
| CHRIF ENTERPRISES LIMITED. 256776234729. Buwaate.0.395694,32.624194. FTTH_20 |  |  | Enetworks |  |  |  | 2248849.2 | Office Internet |  | On Hold | Office Internet (Postpaid) not on air | 2023-03-29 | 2023-03-29 | 2023-03-31 |  |  |  | Customer to communicate when ready
| CHRIF ENTERPRISES LIMITED. 256770881561. Buwaate.0.395694,32.624194. FTTH_20 |  |  | Enetworks |  |  |  | 0 | Office Internet |  | On Hold | Office Internet (Postpaid) not on air | 2023-03-29 | 2023-03-29 | 2023-03-31 |  |  |  | Customer to communicate when ready
| CHRIF ENTERPRISES LIMITED. 256763461949. Buwaate.0.395694,32.624194. FTTH_20 |  |  | Enetworks |  |  |  | 0 | Office Internet |  | On Hold | Office Internet (Postpaid) not on air | 2023-03-29 | 2023-03-29 | 2023-03-31 |  |  |  | Customer to communicate when ready
| null null. 256770441931. Bugolobi.0.309722,32.625765. FTTH_20_M_O |  |  | Enetworks |  |  |  | 1,823,974.1 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-03-29 | 2023-03-29 | 2023-03-31 |  |  |  | ROW
| null null. 256784651470. galaxy international.0.318811,32.595311. FTTH_40_M_O |  |  | Rontech |  |  |  | 0 | Office Internet | 27 | On Hold | Office Internet (not on air) | 2023-03-31 | 2023-03-30 | 2023-04-01 |  |  |  | ROW issue being resolved
| KADIJA ANGUCHIA. 256772924135. bwebajja.0.164019,32.54788. FTTH_20_M_O |  |  | Chrif |  |  |  | 0 | Office Internet | 4 | Refunded | Office Internet (not on air) | 2023-04-05 | 2023-04-05 | 2023-04-07 |  |  |  | Pending Consolidation
| SUNDUS NALWOGA. 256788468331. Bunamwaya.0.264913,32.546466. FTTH_20_M_O |  |  | Rontech | 2474864 | 761299 | 2708390.5 | 3236163 | Office Internet | 25 | Done | Office Internet (not on air) | 2023-04-05 | 2023-04-05 | 2023-04-07 |  |  |  | considated with Raymond, to activate account at end of month.
| KYOFUNA OYAGALA NAKAYIZA. 256773899048. seguku lubowa nfuufu.0.229468,32.564324. FTTH_20_M_O |  |  | Rontech | 0 | 0 | 0 | 0 | Office Internet | 5 | On Hold | Office Internet (not on air) | 2023-04-09 | 2023-04-09 | 2023-04-11 |  |  |  | Contact unavailable
| kabalega abdallah. 256775195405. lubowa.0.229468,32.564324. FTTH_20_M_O |  |  | Rontech | 0 | 0 | 0 | 0 | Office Internet | 8 | On Hold | Office Internet (not on air) | 2023-04-12 | 2023-04-12 | 2023-04-14 |  |  |  | client having internet already.
| MUKISA EMMANUEL ONYAIT. 256781525884. Entebbe.0.077698,32.450298. FTTH_20_M_O |  |  | Chrif |  |  |  | 0 | Office Internet | 12 | On Hold | Office Internet (not on air) | 2023-04-13 | 2023-04-13 | 2023-04-15 |  |  |  | Clients are 850m away from service. MTN sales team is getting more clients
| RUTH NAKAWEESA. 256770764944. Entebbe.0.051184,32.463708. FTTH_40_M_O |  |  | Chrif |  |  |  | 0 | Office Internet | 12 | On Hold | Office Internet (not on air) | 2023-04-13 | 2023-04-13 | 2023-04-15 |  |  |  | Clients are 850m away from service. MTN sales team is getting more clients
| JULIUS MUTANDA. 256782236940. Sir Apollo Kaggwa road.0.318811,32.595311. FTTH_20_M_O |  |  | Rak |  |  |  | 0 | Office Internet | 13 | On Hold | Office Internet (not on air) | 2023-04-14 | 2023-04-14 | 2023-04-16 |  |  |  | Not picking standard sms
| SAMUEL ANDREON. 256775923390. ntinda.0.350605,32.615769. FTTH_20_M_O |  |  | Enetworks | 390915.5 | 319612 | 547616.5 | 710527 | Office Internet | 5 | Done | Office Internet (not on air) | 2023-04-14 | 2023-04-14 | 2023-04-16 |  |  |  | to be commissioned at the end of the month
| LORDINE ARTHUR OKUMU. 256763764057. bukoto.0.350525,32.595242. FTTH_10_M_O |  |  | Enetworks | 1212654 | 258615.5 | 1070549.5 | 1471269.5 | Office Internet | 7 | Done | Office Internet (not on air) | 2023-04-15 | 2023-04-15 | 2023-04-17 |  |  |  | Requested to be activated begining of May
| BRENDAR NALUNGA. 256782971974. namulanda buzzi.0.154649,32.541517. FTTH_10_M_O |  |  | Chrif |  |  |  | 0 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-04-15 | 2023-04-15 | 2023-04-17 |  |  |  | Pending COnsolidation
| NUR AHMED MOHAMUD. 256772571817. Has petro station mengo.0.318811,32.595311. FTTH_10_M_O |  |  | Chrif | 2015729 | 464820.6 |  | 2480549.6 | Office Internet | 8 | Done | Office Internet (not on air) | 2023-04-17 | 2023-04-17 | 2023-04-19 |  |  |  | (sahmiye travel and cargo agency) WIP. Physical installations partly done, seeking R.O.W
| TAN TELECOMS LIMITED. 256784005256. Soroti.1.714708,33.611278. FTTH_20 |  |  | Rontech | 0 | 0 | 0 | TBC | Office Internet ( Postpaid) |  | Done | Office Internet (Postpaid) not on air | 2023-04-15 | 2023-04-15 | 2023-04-17 |  |  |  | Mathias handling
| TONNY OCAYA. 256772908565. Lira, Uganda.0.318811,32.595311. FTTH_20_M_O |  | MTNFTTO42406123 | Pavicon | 4966080 | 313050 | 5279130 | 7585849 | Office Internet | 5 | On Hold | Office Internet (not on air) | 2023-04-20 | 2023-04-20 | 2023-04-22 |  |  |  | Pending BOQ approval
| MUHAMED KIZITO. 256761466652. Nasser road.0.318811,32.595311. FTTH_10_M_O |  | MTNFTTO82014606 | Rak | 208750 | 447085 | 409600 | 655834.6 | Office Internet | 9 | On Hold | Office Internet (not on air) | 2023-04-20 | 2023-04-20 | 2023-04-22 |  |  |  | Physicall connections done, affected by FAT installation to resolve Core Issues
| SIMON PETER OJOK. 256776020431. Gulu, Churchill Court.2.782904,32.30158. FTTH_20_M_O |  | MTNFTTO36624518 | Pavicon | 2674346 | 131650 | 2805996 | 3462281 | Office Internet | 5 | On Hold | Office Internet (not on air) | 2023-04-20 | 2023-04-20 | 2023-04-22 |  |  |  | Pending Addittional Customer
| Clive Nsiima. 256775230145. kyanja.0.395861,32.593671. FTTH_10_M_O |  | MTNFTTO53823130 | Soliton |  |  |  | 0 | Office Internet |  | test | Office Internet (not on air) | 2023-04-20 | 2023-04-20 | 2023-04-22 |  |  |  | Mobilizing to start Civil works
| HILLARY KAMUKAMA. 256787068424. equatorial mall.0.318811,32.595311. FTTH_10_M_O |  | MTNFTTO26437582 | Soliton |  |  |  | 0 | Office Internet | 8 | On hold | Office Internet (not on air) | 2023-04-20 | 2023-04-20 | 2023-04-22 |  |  |  | ROW , FAT installation ongoing to resolve core issues between shoal house to Wandegeya site
| MOHAMED ABDISALAM SALAT. 256775605525. bombo road.0.318811,32.595311. FTTH_10_M_O |  | MTNFTTO27624134 | Rak |  |  |  | 0 | Office Internet | 9 | On Hold | Office Internet (not on air) | 2023-04-19 | 2023-04-19 | 2023-04-21 |  |  |  | PENDING DUE TO MTN SERVER ISSUES ON THE BUILDING
| INDE KICONCO. 256783466299. Lumumba avenue.0.318811,32.595311. FTTH_20_M_O |  | MTNFTTO43802042 | Rak | 208750 | 431290 | 404800 | 640039.6 | Office Internet | 7 | Done | Office Internet (not on air) | 2023-04-21 | 2023-04-21 | 2023-04-23 |  |  |  | Physicall connections done, affected by FAT installation to resolve Core Issues
| ANNUNZIATO IMELDA. 256760933038. Entebbe.0.071428,32.452632. FTTH_40_M_O |  | MTNFTTO25012744 | Chrif |  |  |  | 0 | Office Internet | 10 | On Hold | Office Internet (not on air) | 2023-04-23 | 2023-04-23 | 2023-04-25 |  |  |  | Client's number not going through, Alternative number unavailable as well. SMS sent
| ESTHER ALUKA. 256782506520. Naguru.0.345513,32.607962. FTTH_10_M_O |  | MTNFTTO30527602 | Rak |  |  |  | 0 | Office Internet | 5 | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 | 2023-04-26 |  |  |  | Above DOA
| VINCENT OTHIENO. 256778869277. makerere.0.332635,32.568586. FTTH_10_M_O |  | MTNFTTO00474282 | Rak |  |  |  | 0 | Office Internet | 5 | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 | 2023-04-26 |  |  |  | No Fiber Feasibility
| ISAAC KUNYA. 256775455412. MUKONO.0.354866,32.752014. FTTH_10_M_O |  | MTNFTTO70614657 | Enetworks | 1628739 | 832746.2 | 3124578 | 4090224.2 | Office Internet |  | Done | Office Internet (not on air) | 2023-04-24 | 2023-04-24 | 2023-04-26 |  |  |  | Internet is for a school. Requested to be commissioned when school resumes again
| SHARIF MUYANJA. 256772768546. confirm.0.318811,32.595311. FTTH_20_M_O |  | MTNFTTO34385452 | Rontech | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-04-25 | 2023-04-25 | 2023-04-27 |  |  |  | Assigned to Rac Not Picking Calls
| MULTIPLEX LIMITED. 256781379360. UAP Building Kimathi Avenue.0.31467,32.583625. FTTH_20 |  | MTNFTTP43255782 | Rak | 208750 | 380886 | 589636 | 786835 | Office Internet ( Postpaid) |  | WIP | Office Internet (Postpaid) not on air | 2023-04-26 |  | 1900-01-01 |  |  |  | Not picking calls |  |  |  |  | 5
| MULTIPLEX LIMITED. 256781379533. Master Electronic, Bombo Road.0.318525,32.57406. FTTH_20 |  | MTNFTTP02178604 | Rak | 1108566 | 686458 | 1401416 | 1795024 | Office Internet ( Postpaid) |  | Refunded | Office Internet (Postpaid) not on air | 2023-04-26 |  | 1900-01-01 |  |  |  | Not picking calls
| MULTIPLEX LIMITED. 256781378706. Postal Office Kampala Road.0.313462,32.581285. FTTH_20 |  | MTNFTTP30757456 | Rak |  |  |  | 0 | Office Internet ( Postpaid) |  | On Hold | Office Internet (Postpaid) not on air | 2023-04-26 |  | 1900-01-01 |  |  |  | Not picking calls
| MULTIPLEX LIMITED. 256776793921. Nyumbakubwa Arua Park.0.316596,32.575078. FTTH_20 |  | MTNFTTP56011155 | Rak | 3099272 | 686458 | 3392122 | 3785330 | Office Internet ( Postpaid) |  | Refunded | Office Internet (Postpaid) not on air | 2023-04-26 |  | 1900-01-01 |  |  |  | Above DOA- Require Manhole casting
| MULTILEX LIMITED. 256781379151. Sal Building Nkrumah Road.0.312005,32.586923. FTTH_20 |  | MTNFTTP07262422 | Rak |  |  |  | 0 | Office Internet ( Postpaid) |  | On hold | Office Internet (Postpaid) not on air | 2023-04-26 |  | 1900-01-01 |  |  |  | denied installation by building management
| MANISH GURMUKHDAS FULWANI. 256787557660. arena mall.0.318811,32.595311. FTTH_10_M_O |  | MTNFTTO22815168 | Pavicon | 1149276 | 397925 | 652726 | 1547201 | Office Internet | 5 | WIP | Office Internet (not on air) | 2023-04-26 | 2023-04-26 | 2023-04-28 |  |  |  | WAITING BUILDING ACCESS PERMISSION
| ARNAUD BANDONKEYE. 256775833226. Makindye.0.272835,32.617492. FTTH_10_M_O |  | MTNFTTO50625000 | Pavicon | 3674174 | 398591 | 3022848 | 4072765 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-04-26 | 2023-04-26 | 2023-04-28 |  |  |  | High BOQ
| BOSTON TWIJUKYE. 256780658959. Bweyogerere.0.348194,32.661714. FTTH_10_M_O |  | MTNFTTO33455808 | Enetworks | 1524079 | 436870.5 | 1524079 | 1960949.5 | Office Internet | 3 | Done | Office Internet (not on air) | 2023-04-26 | 2023-04-26 | 2023-04-28 |  |  |  | To communicate when ready for commissioning
| ROBERT MUTUNZI. 256774573004. fort Portal.0.318811,32.595311. FTTH_10_M_O | Fortpotal | MTNFTTO47741420 | Rontech |  |  |  | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-04-26 | 2023-04-26 | 2023-04-28 |  |  |  | Client will communicate
| AIDAH NAMUTEBI. 256779088118. luteete.0.318811,32.595311. FTTH_10_M_O | Gayaza | MTNFTTO13687657 | Soliton |  |  |  | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-04-27 | 2023-04-27 | 2023-04-29 |  |  |  | Client using another account. |  |  |  |  | 0
| CHRISTINE KIGOZI. 256772473373. lungujja kitunzi.0.309657,32.540489. FTTH_10_M_O |  | MTNFTTO88583072 | Pavicon |  |  |  | 0 | Office Internet | 30 | Done | Office Internet (not on air) | 2023-04-27 | 2023-04-27 | 2023-04-29 |  |  |  | Requested to be activated after 30 days
| ADRIKO GODFREY. 256772784381. Total gayaza.0.318811,32.595311. FTTH_10_M_O | Gayaza | MTNFTTO72636662 | Soliton |  |  |  | 0 | Office Internet |  | Refund | Office Internet (not on air) | 2023-04-27 | 2023-04-27 | 2023-04-29 |  |  |  | Out of DOA(2km)
| DAUDI LUSWATA. 256781492817. namugongo janda.0.385062,32.647526. FTTH_10_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO13376188 | Soliton |  |  |  | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-04-25 | 2023-04-25 | 2023-04-27 |  |  |  | Client using another account.
| TULAIFU MUGOYA. 256762203202. mutudye kilinyabigwo.0.318811,32.595311. FTTH_40_M_O |  | MTNFTTO36544218 | Rontech | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-04-29 | 2023-04-29 | 2023-05-01 |  |  |  | Mobilizing to start Civil works
| HERBERT MBONYE. 256772507806. entebbe.0.051184,32.463708. FTTH_10_M_O |  | MTNFTTO10464040 | Chrif |  |  |  | 0 | Office Internet | 1 | On Hold | Office Internet (not on air) | 2023-05-01 | 2023-05-01 | 2023-05-03 |  |  |  | Consolidation of 7 clients, waiting for the last 3 to pay, sales team in touch
| LUKE TWIINE. 256772888114. Entebbe.0.051184,32.463708. FTTH_10_M_O |  | MTNFTTO57283817 | Chrif |  |  |  | 0 | Office Internet | 1 | On Hold | Office Internet (not on air) | 2023-05-01 | 2023-05-01 | 2023-05-03 |  |  |  | Consolidation of 7 clients, waiting for the last 3 to pay, sales team in touch
| ISAAC TUGUMISIRIZE. 256789567313. entebbe.0.051184,32.463708. FTTH_10_M_O | Kajjansi | MTNFTTO44117188 | Chrif |  |  |  | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-01 | 2023-05-01 | 2023-05-03 |  |  |  | Consolidation, waiting for third client to pay.
| BARBRA NABUTELE. 256774983359. bweyogerere kazinga.0.348194,32.661714. FTTH_40_M_O | Bweyogerere | MTNFTTO33736638 | Enetworks | 0 | 0 | 0 | TBC | Office Internet |  | On Hold | Office Internet (not on air) | 2023-05-02 | 2023-05-02 | 2023-05-04 |  |  |  | Solving ROW
| NURU SHABAN. 256761027515. roofing seguku.0.318811,32.595311. FTTH_20_M_O |  | MTNFTTO67182186 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-02 | 2023-05-02 | 2023-05-04 |  |  |  | High BOQ |  |  |  |  | 18
| MANISH JAISUKHBHAI PALAN. 256775465041. Gulu.2.770693,32.289795. FTTH_20_M_O |  | MTNFTTO38778565 | Pavicon | 2,693,396 | 355,535 | 2,392,646 | 3,048,931 | Office Internet | 3 | Done | Office Internet (not on air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-10 |  |  | High BOQ
| REBECCA ACIO. 256780344761. Gulu.2.77305,32.298667. FTTH_10_M_O |  | MTNFTTO32036830 | Pavicon | 1,251,896 | 397,925 | 1,403,946 | 1,649,821 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-02 | 2023-05-02 | 2023-05-04 | 2023-05-10 |  |  | High BOQ
| CHRISTINE NAMULI. 256774729868. sir apollo.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO02483606 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | Refunded | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | No Fiber Feasibility
| SARAH HILDA NANKYA. 256782318656. Bombo road.0.318811,32.595311. FTTH_40_M_O |  | MTNFTTO16344714 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | Refunded | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | No Fiber Feasibility
| JONATHAN STEVEN NAITA ISABIRYE. 256783773879. kumbuze.0.3726941,32.6022358. FTTH_10_M_O | Gayaza | MTNFTTO78782063 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | Refund | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Out of DOA(5 poles)
| HASSAN MUKIIBI. 256782440566. Bukuto.0.318811,32.595311. FTTH_10_M_O |  | MTNFTTO03802666 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Mobilizing to start Civil works
| ZEDEKIA BRIGHT. 256771870563. bwebajja.0.318811,32.595311. FTTH_20_M_O | Bwebajja | MTNFTTO04814364 | Chrif | 0 | 0 | 0 | 0 | Office Internet | 6 | WIP | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Client unreachable, not picking phone calls.
| MARTIN MELDGAARD MAUGUSTINI. 256776888424. Muyenga.0.296898,32.615028. FTTH_20_M_O | Muyenga | MTNFTTO27147023 | Rontech | 990779 | 560757 | 1286165 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Contractor delay |  |  |  |  | 19
| MARIOS TURYASINGURA. 256762900384. Entebbe.0.051184,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO18321032 | Chrif | 0 | 0 | 0 | 0 | Office Internet | 3 | On Hold | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Above DOA, pending consolidation.
| BRENDAR NALUNGA. 256781915528. Entebbe road.0.051184,32.463708. FTTH_10_M_O |  | MTNFTTO85876070 | Chrif | 0 | 0 | 0 | 0 | Office Internet | 1 | On Hold | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Consolidation of 7 clients, waiting for the last 3 to pay, sales team in touch
| Simon Lutaaya. 256776694106. seguku.0.2375156,32.5411731. FTTH_10_M_O |  | MTNFTTO22823080 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Consolidated with 2 others.
| JAMAIMAH NABADDA. 256779421464. kitintale.0.3107039,32.6348102. FTTH_10_M_O | Luzira | MTNFTTO51175724 | Enetworks | 1111709 | 448727.6 | 1076699 | 1560436.6 | Office Internet | 6 | On Hold | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Solving ROW |  |  |  |  | 7
| Lukusa Michael. 256763955786. masaka Rd.-0.3123123,31.7729041. FTTH_20_M_O |  | MTNFTTO88047847 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Client handled by Pavicon
| OLIMI EMMANUEL KASIGAZI. 256771611911. Entebbe road, zana.0.051184,32.463708. FTTH_10_M_O |  | MTNFTTO36503877 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-05 |  |  |  | Contractor Delay
| JOEL MWIINE. 256782270878. Entebbe road.0.0511839,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO71654818 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 |  |  |  | Mobilizing to start Civil works
| AISHA MALE. 256770506713. Entebbe.0.0511839,32.463708. FTTH_10_M_O | Entebbe | MTNFTTO76077266 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 |  |  |  | Mobilizing to start Civil works
| RONALD MAYOMBWE. 256778121713. Entebbe Road.0.0511839,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO78226782 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 | 2023-05-10 |  |  | Client unreachable, not picking phone calls.
| JOANITA NAKIMULI. 256771850272. sir apollo.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO02878634 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 |  |  |  | Mobilizing to start Civil works |  |  |  |  | 1
| Kato Winston. 256787814746. Ntinda, strecher road.0.3418294,32.6190734. FTTH_40_M_O | Ntinda | MTNFTTO48357304 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 |  |  |  | System delay, contractor did not receive the mail.
| KELLY ATUNGOZA. 256776865857. bunamwaya.0.2649128,32.5464662. FTTH_20_M_O | Najjanankumbi | MTNFTTO62173155 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 |  |  |  | Contractor delay
| DANIEL ARAPMOI.256784419167.gulu university.2.786901,32.314531. FTTH_40_M_O |  | MTNFTTO57061570 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-03-22 | 2023-04-26 | 2023-04-28 | 2023-05-10 |  |  | Mobilizing to start Civil works
| NNAAKIRYA ANTHONY MATEEGA. 256772441777. bunamwaya.0.2649128,32.5464662. FTTH_10_M_O |  | MTNFTTO75084572 | Pavicon | 1760842 | 558809 | 2068211 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Mobilizing to start Civil works |  |  |  |  | 5
| ARTHUR LUGEMWA. 256772063174. bunamwaya.0.2649128,32.5464662. FTTH_20_M_O |  | MTNFTTO80838404 | Pavicon | 5130991 | 615439 | 5474650 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Re assigned to RonTech |  |  |  |  | 22
| . 256763720746. bukoto.0.350525,32.5952415. FTTH_10_M_O |  | MTNFTTO28052252 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | Refunded | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Nansana- Ganda not feasible
| ANTHONY KYATEREKERA. 256786980012. kisaasi.0.3614407,32.5966549. FTTH_10_M_O | Kisaasi | MTNFTTO05530328 | Soliton |  |  |  |  | Office Internet |  | Refund | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Site out of DOA range(900m about 12poles)
| Nakimuli Rosette. 256781326099. Entebbe road.0.0511839,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO86705252 | Pavicon |  |  |  |  | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Mobilizing to start Civil works
| . 256763746462. namanve.0.3552961,32.6924934. FTTH_10_M_O | Mukono | MTNFTTO52267026 | Enetworks | 2563429 | 475125.5 | 1966679 | 3038554.5 | Office Internet | 1 | On Hold | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | To be commissioned today |  |  |  |  | 7
| ARONE AMARA. 256770400330. sseta.0.3188106,32.5953111. FTTH_10_M_O | Seeta | MTNFTTO67854115 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Delayed by Client
| Sarah Wadembere. 256782929540. stensera road.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO06542842 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-05 | 2023-05-07 |  |  |  | Mobilizing to start Civil works
| AYOUB ADAM. 256761343141. Najjanankumbi.0.2848602,32.5706434. FTTH_10_M_O | Najjanankumbi | MTNFTTO65286728 | Rontech | 2444588 | 565109 | 2743920 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-06 | 2023-05-08 |  |  |  | Not picking calls |  |  |  |  | 15
| . 256787932573. Makindye.0.2728351,32.6174919. FTTH_10_M_O |  | MTNFTTO17521635 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-06 | 2023-05-08 |  |  |  | Mobilizing to start Civil works
| TONNY TUMWESIGYE. 256775644641. kireka.0.3374838,32.6468956. FTTH_20_M_O |  | MTNFTTO55225247 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-06 | 2023-05-08 |  |  |  | Mobilizing to start Civil works
| TONNY TUMWESIGYE. 256761906408. Bweyogerere main.0.348194,32.6617141. FTTH_20_M_O |  | MTNFTTO00102576 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-06 | 2023-05-08 |  |  |  | Mobilizing to start Civil works
| ESTHER MAKAI BAGUMA. 256776937837. kireka.0.3374838,32.6468956. FTTH_10_M_O | Bweyogerere | MTNFTTO03536526 | Enetworks | 2266229 | 475125.6 | 2101879 | 2741354.6 | Office Internet | 3 | Done | Pending | 2023-05-06 | 2023-05-06 | 2023-05-08 |  |  |  | GPON blinking |  |  |  |  | 6
| Winnie Insuti. 256783471029. Entebbe.0.0511839,32.463708. FTTH_10_M_O | Entebbe | MTNFTTO80852504 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-04 | 2023-05-04 | 2023-05-06 |  |  |  | Client not aware of services.
| DARIUS KAIJUKA. 256763707800. CBD katwe.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO21026130 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-06 | 2023-05-06 | 2023-05-08 | 2023-05-10 |  |  | Mobilizing to start Civil works
| BOSCO SSEMAKULA. 256763459289. bwebajja.0.3188106,32.5953111. FTTH_10_M_O | Bwebajja | MTNFTTO26456521 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-06 | 2023-05-08 |  |  |  | Works ongoing
| JERRY BENARD ETOLU. 256779046795. oilibya wakaliga.0.3004172,32.5353879. FTTH_20_M_O |  | MTNFTTO23348847 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| JAMES AISU. 256770485497. oillibya kagoma petrol station.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO61202587 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | No GPON Coverage
| JANE BAITWA. 256785800611. Kyaliwajjala Namugongo road.0.3805965,32.6468192. FTTH_10_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO16131850 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-08 | 2023-05-10 |  |  |  | WIP
| WINNIE NAKATO. 256782509121. national theatre.0.3188106,32.5953111. FTTH_10_M_O | Kampala Upper CBD | MTNFTTO15138085 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-08 | 2023-05-10
| SYLIVIA NANYONJO. 256760386897. Muyenga bukasa.0.2968976,32.6150277. FTTH_20_M_O | Ggaba | MTNFTTO76085126 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | Refund | Office Internet (not on air) | 2023-05-05 | 2023-05-08 | 2023-05-10 |  |  |  | High BOQ
| JIM AGABA. 256778218288. muganzirwaza complex.0.3188106,32.5953111. FTTH_10_M_O | Ndeeba | MTNFTTO25780255 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-08 | 2023-05-10
| SILAS KATO. 256787546143. Kirinya Kito.0.3188106,32.5953111. FTTH_10_M_O | Bweyogerere | MTNFTTO26535112 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | On Hold | Office Internet (not on air) | 2023-05-06 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing more 3 clients
| JOSEPH MUGENYI. 256782639061. lubowa.0.2294685,32.5643239. FTTH_10_M_O | Najjanankumbi | MTNFTTO25757255 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| FAITH KABAKCI. 256761392166. luweza road.0.2239317,32.5519538. FTTH_10_M_O | Najjanankumbi (Lubowa - Lweza) | MTNFTTO32846312 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| IMAN TUBUNE. 256787617360. Banda kyambogo.0.3441441,32.6366848. FTTH_10_M_O |  | MTNFTTO23041523 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | Refunded | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Not feasible
| VINCENT MUKASA NTEGE. 256775885792. bukoto.0.350525,32.5952415. FTTH_20_M_O |  | MTNFTTO16165864 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| REBECCA KISAAKYE. 256780721857. Bombo Road.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO52564518 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| MARK TUSHEMERIRWE. 256780362712. kawala.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO46280223 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| SIRAJI GOGOSI. 256789305969. kibuli.0.3108412,32.5952415. FTTH_10_M_O |  | MTNFTTO83354664 | ROntech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| . 256764115764. entebbe uganda.0.0511839,32.463708. FTTH_40_M_O | Entebbe | MTNFTTO66688526 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Works ongoing.
| KOBUSINGYE PATIENCE. 256774417194. mutundwe.0.2807483,32.5404161. FTTH_10_M_O |  | MTNFTTO70447683 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| STELLA NAJJEKE. 256773723357. sir Apollo kaggwa road.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO04551664 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| VICENT KALUNGA. 256782408090. Jinja kutch.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO78741770 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | Refunded | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | No space for poles
| Kateregga Godfrey. 256782754253. Kabuuma.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO06814533 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| Namara Sheila. 256784747608. middle east supermarket bukoto.0.3595424,32.6069927. FTTH_10_M_O |  | MTNFTTO54858712 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| JOSEPH NITUMWESIGA. 256781497731. mbarara, Uganda..-0.6071596,30.6545022. FTTH_40_M_O |  | MTNFTTO82434567 | Rontech | 3482749 | 540375 | 3810533 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works |  |  |  | 10
| ROSEMARY NASSALI. 256785773625. Uganda Martyr's S.S, Namugongo.0.3188106,32.5953111. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO11710753 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| ABRAHAM LUZIRA. 256772120987. java house jinja.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO56804405 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | Refunded | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Very far from the MTN fiber line, 0.429584 33.199139 |  |  | 256783070779
| FRANK KARAMUKYO. 256774573060. ntinda kigowa.0.356946,32.6126447. FTTH_10_M_O | Ntinda | MTNFTTO82524532 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| BRIGHTON ARIKIRIZA. 256787044228. nasozi complex salama road.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO30131132 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| ABDUL KABUYE. 256784980857. Entebbe.0.0511839,32.463708. FTTH_10_M_O | Entebbe | MTNFTTO35864080 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Pending consolidation, 5/7 clients paid.
| TIMOTHY BUKENYA. 256775009000. najjanankumbi.0.2855916,32.5673493. FTTH_20_M_O |  | MTNFTTO43774402 | Rontech | 1353213 | 556881 | 1657013 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works |  |  |  |  | 15
| FRANK MUNGULENI. 256762978603. oil energy kira.0.3188106,32.5953111. FTTH_20_M_O | Kira (Buwate - Busibante Najjera) | MTNFTTO34643178 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| SALIM KATSIGAZI. 256776000110. ntinda kigowa.0.356946,32.6126447. FTTH_40_M_O | Ntinda | MTNFTTO45161388 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| PATRICK MWERINDE. 256777823065. sonde.0.3188106,32.5953111. FTTH_10_M_O | Sonde | MTNFTTO42870216 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| JOHN OUMA. 256781489925. Ntinda.0.350605,32.6157688. FTTH_20_M_O | Ntinda | MTNFTTO31165312 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| Amanda Lisa. 256772717216. Rubaga division.0.3087385,32.5479178. FTTH_10_M_O |  | MTNFTTO70566271 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| SARAH BASUBIZE. 256776333774. hote africana.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO04586538 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| HANNINGTON NKAYIVU. 256782528365. kirudo hospital.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO10881444 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| JOYCE MUKAMUNYANA. 256787793808. kololo.0.327297,32.5949199. FTTH_40_M_O |  | MTNFTTO60561766 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| BALABA DOUGLAS. 256778674436. sir apollo.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO25285378 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| SUSAN NAKAZZI. 256770558508. natete.0.2972025,32.5266698. FTTH_20_M_O |  | MTNFTTO81503542 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| AKISAM SSERUNKUUMA. 256779810697. Lira, Uganda.0.3188106,32.5953111. FTTH_10_M_O |  | MTNFTTO21650352 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| SETH KASHUMBUSHA. 256783046070. monalisa pub rubaga.0.3087385,32.5479178. FTTH_10_M_O |  | MTNFTTO27055250 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 | 2023-05-10 |  |  | Mobilizing to start Civil works
| ABDALLAH MUSOKE. 256786040439. kololo Baskerville.0.327297,32.5949199. FTTH_20_M_O |  | MTNFTTO52080218 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| FRED WOKORACH. 256770727007. Gulu.2.7722789,32.2984743. FTTH_10_M_O |  | MTNFTTO26682527 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| REBECCA NALUWAGGA. 256782656544. Bugolobi Lithuli Avenue plot 99.0.309722,32.6257655. FTTH_20_M_O |  | MTNFTTO53338677 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| BRIAN MAMBO. 256773025144. rubaga.0.3087385,32.5479178. FTTH_20_M_O |  | MTNFTTO05147877 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| MOSES NKUBA. 256785556437. mpelerwe.0.3818907,32.5761582. FTTH_10_M_O | Gayaza | MTNFTTO10853764 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| TONNY TUMWESIGYE. 256780495649. imperewe.0.3188106,32.5953111. FTTH_20_M_O | Gayaza | MTNFTTO21448715 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| DANIEL LOPEYOK. 256770569510. Gulu.2.7829094,32.3015749. FTTH_20_M_O |  | MTNFTTO68740316 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| AISHA KWAGA. 256785435201. Entebbe Road.0.0511839,32.463708. FTTH_20_M_O | Entebbe | MTNFTTO03721485 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| VIOLA NAMPIIMA. 256773369777. Sir Apollo.0.3188106,32.5953111. FTTH_20_M_O |  | MTNFTTO07370227 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| schroeder. 256771137386. public service.0.3311665,32.5768018. FTTH_10_M_O |  | MTNFTTO85186563 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-05 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| . 256775833443. Kevin a road.0.3188106,32.5953111. FTTH_10_M_O | Nsambya | MTNFTTO83160048 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-06 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| DENIS ONGOM. 256784270458. mutungo - kidduka stage.0.3204901,32.645402. FTTH_10_M_O | luzira | MTNFTTO58104473 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| KHASSIM NSUBUGA. 256784089283. Natete.0.2972025,32.5266698. FTTH_20_M_O | Ndeeba | MTNFTTO58506538 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| PATRICK SSEBUTINDE. 256772460348. Ntinda.0.350605,32.6157688. FTTH_10_M_O | Bukoto | MTNFTTO71160513 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| SAMUEL DDAMULIRA. 256762303088. bwebaja.0.3188106,32.5953111. FTTH_20_M_O | Bwebajja | MTNFTTO53274326 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| PETER MASAABA. 256786208335. Munyonyo.0.2406666,32.6197968. FTTH_20_M_O | Bunga | MTNFTTO32274711 | ROntech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| Faith Mirembe. 256784721989. kireka.0.3374838,32.6468956. FTTH_10_M_O | Bweyogerere | MTNFTTO28412786 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 | 2023-05-11 |  |  | Mobilizing to start Civil works
| ANTHONY ATAMBA. 256761619004. Natete.0.2972025,32.5266698. FTTH_20_M_O | Ndeeba | MTNFTTO14338388 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| Rebecca Yom. 256760914622. Lweza National Water , Entebbe.0.0511839,32.463708. FTTH_40_M_O | Lweza | MTNFTTO37207124 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| sead. 256771753160. ntinda.0.350605,32.6157688. FTTH_10_M_O | Bukoto | MTNFTTO51023474 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| NAMBAYO PATRICIA NYENDE. 256783401330. najjanakumbi.0.2848602,32.5706434. FTTH_20_M_O | Najja | MTNFTTO30114031 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| MUBARAK MUKWAYA. 256783012719. Entebbe.0.0511839,32.463708. FTTH_40_M_O |  | MTNFTTO45357882 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-08 | 2023-05-10 |  |  |  | Mobilizing to start Civil works
| JESCA NOREEN ASEMO. 256779409850. kireka.0.341382,32.6424308. FTTH_10_M_O | Bweyogerere | MTNFTTO37602771 | Enetworks | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-08 | 2023-05-10 | 2023-05-12 |  |  |  | Mobilizing to start Civil works
| KAWERE RUKIA. 256770602364. muyenga.0.2968976,32.6150277. FTTH_20_M_O | Ggaba | MTNFTTO05704314 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-10 | 2023-05-10 | 2023-05-12 |  |  |  | Mobilizing to start Civil works
| . 256764155346. Rubaga Road Butikiro Complex.0.3087385,32.5479178. FTTH_10_M_O | Rubaga | MTNFTTO80415088 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-10 | 2023-05-10 | 2023-05-12 |  |  |  | Mobilizing to start Civil works
| FRANCIS BAMPIGA. 256774717999. Lira Uganda.0.3188106,32.5953111. FTTH_20_M_O | Lira | MTNFTTO01215023 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-10 | 2023-05-10 | 2023-05-12 |  |  |  | Mobilizing to start Civil works
| Oryema John Paul. 256781570800. Help Africa, Rubaga.0.3087385,32.5479178. FTTH_10_M_O | Rubaga | MTNFTTO87527167 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | Done | Office Internet (not on air) | 2023-05-10 | 2023-05-10 | 2023-05-12 | 2023-05-10 |  |  | Mobilizing to start Civil works
| ALBERT NATAMBA.256781367285.Mbarara:Kabale - Mbarara Road.0.601416,30.66424.FTTH_10_M_O | Mbarara | MTNFTTO00610111 | Rontech | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2022-11-30 | 2023-04-24 | 2023-04-26 |  |  |  | Mobilizing to start Civil works
| PERUTH KORUGENDO. 256772491470. bwebajja.0.3188106,32.5953111. FTTH_10_M_O | Bwebajja | MTNFTTO76068354 | Chrif | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-09 | 2023-05-09 | 2023-05-11 |  |  |  | Mobilizing to start Civil works
| . 256764134627. kyanja.0.3958614,32.5936711. FTTH_10_M_O | Kisaasi | MTNFTTO06271051 | Soliton | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-05-10 | 2023-05-10 | 2023-05-12 | 2023-05-14 |  |  | Mobilizing to start Civil works
| EMMANUEL ABAASA.256770915807.Bombo Road Kawempe.0.345704,32.568155.FTTH_10_M_O | Makerere | MTNFTTO68237550 | Rak | 0 | 0 | 0 | TBC | Office Internet |  | Done | Office Internet (not on air) | 2023-03-31 | 2023-05-03 | 2023-05-05 | 2023-05-10
| ENID SSEMUSU KATO NABWAMI.256789818842.mankidye jjuko zone.0.272835,32.617492. FTTH_10_M_O | Makindye | MTNFTTO48783182 | Pavicon | 0 | 0 | 0 | 0 | Office Internet |  | WIP | Office Internet (not on air) | 2023-03-31 | 2023-04-17 | 2023-04-19 |  |  |  | Not feasible
Formulas:
Planned End Date = [Customer commitment/Payment date]+2
Date commissioned = [Planned End Date]+2
Customer commitment/Payment date = [Date logged]+2

## Refunded
Completion Month | Customer Name | Total cost | FTTx type | Permit Process Application | Permit Granted | Contractor | Installation delay due to customer (days) | Installation Status | On-air status | Date logged | Customer commitment/Payment date | Date commissioned | Total MTTI (days) | MTTI after payment/Customer commitment | Remarks | Snag tracker | PAC status | FAC status
| null null. 256777263719. Kampala Downtown:Kyaggwe Road.0.312122,32.57137 . FTTH_20_M_O | TBC | Office Internet |  |  | Chrif | 0 | Refunded | Office Internet (not on air) | 2022-12-12 | 2023-01-13 |  |  | -44939 | ROW- Refund Please
| null null. 256782854160. Soroti:Haridas Road.1.717988,33.621647 . FTTH_40_M_O | N/A | Office Internet |  |  | ATX | 7 | Refunded | Office Internet (not on air) | 2022-12-14 | 2022-12-30 |  |  |  | Route being reviewed, pending updated BOQ
| ANTHONY KIPKURUI CHERUIYOT. 256761000259. Najjanankumbi:Lubowa Terrace Road.0.222319,32.56261 . FTTH_40_M_O | N/A | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2022-08-17 | 2022-12-22 |  |  |  | This client requires 6poles and 470m cable which makes him not feasible due to high boq More sales should be done around the location
| PETER KIGUAMBA NDIRANGU. 256788015262. Bweyogerere:Bweyogerere.0.365785,32.6556 . FTTH_20_M_O | 5927140 | Office Internet |  |  | Seagate |  | Refunded | Office Internet (not on air) | 2022-09-29 | N/A |  |  |  | =COUNTIF('Detailed summary'!J:J,Summary!P5)+countif(
| null null. 256777666921. Rubaga:Rubaga Road.0.305717,32.559233 . FTTH_20_M_O | TBC | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2023-02-08 | 2023-02-13 |  |  |  | Null null. 256777666921. Rubaga. is in slum area, there is no space to plant a pole. Richard advised you consider Pro Max for him
| null null. 256779354325. Kololo:Acacia Avenue.0.334277,32.586333 . FTTH_40_M_O | TBC | Office Internet |  |  | Selmer |  | Refunded | Office Internet (not on air) | 2023-02-09 | 2023-02-14 |  |  |  | 700m and ROW
| null null. 256785016644. Muyenga:Bukasa Road.0.302009,32.611725 . FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-02-02
| null null. 256783357571. Ntinda Bukoto:Kira Road.0.341986,0.341986 . FTTH_40_M_O | UGX 5,666,928.6 | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-01-31 | 2023-02-16 |  |  |  | High BOQ , There are 6 poles
| null null. 256771939043. Rubaga:Mengo.0.353992,32.607849 . FTTH_40_M_O | 4495128.6 | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-01-31 | 2023-02-06 |  |  |  | The client named below failed to get in terms with his landlord to allow MTN fiber into his premises. The client decided to shift therefore he suggested a refund at the moment. null null. 256771939043. Rubaga:Mengo.0.353992,32.607849 . FTTH_40_M_O (Mirembe f.m
| null null. 256772656611. kyanja. FTTH_20_M_O | 6879555 | Office Internet |  |  | Seagate |  | Refunded | Office Internet (not on air) | 2023-02-20 | 2023-02-20 |  |  |  | High BOQ 687,9555
|  | 5698104 | Office Internet |  |  | Enetworks | 5 | Refunded | Office Internet (not on air) | 2023-02-20 | 2023-02-21 |  |  |  | High BOQ
| null null. 256763222465. kirudu hospital. . FTTH_20_M_O | 7302765 | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-02-20 | 2023-02-21 |  |  |  | High BOQ
| null null. 256775852859. Buwaate. . FTTH_20_M_O | 5698104 | Office Internet |  |  | Seagate |  | Refunded | Office Internet (not on air) | 2023-02-21 | 2023-02-21 |  |  |  | High BOQ
| null null. 256760209168. namanve. . FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-02-22 | 2023-02-22 |  |  |  | Far from service
| null null. 256772098079. kireka. . FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-02-22 | 2023-02-22 |  |  |  | 256772098079 - User is far from the services. Requires an extra two people for consolidation
| null null. 256775776953. Lira:Ireda Road.2.253024,32.901082 . FTTH_20_M_O | 4682239.6 | Office Internet |  |  | ATX | 10 | Refunded | Office Internet (not on air) | 2022-11-29 | 2023-12-05 |  |  |  | Customer on air as 256789008372
| null null. 256777531056. lira uganda. . FTTH_20_M_O | TBC | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2023-02-20 | 2023-02-24 |  |  |  | Longest route is not feasible, shortest route, no where to plant poles
| null null. 256775674220. Kampala Downtown:Nakivubo Road.0.310007,32.57684 . FTTH_20_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-02-08 | 2023-02-19 |  |  |  | Location not feasible
| null null. 256762416047. MBARARA. -0.60716,30.654502.FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-02-16 | 2023-02-21 |  |  |  | High BOQ
| null null. 256771651710. makamba road. . FTTH_20_M_O | TBC | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2023-03-03 | 2023-03-03 |  |  |  | Not feasible by 2Kmtsr
| null null. 256393877774. ntinda. . FTTH_20_M_O | 5672280.6 | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-03-06 | 2023-03-06 |  |  |  | High BOQ
| null null. 256782206600. lasto oketch road. . FTTH_40_M_O | TBC | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2023-03-07 | 2023-03-07 |  |  |  | NULL NULL-256782206600- needs a refund 7poles and 650m
| null null. 256787283855. Salaama Road after bunzali stage. 0.318811,32.595311.FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-02-26 | 2023-02-07 |  |  |  | Says was misled by Sales agent who told him there is no Installation fee for the Office Internet so then was onboarded without agreeing on that part.
| SALIM KATSIGAZI. 256776000110. inyamat village. . FTTH_40_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-03-10 | 2023-03-10 |  |  |  | Far from service
| SHARON NAMUSISI. 256779706862. shell busega. . FTTH_20_M_O | TBC | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2023-03-10 | 2023-03-10 |  |  |  | she’ll busega no fiber (not our cluster too)
| null null. 256783199039. nsawo namugongo. . FTTH_20_M_O | TBC | Office Internet |  |  | Seagate |  | Refunded | Office Internet (not on air) | 2023-03-10 | 2023-03-10 |  |  |  | No fibre in Nsawo
| Birungi Lukiya. 256787196622. Kyambogo University. . FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-03-10 | 2023-03-10 |  |  |  | 1 Km from fibre
| null null. 256784970836. kabalagala. . FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-03-10 | 2023-03-10 |  |  |  | High BOQ
| null null. 256788712896. Mulawa,Kira. . FTTH_40_M_O | TBC | Office Internet |  |  | Seagate |  | Refunded | Office Internet (not on air) | 2023-03-14 | 2023-03-14 |  |  |  | Not feasible
| null null. 256760995597. Bombo. 0.318811,32.595311 FTTH_10_M | TBC | Office Internet |  |  |  |  | Refunded | Office Internet (not on air) | 2023-02-27 | 2023-03-23 |  |  |  | Located at Bombo- Out of GPON Coverage
| Chipampa Chibesakunda.256781484163.0.3189,32.5981.FTTH_40_M | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-03-07 | 2023-03-13
| EVE AMANYA. 256777605383. Nakasero Hill:Kyaggwe Road. 0.316534,32.574786.FTTH_20_M | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2022-06-14 | 2023-03-03 |  |  |  | Far from Service
| null null. 256783100374. kiganda kalamba. . FTTH_20_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-03-20 | 2023-03-20
| DENIS OKWARE. 256774221277. Ben kiwanuka Street. . FTTH_20_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-03-16 | 2023-03-16 |  |  |  | connection is associated with r.o.w where a kcca permit will be needed. Poles can't be used near cooper complex (Namaganda Plaza
| null null. 256763491042. konge. . FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-03-21 | 2023-03-21 |  |  |  | Over 1 Km away from Service
| null null. 256775570306. Kampala Downtown:Wilson Road.0.298509,32.600674 . FTTH_20_M_O | 2751284.9 | Office Internet |  |  | Chrif | 7 | Refunded | Office Internet (not on air) | 2023-02-09 | 2023-02-17 |  | -44966 | -44981 | The client is not in the country, currently roaming in south sudan. We have managed to reach him through international bundles and he says he needs a refund.
| null null. 256776639989. bugolobi.0.309722,32.625765. FTTH_20_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-03-22 | 2023-03-22 |  |  |  | Customer is far from the services
| KATO DOKA. 256780591644. Entebbe.0.051184,32.463708. FTTH_40_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-03-21 | 2023-03-21 |  |  |  | Not feasible
| null null. 256772556083. kisaasi.0.361441,32.596655. FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-03-26 | 2023-03-26 |  |  |  | fAR FROM sERVICE
| null null. 256785608434. zana easy buy supermarket. 0.318811,32.595311. FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-01 | 2023-04-11 |  |  |  | fAR FROM sERVICE
| null null. 256763855155. kabuuma.0.318811,32.595311. FTTH_20_M_O | TBC | Office Internet |  |  | Rontech | 4 | Refunded | Office Internet (not on air) | 2023-03-27 | 2023-03-27 |  |  |  | Not feasible
| OWECI SALHA. 256774297485. kyanja.0.395861,32.593671. FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-03-29 | 2023-03-29 |  |  |  | Not feasible
| null null. 256772670401. nakivubo lane.0.311688,32.573687. FTTH_20_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-03-03 | 2023-03-03 |  |  |  | no fiber in Ssekaziga building 0.3116691 32.5753628
| Raymond Tugume. 256779171221. Buziga.0.269005,32.616445. FTTH_40_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-04 | 2023-04-04 |  |  |  | Please note that client is in a range of 800m from picking point. It requires 14 poles and a cable 950m
| null null. 256760613742. Ndeeba.0.295632,32.559239. FTTH_20_M_O | TBC | Office Internet |  |  | ROntech |  | Refunded | Office Internet (not on air) | 2023-04-04 | 2023-04-04 |  |  |  | 1.2km away from picking point
| BARBARA OINE. 256772829183. Lubowa-Bunamwaya.0.264913,32.546466. FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-05 | 2023-04-05 |  |  |  | 1 Km away
| FRED OBONYO. 256788937425. Mapeera.0.314439,32.57766. FTTH_20_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-05 | 2023-04-05 |  |  |  | ROW at Mapeera House
| Robert Mulinde. 256772434117. luwum Street kampala.0.312683,32.579368. FTTH_40_M_O | TBC | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-08 | 2023-04-08 |  |  |  | Kindly consider a refund for this application. The client is the landlord of Julina Building on Luwum street and he instead needs MTN to provide him with IBS / RF antennas to boost the poor network coverage within the building since his tenants are complaining about the absence of MTN signal on the building.
| JOSHUA KIRYA. 256763490963. Bugolobi.0.316091,32.624545. FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-12 | 2023-04-12 |  |  |  | ROW with Bugolobi Flats
| VERONICA NAMULONDO. 256777913081.muyenga. 0.296898,32.615028. FTTH_20_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-12 | 2023-04-12 |  |  |  | Mobilizing to start Civil works
| PAUL NUWAGABA 256772415361 Location 0.367696 , 32.638611 Nanlya FTTH_20_M_O | TBC | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-06 | 2023-04-14 |  |  |  | High BOQ 4921801.6
| null null. 256770418236. Nyeihanga Police Station. 0.318811,32.595311. FTTH_40_M_O | TBC | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-06 | 2023-04-14 |  |  |  | Not Feasible
| null null.256788008071.onono road gulu.2.784699.32.297938. FTTH_40_M_O | TBC | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-03-31 | 2023-04-19 |  |  |  | Not Feasible/High BOQ
| FRANK MUSISI. 256788383229. Our lady Consolata ss kireka.0.337484,32.646896. FTTH_40_M_O |  | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-08 | 2023-04-08 |  |  |  | On hold, Client solving ROW.
| STEPHEN LAILA. 256770493565. Zaid complex Wilson road.0.318811,32.595311. FTTH_20_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-12 | 2023-04-12 |  |  |  | Not feasible
| ASUMAN WEPUKHULU. 256770735807. sentema road mengo.0.310847,32.557224. FTTH_20_M_O |  | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-13 | 2023-04-13 | 2023-04-28 |  |  | High BOQ
| Emmanuel Mwanje. 256784168331. Nkrumah road.0.318811,32.595311. FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-11 | 2023-04-11 |  |  |  | Karobwa building mgt has totally refused us to run mtn cable in their building especially off the cable trays installed by Atc. This is because the agreement btn Karobwa and Atc dictates that any additional infrastructure from the equipment room has to be first agreed upon or possibly after paying for it.
| ANDREW BRIGHT. 256762504692. lunguja.0.309657,32.540489. FTTH_20_M_O |  | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-14 | 2023-04-14 |  |  |  | No Fiber
| BOSTON TWIJUKYE. 256780658959. Bweyogerere.0.348194,32.661714. FTTH_10_M_O |  | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-17 | 2023-04-17 |  |  |  | Not feasible
| KINENE ANGELLO. 256789652909. mapeera.0.314436,32.578327. FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-17 | 2023-04-17 |  |  |  | ( pioneer mall)- 2nd client not possible because mgt says they haven't provisioned for service providers since the building is still under construction. Client proposed a refund.
| STELLA VIVIENNE ADOKO. 256772022228. Entebbe.0.051184,32.463708. FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-17 | 2023-04-17 |  |  |  | Kindly note that the subject client is 700m away from the nearest termination point. Sales team is looking for more clients to consolidate.
| PHILLIP EGESSA. 256393244998. Bukoto.0.353255,32.596852. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-04-18 | 2023-04-18 |  |  |  | Mobilizing to start Civil works
| Elizabeth Nakawunde. 256774002112. lungujja.0.309657,32.540489. FTTH_40_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-18 | 2023-04-18 |  |  |  | Above DOA DOA- 4,039,859
| NABUYUNGO SYLVIA. 256789831549. Bwebajja:Kajjansi. 0.309217,32.563058. FTTH_10_M_O |  | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2022-11-09 | 2023-04-18 |  |  |  | No Fiber
| SAMUEL PRINCE MUKISA.256774581871.salaama road.0.318811.32.595311.FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-05 | 2023-04-14 |  |  |  | 1 KM away from picking point
| JEFFREY BAIGA. 256773560174. kisaasi.0.361441,32.596655. FTTH_20_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-17 | 2023-04-17 |  |  |  | Out of Range
| JOHN ONEN MUSA LAKOR. 256784107285. Naguru.0.345513,32.607962. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-04-20 | 2023-04-20 |  |  |  | Customer in subject requires 7poles which is above DOA
| ISAAC KUNYA. 256775455412. MUKONO.0.354866,32.752014. FTTH_40_M_O |  | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-20 | 2023-04-20 |  |  |  | Customer far from fiber
| PETER NETUWA. 256782670409. Rubaga.0.308739,32.547918. FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-20 | 2023-04-20 |  |  |  | Reason: We need a pole inside a customer premises. Or to attach it on UMEME pole which customer says it's his property.
| MARTIN LUKABYA. 256775449551. Buziga.0.318811,32.595311. FTTH_10_M_O |  | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-20 | 2023-04-20 |  |  |  | High BOQ. 7 poles, 420m/48c
| JAYESHBHAI MAGANBHAI CHAVDA. 256777445554. Lira, Uganda.0.318811,32.595311. FTTH_10_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-20 | 2023-04-20 |  |  |  | High BOQ
| DAUDI LUSWATA. 256781492817. namugongo janda.0.385062,32.647526. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-19 | 2023-04-19 |  |  |  | client has 5 poles falling out of the D.O.A range with 12 homes passed
| SHIFRAH ASHABA. 256784057223. muyenga bukasa rd.0.296898,32.615028. FTTH_10_M_O |  | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-19 | 2023-04-19 |  |  |  | High BOQ. 7 poles, 420m/48c
| PATRICK MULINDE. 256787460259. bakuli.0.312933,32.564141. FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-19 | 2023-04-19 |  |  |  | he is at Namayiba bus park and he needs 2 poles. Yesterday one team was arrested at Mukwano mall for digging to install a pole in the middle of the town.
| Jinal Shah Kamlesh. 256777148103. bombo road.0.318811,32.595311. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-04-19 | 2023-04-19 |  |  |  | No Fiber feasibility
| HARRIET ABER. 256774716802. Entebbe.0.064909,32.453946. FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-19 | 2023-04-19 |  |  |  | Kindly note that the subject client is 740m away from the nearest termination point. Sales team is getting more clients.
| NATHANI MATEEYENE. 256760381584. Makindye.0.272835,32.617492. FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-19 | 2023-04-19 |  |  |  | Not feasible - 472 Meters
| SOLOMON SSEBUNYA. 256782402958. ssonde.0.318811,32.595311. FTTH_10_M_O |  | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-23 | 2023-04-23 |  |  |  | High BOQ
| ANTONIO KAYONGO. 256770340735. bulindo.0.41936,32.643994. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 |  |  |  | Poles = 9 - Distance = 700m - 48FC = 760m - Homes passed = 4
| VICKY ATIM. 256776379335. kyanja.0.395861,32.593671. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 |  |  |  | Out of Range
| DONALD SIBO. 256763078881. kyanja.0.395861,32.593671. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 |  |  |  | Out of Range
| Vivian Tumuhairwe.256787304480.Kumbuzi.0.404679,2.588007.FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | - Poles = 7 - Distance = 560m - 48FC = 660m - Homes passed = 6
| HENRY MUGANGA.256762937721.Entebbe, UN Base.0.051184,32.463708.FTTH_40_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-12 | 2023-04-24 |  |  |  | 2nd Client on Crystal Apartments Entebbe. Installation not possible at the moment due to R.O.W issue with NWSC
| . 256786176199. mainstreet jinja.0.428828,33.209498. FTTH_10_M_O |  | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | client below is not feasible. Place needs mauling which the management is against.
| BRIAN BIRURU.256784247793.kisenyi.0.318563,32.576694. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-04-14 | 2023-04-19 |  |  |  | Not feasible
| MOSES MUTUMBA. 256770584895. zana.0.318811,32.595311. FTTH_20_M_O |  | Office Internet |  |  | Rontech |  | Refunded | Office Internet (not on air) | 2023-04-12 | 2023-04-12 |  |  |  | No Fiber feasibility
| Kenneth Nyeko. 256783775807. Gulu, Uganda.2.770693,32.289795. FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-23 | 2023-04-23 |  |  |  | ROW- NEEDS MUNICIPAL PERMIT
| GACH NYABOL. 256762479436. Bunamwaya.0.264913,32.546466. FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 |  |  |  | Not Feasible- 920 m
| PETER KASUMBA. 256776422593. entebbe.0.051184,32.463708. FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 |  |  |  | Not feasible
| FATMAH ABDALLAH. 256773201216. lubaga.0.308739,32.547918. FTTH_10_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-24 | 2023-04-24 |  |  |  | High BOQ
| FELIX GUMA. 256776783898. William street gazaland.0.31416,32.576684. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | No Fiber feasibility
| ALBERT ANGUATI. 256775800697. kajjansi.0.207025,32.540103. FTTH_10_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | Client is 500m away from service
| DAOUD ABDELRAZAG HUSSEIN. 256772924414. Nsambya.0.295032,32.588944. FTTH_40_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | High BIQ
| Vivian Tumuhairwe. 256787304480. kumbuzi.0.404679,32.588007. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | Mobilizing to start Civil works
| TONNY KUNIHIRA. 256763568306. nalukolongo.0.291146,32.555658. FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-04-25 |  |  |  | High BOQ
| IVAN MWIMA. 256777764737. wandegeya.0.333753,32.568383. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-04-26 | 2023-04-26 |  |  |  | building management denial of installation
| NANTONGO ZUBEDA. 256772383525. nateete.0.297102,32.526805. FTTH_10_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-04-27 | 2023-04-27 |  |  |  | Not approved
| ROSE NATANDA. 256783554723. Namirembe Parents Nursery School.0.316911,32.561313. FTTH_40_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | 2023-05-01 | 2023-05-01 |  |  |  | Not Approved – No. HP is low
| HAMUZA YAWE WALAKIRA. 256786907907. ntinda.0.353116,32.614632. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-05-01 | 2023-05-01 |  |  |  | User was trying to renew for another
| KELVIN ZZIWA. 256771026689. Rubaga:Nateete. . FTTH_20_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | [5 empty] | Mobilizing to start Civil works
| QASIM MOHAMED ABDI. 256783174800. Sekawa next to Tawqid Mosque.0.312077,32.572861. FTTH_10_M_O |  | Office Internet |  |  | Rak |  | Refunded | Office Internet (not on air) | 2023-05-03 | 2023-05-03 | 2023-05-08 |  |  | This customer requires 5 poles which is above DOA.
| Elizabeth Nakawunde. 256774002112. lungujja.0.309657,32.540489. FTTH_40_M_O |  | Office Internet |  |  | Pavicon |  | Refunded | Office Internet (not on air) | [5 empty] | High BOQ
| JEFFREY BAIGA.256773560174.kisaasi.0.361441,32.596655. FTTH_20_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | [5 empty] | Site out pf DOA range - 450m - 6 poles
| ANTONIO KAYONGO.256770340735.bulindo.0.41936,32.643994. FTTH_10_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | [5 empty] | Site out of DOA range - 700m 9 poles
| DERRICK WATOKER.256776233220.Bweyogerere Buto.0.348194,32.661714. FTTH_10_M_O |  | Office Internet |  |  | Enetworks |  | Refunded | Office Internet (not on air) | 2023-04-26 | 2023-05-05 |  |  |  | >1500 meters
| null null. 256763333045. kyaliwajja. . FTTH_20_M_O |  | Office Internet |  |  | Soliton |  | Refunded | Office Internet (not on air) | 2023-03-03 | 2023-03-03 | 2023-03-05 |  |  | Contact currently not available
| CANARY TWINOBUSINGYE.256771030992.abaita Ababiri Entebbe road.0.092247.32.498391. FTTH_20_M_O |  | Office Internet |  |  | Chrif |  | Refunded | Office Internet (not on air) | 2023-04-25 | 2023-05-03 | 2023-05-05 |  |  | High BOQ - sales looking for addittional customers
Formulas:
Date commissioned = [Customer commitment/Payment date]+2

## Relocation
Completion Month | Customer Name | P1/P2 | Total cost | FTTx type | Permit Process Application | Permit Granted | Contractor | Installation delay due to customer (days) | Installation Status | On-air status | Date logged | Customer commitment/Payment date | Date commissioned | Total MTTI (days) | MTTI after payment/Customer commitment | Remarks
January | null null. 256787478346. Mukono:Nasuuti.0.36048,32.745624 . FTTH_40_M_O | P2 | UGX 4,709,799.60 | Office Internet |  |  | Selmer | 0 | Done | Office Internet (on air) | 2022-12-19 | 2022-12-20 | 2023-01-02 | 14 | 13 | Network Freeze
| LAURAH KAYAGA. 256782032264. Buwate:Kungu.0.310761,32.578064 . FTTH_20_M_O | P2 | UGX 3,247,312 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2022-12-12 | 2022-12-20 | 2023-01-02 | 21 | 13 | Network Freeze
| FARHAN ABDI HASSAN. 256760592290. Rubaga:Kabusu Road.0.296088,32.551404 . FTTH_20_M_O | P1 | UGX 2,070,522.10 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2022-10-19 | 2022-12-26 | 2022-12-31 | 73 | 5 | Network Freeze
| Sulaiman Nattimba Fatuma 256773427227 Entebbe:Church Road 0.048655 ,32.468981 FTTH_40_M_O | P2 | UGX 5,146,096.20 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2022-12-23 | 2023-01-02 | 2023-01-02 | 10 | 0 | Network Freeze
| null null. 256778154517. Mbarara:Kabale - Mbarara Road.0.616224,30.654322 . FTTH_20_M_O | P2 | UGX 12,218,224 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2022-11-28 | 2022-12-08 | 2023-01-04 | 37 | 27 | Reassigned to ATX on 20th December. PO issue with ROntech
| null null. 256777444295. Mbarara:Buremba Road.0.607731,30.661851 . FTTH_20_M_O | P2 | UGX 12,218,224 | Office Internet |  |  | ATX | 4 | Done | Office internet (on air) | 2022-11-24 | 2022-12-15 | 2023-01-04 | 41 | 16 | Reassigned to ATX on 20th December. PO issue with ROntech
| SHARON NABUWULE. 256773687497. Kisaasi:Kyanja Ring Road.0.378259,32.599126 . FTTH_40_M_O | P2 | UGX 2,783,195.8 | Office Internet |  |  | Enetworks | 0 | Done | Office internet (on air) | 2022-11-03 | 2022-12-22 | 2023-01-03 | 61 | 12
| null null. 256781461023. Makerere:Bombo Road.0.34057,32.570327 . FTTH_20_M_O | P2 | UGX 3,789,082.00 | Office Internet |  |  | Cool Wave | 0 | Done | Office internet (on air) | 2023-01-02 | 2023-01-04 | 2023-01-05 | 3 | 1
| null null. 256760962789. Rubaga:Stensera Road.0.298869,32.601517 . FTTH_20_M_O | P2 | UGX 4,612,624.60 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2022-12-30 | 2023-01-03 | 2023-01-06 | 7 | 3
| HASSAN OSMAN MOHAMUD. 256787588487. Rubaga:Lubiri Ring Road.0.308213,32.570325 . FTTH_20_M_O | P2 | UGX 1,510,468.60 | Office Internet |  |  | Chrif | 9 | Done | Relocation ( On air) | 2022-09-27 | 2022-10-16 | 2023-01-05 | 100 | 72 | Relocation
| null null. 256778154517. Mbarara:Kabale - Mbarara Road.0.616224,30.654322 . FTTH_20_M_O | P2 | UGX 12,218,224 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2022-11-28 | 2022-12-08 | 2023-01-05 | 38 | 28 | Reassigned to ATX on 20th December - Consolidation delayed payment
| null null. 256783307541. Luzira:Port Bell road.0.353921,32.607822 . FTTH_20_M_O | P1 | UGX 2,363,651.0 | Office Internet |  |  | Enetworks | 0 | Done | Relocations ( On air) | 2023-01-03 | 2023-01-05 | 2023-01-06 | 3 | 1
| CIPLA QUALITY CHEMICALS. 256772789725. KANYANYA.0.369885,32.58359 . FTTH_40 | P1 | N/A | Office Internet (Postpaid) not on air |  |  | Seagate | 0 | Done | Relocations ( On air) | 2023-01-03 | 2023-01-09 | 2023-01-09 | 6 | 0
| null null. 256788254548. Bwebajja:Arkright City.0.183424,32.539219 . FTTH_20_M_O | P2 | UGX 3,357,296.60 | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2023-01-02 | 2023-01-02 | 2023-01-07 | 5 | 5
| null null. 256773155598. Najjanankumbi:Kampala Entebbe Road.0.295037,32.572762 . FTTH_40_M_O |  | UGX 3,792,869.10 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2023-01-02 | 2023-01-06 | 2023-01-09 | 7 | 3
| null null. 256773879175. Luzira:Mutungo Ring Road.0.338189,32.622669 . FTTH_20_M_O | P2 | UGX 4,091,795.0 | Office Internet |  |  | Enetworks | 0 | Done | Relocations ( On air) | 2023-01-02 | 2023-01-06 | 2023-01-07 | 5 | 1
| null null. 256772970641. Ntinda (Kiwatule - Naalya):Flamingo Close.0.357614,32.619044 . FTTH_40_M_O | P1 | UGX UGX 1,818,380 | Office Internet |  |  | Seagate | 0 | Done | Relocations ( On air) | 2022-12-19 | 2023-01-04 | 2023-01-06 | 18 | 2
| PETROLEUM AUTHORITY OF UGANDA. 256785980600. SALAAMA MUNYONYO.0.244253,32.617981 . FTTH_20 | P1 | N/A | Office Internet (Postpaid) not on air |  |  | ATX | 0 | Done | Relocations ( On air) | 2022-12-19 | 2023-01-09 | 2023-01-09 | 21 | 0 | User was active as prepaid now migrated to Postpaid
| ERIA BENJAMINE JJAGWE. 256782356690. Najjanankumbi:Kampala Entebbe Road.0.283677,32.568446 . FTTH_20_M_O | P2 | UGX 2,070,277.60 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2022-12-29 | 2023-01-03 | 2023-01-07 | 9 | 4 | civil works commenced today
| ROSEMARY KABASINGUZI. 256771270472. Entebbe:Nsamizi Road.0.06131,32.46136 . FTTH_40_M_O | P2 | N/A | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2022-11-26 | 2022-11-29 | 2023-01-07 | 42 | 39 | Pole erection and cable hauling done, traffic routing ongoing
| DANIEL ARINDA. 256775545901. Mbarara:High Street.-0.585049,30.678533 . FTTH_20_M_O | P2 | UGX 12,218,224 | Office Internet |  |  | ATX | 4 | Done | Relocations ( On air) | 2022-11-08 | 2022-12-15 | 2023-01-05 | 58 | 17 | Access denied
| null null. 256762811678. Najjanankumbi:Kampala Entebbe Road.0.288558,32.570014 . FTTH_20_M_O | P2 | UGX 2,114,920.10 | Office Internet |  |  | ATX | 10 | Done | Relocations ( On air) | 2022-11-25 | 2022-12-27 | 2023-01-09 | 45 | 3
| null null. 256775166621. Makerere:Sir Apollo Kaggwa Road.0.308021,32.570305 . FTTH_20_M_O | P1 | UGX 4,261,624 | Office Internet |  |  | Cool Wave | 0 | Done | Relocations ( On air) | 2023-01-03 | 2023-01-04 | 2023-01-06 | 3 | 2
| null null. 256788800515. Luzira:Old Butabika Road.0.315045,32.654657 . FTTH_20_M_O | P2 | UGX 12,389,758.2 | Office Internet |  |  | Enetworks | 0 | Done | Relocations ( On air) | 2022-12-29 | 2023-01-04 | 2023-01-06 | 8 | 2 | Above DOA >> Consolidated with null null. 256772122602. Luzira:Old Butabika Road.0.313644,32.653555 . FTTH_20_M who has not paid
| null null. 256772746557. Old Park:Luwum Street.0.307432,32.570534 . FTTH_40_M_O | P2 | UGX 2,049,221.00 | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2022-12-21 | 2023-01-04 | 2023-01-06 | 16 | 2
| null null. 256782400722. Kampala Downtown:Kyaggwe Road.0.317983,32.573507 . FTTH_20_M_O | P2 | UGX 2,397,628.10 | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2022-12-02 | 2022-12-28 | 2023-01-08 | 37 | 11
| null null. 256789463704. Nakasero Hill:Kyaggwe Road.0.315209,32.586937 . FTTH_20_M_O |  |  | Office Internet |  |  | Chrif | 11 | Done | Relocation ( On air) | 2022-12-05 | 2022-12-09 | 2022-12-28 | 23 | 8 | Cable waiting to be put inside, client has issues with the landlord
| ROBERT TURAHE. 256777968471. Kisaasi:Bahai Road.0.356995,32.583103 . FTTH_20_M_O | P1 | N/A | Office Internet |  |  | Seagate | 0 | Done | Relocations ( On air) | 2023-01-02 | 2023-01-05 | 2023-01-09 | 7 | 4
| null null. 256772432832. Bwebajja:Arkright City.0.353464,32.613416.FTTH_20_M_O 3-Jan-23 FTTO MTNFTTO72740213 | P1 | UGX 8,117,164.20 | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2023-01-03 | 2023-01-05 | 2023-01-10 | 7 | 5
| null null. 256783216649. Kisaasi:Kulambiro.0.379161,32.617861 . FTTH_20_M_O | P1 | UGX 1,336,890 | Office Internet |  |  | Seagate | 0 | Done | Relocations ( On air) | 2023-01-03 | 2023-01-09 | 2023-01-10 | 7 | 1
| null null. 256778542478. Rubaga:Lungujja.0.298393,32.536057 . FTTH_20_M_O | P2 | UGX 2,719,529.60 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2023-01-02 | 2023-01-05 | 2023-01-09 | 7 | 4
| null null. 256785137637. Rubaga:Rubaga Road.0.296561,32.556695 . FTTH_20_M_O | P2 | UGX 2,137,119.10 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2022-01-01 | 2023-01-07 | 2023-01-09 | 373 | 2
| null null. 256773344238. Ntinda (Kyambogo - Min Village):Martyrs Way.0.355279,32.616217 . FTTH_40_M_O | P2 | UGX 4,290,700 | Office Internet |  |  | Seagate | 0 | Done | Relocations ( On air) | 2022-12-28 | 2023-01-05 | 2023-01-09 | 12 | 4
| EZRA BALEERO DAVID MPAATA. 256789425020. Kampala Upper CBD:Kampala Road.0.314977,32.576966 . FTTH_40_M_O | P2 | UGX 2,913,408.00 | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2022-12-19 | 2023-01-02 | 2023-01-10 | 22 | 8
| null null. 256789748052. Seeta:Seeta Town.0.371023,32.710549 . FTTH_20_M_O | P2 | UGX 6,873,916.8 | Office Internet |  |  | Chrif | 3 | Done | Relocations ( On air) | 2022-12-12 | 2022-12-30 | 2023-01-10 | 29 | 8 | Consolidation delayed by another customer who didnt pay on time ( null null. 256789748052. Seeta:Seeta Town.0.371023,32.710549 . FTTH_20_M_O null null. 256783378924. Seeta:Seeta Town.0.370774,32.710902 . FTTH_20_M_O)
| null null. 256783378924. Seeta:Seeta Town.0.370774,32.710902 . FTTH_20_M_O | P2 | UGX 6,873,916.8 | Office Internet |  |  | Chrif | 3 | Done | Relocations ( On air) | 2022-12-05 | 2022-12-30 | 2023-01-10 | 36 | 8 | Consolidation delayed by another customer who didnt pay on time ( null null. 256789748052. Seeta:Seeta Town.0.371023,32.710549 . FTTH_20_M_O null null. 256783378924. Seeta:Seeta Town.0.370774,32.710902 . FTTH_20_M_O)
| JULIET NANDUJJA. 256772088897. Ntinda Bukoto:Kira Road.0.356203,32.611431 . FTTH_20_M_O |  | UGX 2,025,879.60 | Office Internet |  |  | Enetworks | 0 | Done | Relocations ( On air) | 2022-10-17 | 2023-01-06 | 2023-01-11 | 86 | 5
| null null. 256770944590. Ggaba:Ggaba Road.0.274553,32.616103 . FTTH_40_M_O | P2 | UGX 2,025,879.60 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2023-01-04 | 2023-01-09 | 2023-01-12 | 8 | 3
| null null. 256788120774. Kisaasi:Kyanja Ring Road.0.394091,32.598952 . FTTH_40_M_O | P2 | UGX 3,466,029 | Office Internet |  |  | Seagate | 0 | Done | Relocations ( On air) | 2022-12-30 | 2023-01-05 | 2023-01-13 | 14 | 8
| null null. 256788003468. Rubaga:Mengo.0.315243,32.564413 . FTTH_20_M_O | P2 | UGX 3,494,940 | Office Internet |  |  | ATX | 0 | Done | Relocations ( On air) | 2022-11-18 | 2023-01-03 | 2023-01-11 | 54 | 8
| JAPHETH GALIWANGO. 256785787894. Bwebajja:Kajjansi.0.231136,32.541693 . FTTH_20_M_O | P1 | UGX 1,479,343.60 | Office Internet |  |  | Chrif | 0 | Done | Relocations ( On air) | 2022-11-15 | 2023-01-05 | 2023-01-12 | 58 | 7
| Saviour Najuna. 256789843297. Makindye:Lukuli Road.0.289925,32.585048 . FTTH_20_M_O | P1 | UGX 1,469,070.60 | Office Internet |  |  | Chrif | 0 | Done | Relocation ( On air) | 2022-03-15 | 2023-01-13
| null null. 256786216613. Rubaga:Kabusu Road.0.298534,32.535853 . FTTH_20_M_O | P1 | UGX 6,688,824 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2022-12-30 | 2023-01-12 | 2023-01-15 | 16 | 3
| null null. 256761134101. Kampala Upper CBD:Kampala Road.0.313745,32.580151 . FTTH_20_M_O |  |  | Office Internet |  |  | Chrif | 15 | Done | Office internet (on air) | 2022-12-12 | 2022-12-14 | 2023-01-14 | 33 | 16 | Contact is not available
| ATC. 256780140632. Kasasiro Luzira.0,0 . FTTH_20 | P2 | UGX 8,505,005.6 | Office Internet ( Postpaid) |  |  | Enetworks | 0 | Done | Office Internet (Postpaid) on air | 2022-11-29 | 2023-01-17 | 2023-01-17 | 49 | 0 | Not available during the Weekend , to close on 10/01/23
| null null. 256773805845. Entebbe:Bugonga Road.0.053028,32.469192 . FTTH_20_M_O | P1 | N/A | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2023-01-04 | 2023-01-10 | 2023-01-16 | 12 | 6
| null null. 256774231254. Kampala Upper CBD:Kampala Road.0.331018,32.593107 . FTTH_20_M_O | P2 | UGX 2,129,292 | Office Internet |  |  | Cool Wave | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-16 | 2023-01-17 | 5 | 1
| SUMANT KUMAR KUMAR. 256775543208. Ntinda Bukoto:Old Kira Road.0.348805,32.59889 . FTTH_20_M_O | P2 | UGX 2,045,966.5 | Office Internet |  |  | Enetworks | 0 | Done | Office internet (on air) | 2023-01-12 | 2023-01-16 | 2023-01-17 | 5 | 1
| null null. 256773805845. Entebbe:Bugonga Road.0.053028,32.469192 . FTTH_20_M_O | P2 | UGX 2,811,716.10 | Office Internet |  |  | ATX | 0 | Done | Office internet (on air) | 2023-01-04 | 2023-01-10 | 2023-01-16 | 12 | 6
| DAVID MUTAAGA. 256773248700. Entebbe:Nakiwogo Road.0.07347,32.455921 . FTTH_20_M_O |  |  | Office Internet |  |  | Chrif | 8 | On Hold | Office Internet (not on air) | 2022-08-18 | 2022-08-25 |  |  |  | Consolidated with ANGELLA BABIRYE. 256777773749. Entebbe:Nakiwogo Road.0.075317,32.454412 . FTTH_20_M_O, DAVID MUTAAGA. 256773248700. Entebbe:Nakiwogo Road.0.07347,32.455921 . FTTH_20_M_O, AIDAH MINDE. 256783885405. Entebbe:Uringi Cres Road.0.074963,32.457162 . FTTH_40_M_O
| ANGELLA BABIRYE. 256777773749. Entebbe:Nakiwogo Road.0.075317,32.454412 . FTTH_20_M_O |  |  | Office Internet |  |  | Chrif | 8 | On Hold | Office Internet (not on air) | 2022-08-20 | 2022-08-26 |  |  |  | Consolidate with Aisha Minde, David Mutaaga and Angella Babirye
| HALIMO AHMED SHIRE. 256779221889. Rubaga:Albert Cook Road.0.311073,32.555381 . FTTH_20_M_O |  |  | Office Internet |  |  | Cool Wave | 6 | On Hold | Office Internet (not on air) | 2022-09-06 | 2022-09-13 |  |  |  | Customer not answering several call attempts/Waiting for FHLS, commissioning tomorrow 20.09.2022/Right of way (ROW), the client to agree with the landlord for works to proceed
| JACKSON JOHN ONYANGO. 256782827627. Kisaasi:Bahai Road.0.367615,32.592287 . FTTH_20_M_O |  |  | Office Internet |  |  | Seagate | 8 | On Hold | Office Internet (not on air) | 2022-09-19 | 2022-09-26 |  |  |  | Waiting For Mary Birungi, Patricia Nalwanga and Sulaiman Katongole to pay
| JEAN PAUL GOLDRING (Emmanuel kayomoati) . 256773150188. Entebbe:Uringi Cres Road.0.069184,32.45825 . FTTH_20_M_O |  |  | Office Internet |  |  | Rontech |  | Done | Office Internet (not on air) | 2022-08-09 | 2022-09-29 |  |  |  | Reassigned to Rontech on 30th Sept/Error on Portal
| PAUL KEVIN KASIRYE. 256778415015. Mbarara:Buremba Road.-0.605646,30.671935 . FTTH_20_M_O |  |  | Office Internet |  |  | Rontech |  | On Hold | Office Internet (not on air) | 2022-10-15 | 2022-10-24 |  |  |  | Band width insufficiency.
| Valentina Revelli. 256770891529. Tank hill, Muyenga.0,0 . FTTH_20 |  |  | Office Internet ( Postpaid) |  |  | Rontech |  | On Hold | Office Internet (Postpaid) not on air | 2022-10-12 | N/A |  |  |  | Customer has requested for communication/Sent back to EBU to address with the account manager
| KEVIN BAGGOTTE. 256787518736. Entebbe:Church Road.0.063436,32.455294 . FTTH_20_M_O |  |  | Office Internet |  |  | Chrif | 6 | Refunded | Office Internet (not on air) | 2022-10-25 | 2022-11-10 |  |  |  | 1.2kms from cable
| null null. 256784286700. Kampala Downtown:Kyaggwe Road.0.304026,32.570226 . FTTH_40_M_O |  |  | Office Internet |  |  | Chrif |  | On Hold | Office Internet (not on air) | 2022-11-14 | 2022-11-17 |  |  |  | Not feasible, loking for addittional customers
| null null. 256787000684. Rubaga:Lubiri Ring Road.0.307219,32.565633 . FTTH_20_M_O |  |  | Office Internet |  |  | ATX |  | Done | Office Internet (not on air) | 2022-11-24 | 2022-11-28 |  |  |  | Second router for ABDALLE ADAN DAUD he says he will call us for commissioning it when ready
| MTN INTERNAL STAFF - ESTHER ATUKUNDA. 256772122531. NAKASERO.0,0 . FTTH_20 |  |  | Office Internet ( Postpaid) |  |  | Chrif | 10 | On Hold | Office Internet (Postpaid) not on air | 2022-11-21 | 2022-11-24 |  |  |  | STHER ATUKUNDA- No fiber in hardware city, still devising means of accessing the building with the MTN fiber.
| FADUMO ABDIAZIZ HUSSEIN. 256761404801. Rubaga:Mengo.0.308403,32.55769 . FTTH_20_M_O | P2 | UGX 3,575,832.10 | Office Internet |  |  | ATX | 5 | On Hold | Relocation (not on air) | 2022-10-11 |  |  |  |  | ROW issue
| null null. 256762429152. Bwebajja:Kitende.0.058778,32.473499 . FTTH_20_M_O | P2 | N/A | Office Internet |  |  | Chrif | 9 | WIP | Office Internet (not on air) | 2023-01-04 | 2023-01-07 |  |  |  | Survey set on 11- Jan-23/Survey re scheduled for 18.1.2023
| null null. 256783740055. Namuwongo:Kisugu Road.0.337853,32.543086 . FTTH_20_M_O | P2 | UGX 6,688,824.20 | Office Internet |  |  | ATX |  | On Hold | Office Internet (not on air) | 2022-12-28 | 2023-01-06 |  |  |  | High BOQ, Get more Clients/We have ROW challenges with client below - the neighbours have cut our cable and want him to settle their differences first
| null null. 256782854160. Soroti:Haridas Road.1.717988,33.621647 . FTTH_40_M_O | P2 | N/A | Office Internet |  |  | ATX | 7 | Refunded | Office Internet (not on air) | 2022-12-14 | 2022-12-30 |  |  |  | Route being reviewed, pending updated BOQ
| null null. 256782647213. Kampala Upper CBD:Colville Street.0.313432,32.583845.FTTH_20_M_O | P2 | UGX 2,670,011.60 | Office Internet |  |  | Chrif |  | On Hold | Office Internet (not on air) | 2022-12-14 | 2022-12-29 |  |  |  | High BOQ, Get more Clients, 0786216613 yet to pay
| null null. 256776291440. Bwebajja:Arkright City.0.353464,32.613416.FTTH_20_M_O | P2 | UGX 8117164.2 | Office Internet |  |  | Chrif |  | Done | Office Internet (not on air) | 2023-01-03 | 2023-01-05 |  |  |  | Customer to communicate when ready for commissioning
| null null. 256760055140. Bugolobi:Port Bell road.0.189375,32.529319 . FTTH_40_M_O | P1 | N/A | Office Internet |  |  | Cool Wave | 7 | On Hold | Office Internet (not on air) | 2023-01-04 | 2023-01-11 |  |  |  | where we supposed to erect our pole it's a parking lot so we opted for a Sunday to reduce on chances of damaging people's vehicles
| null null. 256783869342. Nsambya:Kabega Road.0.2976,32.590401 . FTTH_40_M_O | P1 | UGX 2,495,620.60 | Office Internet |  |  | Chrif | 4 | On Hold | Office Internet (not on air) | 2023-01-04 | 2023-01-10 |  |  |  | Onhold, r.o.w challenge, we’re handling with the client possibly tomorrow pole erection will resume
| ANTHONY KIPKURUI CHERUIYOT. 256761000259. Najjanankumbi:Lubowa Terrace Road.0.222319,32.56261 . FTTH_40_M_O | P2 | N/A | Office Internet |  |  | ATX |  | Refunded | Office Internet (not on air) | 2022-08-17 | 2022-12-22 |  |  |  | This client requires 6poles and 470m cable which makes him not feasible due to high boq More sales should be done around the location
| null null. 256772575884. Rubaga:Lubowa Terrace Road.0.287964,32.563066 . FTTH_20_M_O | P2 | UGX 2,048,323.10 | Office Internet |  |  | ATX |  | WIP | Office Internet (not on air) | 2023-01-10 | 2023-01-16 |  |  |  | Civil works ongoing
| BRENDA AMONG. 256776587629. Kira:Namugongo Road.0.365417,32.653672 . FTTH_20_M_O | P2 | UGX 1,989,625 | Office Internet |  |  | Seagate | 33 | WIP | Office Internet (not on air) | 2022-12-02 | 2023-01-04 |  |  |  | Delayed by customer who first said not interested in the service and yet they had paid
| JESCA MUHEBWA. 256788809554. Makerere:Sir Apollo Kaggwa Road.0.33839,32.548664 . FTTH_20_M_O | P2 | UGX 4,901,028 | Office Internet |  |  | Cool Wave | 10 | On Hold | Office Internet (not on air) | 2022-10-07 | 2023-01-05 |  |  |  | Customer re arrangement since they they were uanvailable for survey
| null null.256775380000.Kololo:KAR Road.0.324178,32.598766.FTTH_20_M_O | P2 | UGX 1,729,360 | Office Internet |  |  | Cool Wave |  | Done | Office Internet (not on air) | 2023-01-13 | 2023-01-16 | 2023-01-18 |  |  | Customer changed location to Parliament Avenue thus delaying the survey
| Tusiime Eseza. 256770643625. Nakasero Hill:Buganda Road.0.317548,32.576783 . FTTH_20_M_O | P2 | UGX 2,426,134 | Office Internet |  |  | Cool Wave |  | WIP | Office Internet (not on air) | 2023-01-12 | 2023-01-17 |  |  |  | Civil works ongoing
| null null. 256784340770. Nsambya:Nsambya Estate Road.0.299329,32.591531 . FTTH_20_M_O | P2 | UGX 3,482,660.60 | Office Internet |  |  | Chrif |  | WIP | Office Internet (not on air) | 2023-01-11 | 2023-01-16 |  |  |  | Civil works ongoing
| null null. 256782541119. Bugolobi:Port Bell road.0.318535,32.627569 . FTTH_20_M_O | P2 | UGX 3,149,483.0 | Office Internet |  |  | Enetworks |  | WIP | Office Internet (not on air) | 2023-01-11 | 2023-01-17 |  |  |  | Civil works ongoing
| Brandon. 256782129261. Ntinda (Kyambogo - Min Village):Kyambogo Road.0.342282,32.629379 . FTTH_20_M_O | P2 | UGX 4,217,391.0 | Office Internet |  |  | Seagate |  | WIP | Office Internet (not on air) | 2023-01-10 | 2023-01-16 |  |  |  | Civil works ongoing
| Margaretha Wilhelmina Geluka. 256787745145. Makindye:Kizungu Road.0.340207,32.588781 . FTTH_20_M_O | P2 | UGX 4,251,680.60 | Office Internet |  |  | Chrif |  | WIP | Office Internet (not on air) | 2023-01-10 | 2023-01-16 |  |  |  | Civil works ongoing
| null null. 256762486291. Bwebajja:Kitende.0.404778,32.543815 . FTTH_20_M_O | P2 | 9,124,566.20 | Office Internet |  |  | Chrif |  | WIP | Office Internet (not on air) | 2023-01-10 | 2023-01-16 |  |  |  | Civil works ongoing
| null null. 256775833909. Fort Portal:Fort Portal Mpondwe Road.0.652979,30.27168 . FTTH_20_M_O | P2 | UGX 3,156,177.10 | Office Internet |  |  | ATX |  | WIP | Office Internet (not on air) | 2023-01-10 | 2023-01-17 |  |  |  | Civil works ongoing
| null null. 256783375364. Entebbe:Hill Lane.0.225029,32.555774 . FTTH_40_M_O | P1 | 2,181,517 | Office Internet |  |  | ATX |  | WIP | Office Internet (not on air) | 2023-01-17 | 2023-01-20 |  |  |  | Civil works ongoing
| SULAIMAN AGABA. 256777069580. Ntinda Bukoto:Semawata Road.0.346906,32.615575 . FTTH_20_M_O | P2 | 2,041,152.6 | Office Internet |  |  | Seagate |  | WIP | Office Internet (not on air) | 2023-01-16 | 2023-01-19 |  |  |  | Civil works ongoing
| null null. 256787527936. Bugolobi:Port Bell road.0.327587,32.612277 . FTTH_40_M_O | P2 | 2,460,692.00 | Office Internet |  |  | Enetworks |  | WIP | Office Internet (not on air) | 2023-01-14 | 2023-01-19 |  |  |  | Civil works ongoing
| null null. 256787441429. Rubaga:Mengo.0.321932,32.562543 . FTTH_20_M_O | P2 | 3,580,272 | Office Internet |  |  | ATX |  | WIP | Office Internet (not on air) | 2023-01-12 | 2023-01-19 |  |  |  | Civil works ongoing
| null null. 256785538779. Ntinda (Kyambogo - Min Village):Martyrs Road.0.342538,32.618264 . FTTH_40_M_O | P2 | N/A | Office Internet |  |  | Enetworks |  | WIP | Office Internet (not on air) | 2023-01-12 | 2023-01-18 |  |  |  | Civil works ongoing
| null null. 256772468653. Nakasero Hill:Buganda Road.0.317475,32.577042 . FTTH_20_M_O | P2 | 2,265,989.00 | Office Internet |  |  | Cool Wave |  | WIP | Office Internet (not on air) | 2023-01-12 | 2023-01-20 |  |  |  | Civil works ongoing
| null null. 256778891442. Muyenga:Kansanga Kiwafu Road.0.287562,32.620918 . FTTH_40_M_O | P2 | 2,831,240.60 | Office Internet |  |  | ATX |  | WIP | Office Internet (not on air) | 2023-01-11 | 2023-01-18 |  |  |  | Civil works ongoing
| NAMAGGA JOAN. 256773391930. Mbale:Republic Street.1.071921,34.180844 . FTTH_20_M_O | P2 | TBC | Office Internet |  |  | Seagate |  | Done | Relocation ( On air) | 2022-05-12 |  | 2023-02-13
| JOHN BAPTIST KIGGUNDU. 256775061276. Rubaga:Stensera Road.0.311897,32.579929 . FTTH_20_M_O | P2 | UGX 1,998,071 | Office Internet |  |  | Chrif |  | Done | Relocation ( On air) | 2022-06-16 |  | 2023-01-29 | 227 | 44955 | Mobilizing to start Civil works
| JOSHUA MENYA. 256789198409. Ntinda Bukoto:Semawata Road.0.349583,32.614145 . FTTH_20_M_O |  | 5093923 | Office Internet |  |  | Seagate |  | Done | Relocation ( On air)
| null null. 256781088363. Bugolobi:Luthuli Avenue. 0.353988,32.607839. FTTH_20_M_O |  | TBC | Office Internet |  |  | Chrif |  | Done | Relocation ( On air) | 2023-01-24 |  | 2023-03-05
| FRED MULIIRA. 256771430358. Makerere:Bombo Road. 0.332331,32.574053. FTTH_20_M_O |  | 588154.6 | Office Internet |  |  | Chrif |  | Done | Relocation ( On air) | 2023-04-12 |  | 2023-04-14
| GEOFFREY ONYANGO.256786303012.Bweyogerere:Bweyogerere.0.364032,32.66475.FTTH_40_M_O |  |  | Office Internet |  |  | Enetworks |  | Done | Relocation ( On air) | 2022-08-31 |  | 2023-05-06

## Summary
EBU Requests |  | Survey Status |  | BOQ Submitted |  | Business Case or BOQ Approved |  | Customer payment and Commitment |  | Installation status |  | On-Air |  | Acceptance status |  | FTTH (Relocation)
FTTO | 379 | Completed | 380 | FTTP/B | 0 | Pending review | 3 | Office internet (APP.) Paid | 180 | ZTE Upgrade | 0 | Office Internet (on air) | 727 | PAC Done | 312
|  | FTTO WIP | 0 |  |  | Office Internet approved | 278 | Office Internet (APP.) Pending | 99 | On Hold | 32 | Office Internet (Postpaid) on air | 12 | FAC Done | 0 | Relocation ( On air) | 9
|  | FTTO ( Postpaid ) | 2 |  |  | Office Internet rejected | 99 |  |  | WIP | 91 |  |  |  |  | Relocation (not on air) | 1
|  | On Hold | 1 | [6 empty] | Refunded | 118
[10 empty] | Done | 763
[10 empty] | Back to EBU | 0
Totals | 379 |  | 383 |  |  |  | 380 |  | 279 |  |  |  | 739
Await installation | [12 empty] | 559
Civil works ongoing

## CTIO weekly report
| Requests received | Office Internet Approved for payment | P2 Pending Survey | Pending Access | WIP | TOTAL PENDING | Completed by Technology | On AIR | Pending Go live (ZTE) | ZTE Upgrade | Back to EBU | Office internet on air | Relocations on air | Net tech adds a week | Net on air a week | Refunded
Week 1 | 25 | 9 | 17 | 0 | 4 | 21 | 6 | 4 | 2 | 0 | 0 | 4 | 0 | 6 | 4 |  | 6th Jan
Week 2 | 70 | 42 | 6 | 0 | 8 | 14 | 43 | 39 | 4 | 0 | 0 | 39 | 2 | 37 | 35 |  | 13th Jan
Week 3 | 153 | 87 | 12 | 10 | 9 | 31 | 62 | 56 | 6 | 0 | 0 | 56 | 3 | 19 | 17 | 3 | 20th Jan
Week 4 | 196 | 118 | 19 | 10 | 10 | 39 | 82 | 76 | 6 | 0 | 0 | 76 | 3 | 20 | 20 | 3 | 27th Jan
Week 5 | 242 | 152 | 17 | 13 | 17 | 47 | 98 | 93 | 5 | 0 | 0 | 93 | 4 | 16 | 17 | 4 | 3rd Feb
Week 6 | 343 | 221 | 28 | 1 | 26 | 55 | 126 | 122 | 4 | 0 | 0 | 122 | 4 | 28 | 29 | 4 | 10th Feb
Week 7 | 378 | 274 |  | 3 | 19 | 28 | 181 | 177 | 4 | 0 | 0 | 177 | 5 | 55 | 55 | 6 | 17th Feb
Week 8 | N/A | N/A | 0 | 6 | 22 | 28 | 236 | 220 | 16 | 0 | 0 | 236 | 5 | 55 | 59 | 11 | 24th Feb
Week 9 | N/A | N/A | 2 | 12 | 16 | 30 | 291 | 291 | 0 | 0 | 0 | 291 | 5 | 55 | 55 | 15 | 3rd March
Week 10 | N/A | N/A | 2 | 12 | 19 | 33 | 312 | 308 | 4 | 0 | 0 | 308 | 5 | 21 | 17 | 20 | 10th March
Week 11 | N/A | N/A | 2 | 9 | 22 | 33 | 350 | 342 | 8 | 0 | 0 | 342 | 6 | 38 | 34 | 29 | 17th March
Week 12 | N/A | N/A | 2 | 9 | 42 | 53 | 372 | 367 | 5 | 0 | 0 | 367 | 6 | 22 | 25 | 32 | 24th March
Week 13 | N/A | N/A | 2 | 13 | 38 | 53 | 420 | 411 | 9 | 0 | 0 | 411 | 6 | 48 | 44 | 38 | 31st March
Week 14 | N/A | N/A | 0 | 15 | 37 | 52 | 455 | 448 | 7 | 0 | 0 | 448 | 7 | 35 | 37 | 40 | 7th April
Week 15 | N/A | N/A | 0 | 15 | 28 | 43 | 489 | 477 | 12 | 0 | 0 | 477 | 8 | 34 | 29 | 46 | 14th April
Week 16 | N/A | N/A | 2 | 19 | 79 | 100 | 565 | 554 | 11 | 0 | 0 | 554 | 8 | 76 | 77 | 74 | 25th April
Week 17 | N/A | N/A | 2 | 27 | 60 | 89 | 628 | 610 | 18 | 0 | 0 | 610 | 8 | 63 | 56 | 87 | 28th April
Week 18 | N/A | N/A | 0 | 36 | 73 | 109 | 691 | 677 | 14 | 0 | 0 | 677 | 8 | 63 | 67 | 107 | 5th May
Week 19 | N/A | N/A | 0 | 32 | 91 | 123 | 763 | 739 | 24 | 0 | 0 | 739 | 9 | 72 | 62 | 118 | From 6th May

## GM EBU report
Reason for rejection | Wk1 | Wk2 | Wk3 | Wk4
EBU to follow up, client to communicate | 12
Not interested | 13
Not applicable | 0
Not reachable | 12
Not feasible, EBU to pitch SME | 64
Totals | 101
P1/P2 | Wk1 | Wk2 | Wk3 | Wk4
P1
P2
not feasible

## BDM Meeting
| Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | YTD
Monthly Applications | YTD: YTD Applications | 0
Monthly Sales Target | 0 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | YTD Sales Target | 1200
MTD Sales Achievement | YTD: YTD Sales Achievement | 0
MTD % Achievement | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | YTD % Achievement | 0%
Monthly Activation Target | 138 | 146 | 155 | 164 | 173 | 184 | 194 | 206 | 218 | 231 | 244 | 259 | YTD Activation Target | 2312
MTD Activation Achievement | Jan: 87; Feb: 176; March: 148; April: 37; YTD: YTD Activation Achievement | 448
MTD % Achievement | 63.04% | 120.5% | 95.48% | 22.56% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | YTD % Achievement | 19.38%
Total Links
OPERATIONS
Customers Pending Payment | N/A | 47 | 127 | 319 | 479 | 620 | 784 | 923 | 1121 | 1315 |  | 1366
Pending Installation / in progress | N/A | 11 | 10 | 12 | 17 | 27 | 18 | 44 | 47 | 35 |  | 25
Pending Commissioning | N/A | 0 | 4 | 6 | 4 | 2 | 1 | 0 | 7 | 7 |  | 1
Customers pending access and neighbour payment | N/A | 1 | 8 | 3 | 6 | 10 | 8 | 9 | 9 | 24 |  | 12
Opted out - Back to EBU for refund | N/A | 0 | 3 | 7 | 15 | 20 | 28 | 33 | 41 | 57 |  | 60
Pending ZTE upgrades | N/A | 2 | 4 | 2 | 1 | 2 | 1 | 0 | 3 | 2 |  | 0